## ADM Hotspot Inventory
[11 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [23 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan
[41 empty] | Select Yes or No | Select one: Critical Infrastructure, Detailed Design, Fast-Track, or Quick Win | Select one: Permanent, Interim, or Temporary | Please specify if additional budget is required for this hotspot (Yes/No) | Provide the requested budget for each applicable hotspot. If a single project spans multiple hotspots, list the budget only once under the primary hotspot. For all other covered hotspot entries, replace the budget with: "Included in Hotspot #X budget." | Provide the current rainfall design event, including the return period | Provide the existing network’s technical or hydraulic capacit | Provide the future or target rainfall design event, including the return period | Provide the future or target network capacity after the planned intervention | Provide the estimated floodwater volume managed by network after intervention | Provide the expected number of hours required for floodwater to recede after intervention | Revise the planned mobilization date | Revise the planned Phase 1 completion date | Revise the planned completion date | Select one: Contractor Design phase, Parsons Verification Phase, IDAS Review Phase, Municipality Permitting Phase, Implementation phase, Hand Over Phase | Select Yes or No. Enter Yes only after formal approval has been issued. | Provide a brief summary on the design solution | Provide the actual mobilization date (only after actual mobilization) | Provide the actual completion date (only after actual completion) | Select one: Not Started, On Track, Delayed, or Completed | Provide the full name of the accountable IDD owner.
# | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Pumps_Budget_AED | Suction Tankers (NO'S) | TOTAL Suction Tankers Cost per hour (AED) - Duty Mode | Suction Tankers cost (AED) - For ONLY 9 days Only (standby mode) | Suction Tankers cost (AED) For 12 days -Duty mode | Suction Tankers Budget Required (AED) | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD Intervention Planned | IDD_Design_Category | Type of Intervention | Additional Budget Requirment | Additional Budget Requested | Hotspot Network Rain Design Event (Current) | Hotspot Network Design Technical Capacity (Current) | Hotspot Network Rain Design Event (Future) | Hotspot Network Design Technical Capacity (Future) | Flood Volume Capacity after Intervention | Associated recovery time after intervention | Planned_IDD_Mobilization_Date | Critical Infrastructure Area Phase1 Solution Completion Date | Planned_IDD_Completion_Date | Project Stage | Approval from IDAS secured (Yes/No) | Design Description | Actual_Mobilization_Date | Actual_Completion_Date | Intervention status | IDD_Owner_Name | Column1
1 | Al Shahama | Al Shahama Tunnel | 24.4927 | 54.6493 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-25 |  | 2026-12-11 | Contractor Design Completed | Yes |  |  |  | 47 | Parsons
2 | Al Shahama | شارع الشيخ زايد بن سلطان | 24.4858 | 54.6449 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-12-08 | Contractor Design Completed | Yes | Propose a linear pond with free flow towards the pond to collect and temporarily store stormwater runoff, reducing surface water accumulation and mitigating flooding. |  |  | 49 | Parsons
3 | Al Shahama | مجمع الجسور ياس | 24.5378 | 54.6848 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-09-11 | 2026-12-31 | Construction Phase | Yes | Provide geocell storage with suitable ground grading and inlets between the geocells to direct and retain stormwater runoff, minimizing water ponding and reducing flooding. | 2026-09-04 |  | 119 | Parsons
4 | Al Shahama | نفق الشهامة الجديدة المؤدي الى ديرفيلدز مول | 24.5611 | 54.6953 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-25 |  | 2027-01-30 | Contractor Design Completed | Yes |  |  |  | 36 | Parsons
5 | Al Shahama | جسر الشهامة نادي الوحدة | 24.7287 | 54.8168 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-23 |  | 2026-12-30 | Contractor Design Completed | Yes | Provide a stormwater network with geocell storage to manage and temporarily retain runoff, minimizing surface water accumulation and alleviating flooding. |  |  | 37 | Parsons
6 | Al Shahama | نفق كيزاد | 24.4622 | 54.68 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 |  | 2026-12-31 | Concept Design and IDAS review stage | No |  |  |  | 107 | AECOM
7 | Al Shahama | روضة الريف – شارع الشهد | 24.7304 | 54.7793 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 | 2 |  | 0 | [5 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 |  | 800000 | 0 | [7 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-17 |  | 2026-12-21 | Contractor Design Completed | Yes |  |  |  | 34 | Parsons
8 | Al Shahama | خليفة الصناعية - شارع غناضة | 24.4185 | 54.7241 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 4 |  | 4 | 0 | [5 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 |  | 2026-10-08 | Concept Design and IDAS review stage | No |  |  |  | 23 | AECOM
9 | Al Shahama | منطقة الفلاح 4 | 24.4213 | 54.7472 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-01 |  | 2027-01-23 | Contractor Design Completed | Yes | Provide inlets, pipelines, and a geocellular tank area to capture and temporarily retain stormwater, limiting surface water build-up and alleviating flooding |  |  | 83 | Parsons
10 | Al Shahama | منطقة الفلاح 1 | 24.4989 | 54.6024 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-04 |  | 2027-01-23 | Contractor Design Completed | Yes | Introduce inlets, pipelines, and a geocellular tank area to convey and temporarily retain stormwater runoff, reducing surface water build-up |  |  | 80 | Parsons
11 | Al Shahama | ياس الحي الاماراتي | 24.5313 | 54.6376 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-10 |  | 2027-01-13 | Contractor Design Completed | Yes |  |  |  | 34 | Parsons
12 | Al Shahama | الباهية - شارع عجيج – الباهية مدرسة أميتي | 24.5934 | 54.6515 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-21 |  | 2026-12-29 | Contractor Design Completed | Yes | Establish a linear pond and incorporate check dams along its length, suitably arranged to suit the longitudinal slope and help manage the movement and temporary retention of stormwater. |  |  | 38 | Parsons
13 | Al Shahama | شارع عجيج - الصدر | 24.3736 | 54.5229 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-29 |  | 2027-02-16 | Concept Design and IDAS review stage | No |  |  |  | 171 | AECOM
14 | Mussafah | شارع سلطان بن محمد القبيسي - بعد الجسر المؤدي الى المصفح- الأول | 24.3789 | 54.5129 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
15 | Mussafah | مدينة الامارات الانسانية | 24.3656 | 54.4832 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
16 | Mussafah | Sector 17 | 24.3779 | 54.5221 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
17 | Mussafah | Sector 2 | 24.3736 | 54.4826 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
18 | Mussafah | Sector 15 | 24.3792 | 54.5178 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
19 | Mussafah | Sector 1 | 24.3825 | 54.5234 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
20 | Mussafah | Sector 1 | 24.3941 | 54.5186 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
21 | Zayed | مدخل مصفح القادم من شارع الخليج العربي | 24.3686 | 54.4914 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-09-11 | 2027-01-12 | Construction Phase | Yes |  | 2026-08-30 |  | 130 | Parsons
22 | Mussafah | Sector 9 | 24.2884 | 54.5646 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  | 122 | Parsons
23 | Mussafah | دوار دينا تريد | 24.2934 | 54.581 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | [5 empty] | 777600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-04 |  | 2027-01-15 | Contractor Design Phase |  |  |  |  | 72 | Parsons
24 | Mussafah | مستودعات البلدية | 24.1494 | 54.4205 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | [5 empty] | 280800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-12-11 | Construction Phase | Yes | Propose GRP lines with concrete bedding, installing side-entry inlets, and connecting discharge chambers. Demolition and rehabilitation encompass removing or decommissioning existing 300mm lines, flushing drains, repairing reinforced concrete structures, adjusting inlets, and fully reinstating all impacted asphalt, kerbstones, and interlocking pavement tiles. | 2026-08-20 |  | 52 | Parsons
25 | Mussafah | طريق حميم | 24.3314 | 54.7084 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-15 |  | 2027-01-15 | Contractor Design Completed | Yes | Reconstruct the two roads at higher elevations to improve surface water conveyance and reduce the risk of flooding |  |  | 61 | Parsons
26 | Al Wathbah | مدينة الرياض - شارع طوي القايمة | 24.3432 | 54.7578 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-30 |  | 2026-12-13 | Contractor Design Phase |  |  |  |  | 74 | Parsons
27 | Al Wathbah | مدينة الرياض - شارع الخير | 24.3257 | 54.7446 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-18 |  | 2026-12-13 | Contractor Design Phase |  |  |  |  | 56 | Parsons
28 | Al Wathbah | مدينة الرياض - شارع العصري بن حمودة الظاهري | 24.333 | 54.7652 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-18 |  | 2026-12-13 | Contractor Design Phase |  |  |  |  | 56 | Parsons
29 | Al Wathbah | مدينة الرياض -شارع الرياض | 24.3273 | 54.7042 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 0 |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-18 |  | 2026-12-13 | Contractor Design Phase |  |  |  |  | 56 | Parsons
30 | Al Wathbah | مدينة الرياض -شارع النهضة | 24.3307 | 54.7001 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-18 |  | 2026-12-13 | Contractor Design Phase |  |  |  |  | 56 | Parsons
31 | Al Wathbah | مدينة الرياض -شارع الميثاق | 24.3364 | 54.7356 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-08 |  | 2026-12-06 | Contractor Design Phase |  |  |  |  | 59 | Parsons
32 | Al Wathbah | مدينة الرياض - شارع سيح القطع | 24.3415 | 54.7524 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 4 |  |  | 4 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-12 |  | 2027-01-30 | Contractor Design Phase |  |  |  |  | 79 | Parsons
33 | Al Wathbah | مدينة الرياض - شارع الصنوبر | 24.3732 | 54.729 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 |  |  | 3 | [5 empty] | 259200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-08 |  | 2026-12-13 | Contractor Design Phase |  |  |  |  | 66 | Parsons
34 | Al Wathbah | شارع الشيخ محمد بن راشد | 24.3037 | 54.6711 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 20 | 5000 | 540000 | 1440000 | 1980000 |  |  |  | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-09-14 | Contractor Design Phase |  |  |  |  | 6 | Parsons
35 | Al Wathbah | خلف مسلخ بني ياس | 24.3535 | 54.649 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-21 |  | 2026-10-02 | Contractor Design Phase |  |  |  |  | 11 | Parsons
36 | Al Wathbah | الشوامخ - شارع خضيرمان | 24.3505 | 54.6802 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-09 |  | 2027-01-23 | Contractor Design Phase |  |  |  |  | 75 | Parsons
37 | Al Wathbah | الشوامخ - مدخل ومخرج المزن | 24.3855 | 54.6702 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-01 |  | 2027-01-23 | Contractor Design Completed | Yes | Create local depressions with a lifting station and emptying lines to collect, raise, and discharge accumulated stormwater, reducing surface water build-up |  |  | 83 | Parsons
38 | Al Wathbah | شارع الشوامخ | 24.3843 | 54.6745 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 |  | 2026-09-07 | Construction Phase | Yes | Enhance existing inlets and pipelines and upgrade the current network to improve stormwater conveyance and reduce surface water accumulation | 2026-06-13 |  | 86 | Parsons
39 | Al Wathbah | دوار - الشوامخ 12 | 24.3221 | 54.749 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 |  | 2026-09-08 | Construction Phase | Yes | Propose enhanced inlets and pipelines. Upgrade the existing network. Propose sub-surface collection tank. | 2026-06-13 |  | 87 | Parsons
40 | Al Wathbah | مدينة الرياض -شارع الخير | 24.3721 | 54.6705 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-15 |  | 2026-12-17 | Contractor Design Phase |  |  |  |  | 63 | Parsons
41 | Al Wathbah | الشوامخ 7 - شارع بدع بوحصية | 24.1836 | 54.9937 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-16 |  | 2026-12-21 | Contractor Design Completed | Yes | Propose enhanced inlets and pipelines. Upgrade the existing network. Propose sub-surface collection tank. |  |  | 66 | Parsons
42 | Al Wathbah | مسجد الشيخة عفراء بنت زايد ال نهيان | 24.1881 | 54.9966 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-05 |  | 2026-11-30 | Construction Phase | Yes | Propose inlets, pipelines, manholes and geocell soakaways | 2026-07-29 |  | 56 | Parsons
43 | Al Wathbah | الختم القديمة - بجوار حديقة الختم | 24.3293 | 54.6331 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-06 |  | 2026-11-26 | Contractor Design Completed | Yes | Propose inlets, pipelines, manholes, upstand kurbs and geocell soakaways |  |  | 51 | Parsons
44 | Al Wathbah | بني ياس - شارع اليال | 24.3218 | 54.6427 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-15 |  | 2026-11-30 | Contractor Design Completed | Yes |  |  |  | 46 | Parsons
45 | Al Wathbah | بني ياس -شارع اليال | 24.3144 | 54.6534 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-10 |  | 2026-11-12 | Contractor Design Completed | Yes |  |  |  | 33 | Parsons
46 | Al Wathbah | بني ياس -شارع اليال | 24.3069 | 54.6633 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 |  | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 |  | 2026-08-25 | Hand over phase | Yes | Raising of inlet and installing new grp cover, frame and grating. Existing inlet di cover to be replaced with grp cover / repair and painting. Propose road kerb stone. | 2026-06-15 | 2026-08-25 | 71 | Parsons
47 | Al Wathbah | بني ياس - شارع اليال | 24.2888 | 54.6549 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 |  | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 |  | 2026-08-25 | Hand over phase | Yes | Raising of inlet and installing new grp cover, frame and grating. Existing inlet di cover to be replaced with grp cover / repair and painting. Propose road kerb stone. | 2026-06-15 | 2026-08-25 | 71 | Parsons
48 | Al Wathbah | بني ياس - شارع الشيخ محمد بن راشد | 24.3044 | 54.6281 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-09-11 | Contractor Design Phase |  |  |  |  | 3 | Parsons
49 | Al Wathbah | بني ياس - شارع الخويرة | 24.2693 | 54.6681 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 2 | [7 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-12-27 | Construction Phase | Yes | Rip-rap protection for ditches/ponds, and protective acrylic/epoxy coatings for the pump station. Internal wall structural restoration and external waterproofing membrane renewal. Installation pumps with guide rails and accessories. | 2026-08-15 |  | 68 | Parsons
50 | Al Wathbah | نفق الوثبة | 24.2417 | 54.7368 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 4 | 4 | [7 empty] | 1339200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-07 |  | 2027-01-24 | Contractor Design Completed | Yes |  |  |  | 78 | Parsons
51 | Al Wathbah | نفق النهضة | 24.2681 | 54.673 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-20 |  | 2027-01-01 | Contractor Design Phase |  |  |  |  | 42 | Parsons
52 | Al Wathbah | الوثبة - شارع الحفظة | 24.2663 | 54.6578 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-11 |  | 2026-12-20 | Contractor Design Completed | Yes |  |  |  | 70 | Parsons
53 | Al Wathbah | الوثبة جنوب | 24.2758 | 54.6451 | Medium | Yes | Developer (Al Dar) | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-10 |  | 2026-11-12 | Contractor Design Completed | Yes |  |  |  | 33 | Parsons
54 | Al Wathbah | بني ياس - شارع الجزائر | 24.2458 | 54.7097 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-07 |  | 2026-12-07 | Contractor Design Phase | [5 empty] | Parsons
55 | Al Wathbah | الوثبة - شارع الرسوخ - بجانب منتزة الوثبة | 24.269 | 54.684 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-18 | Construction Phase | Yes | Cleaning and CCTV inspection of pipelines to generate pre-rehabilitation reports. Installing GRP pipes , constructing GRP manholes, and fitting various side-entry catch basins and top/side-entry inlets and connecting the new discharge chamber to the existing stormwater network. | 2026-08-24 |  |  | Parsons
56 | Al Wathbah | الوثبة - شارع النهضة | 24.2701 | 54.6498 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 |  | 2026-12-07 | Construction Phase | Yes | Propose pipelines and catch basins. Existing inlets to be replaced with catch basins. | 2026-08-06 |  |  | Parsons
57 | Al Wathbah | بني ياس - شارع السهل | 24.3999 | 54.7328 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 |  | 2026-12-18 | Construction Phase | Yes | Propose grp pipes, manholes, soakaways, catch basins and inlets. Existing flush kerb to be replaced with upstand kerb. Proposed upstand kerb | 2026-08-03 |  |  | Parsons
58 | Al Wathbah | الشامخة - بالقرب من الشامخة مول | 24.3937 | 54.7044 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 60000 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-07 |  | 2027-01-23 | Contractor Design Completed | Yes | Provide inlets, geocellular storage, and pipelines to gather, hold, and convey stormwater runoff, limiting surface water build-up and easing flooding |  |  |  | Parsons
59 | Al Wathbah | الشامخة - شارع احمد بن شملان الفلاحي | 24.411 | 54.747 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-08 |  | 2027-01-23 | Contractor Design Completed | Yes |  |  |  |  | Parsons
60 | Al Wathbah | الشامخة - تقاطع شارع الترشيد مع شارع ام الثعالب | 24.3954 | 54.6943 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-07 |  | 2026-12-23 | Construction Phase | Yes | Introduce depressions, a lifting station, and emptying lines to collect, transfer, and release accumulated stormwater, thereby reducing water build-up and flood impacts | 2026-08-07 |  |  | Parsons
61 | Al Wathbah | الشامخة -شارع محمد بن شبيب المهيري | 24.3759 | 54.6992 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-25 |  | 2026-12-24 | Construction Phase | Yes | Provide inlets, pipelines, and a sub-surface collection tank to capture, convey, and temporarily retain stormwater, reducing surface water build-up | 2026-09-03 |  |  | Parsons
62 | Al Wathbah | الشامخة -شارع الرضى | 24.3507 | 54.6832 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-30 |  | 2026-12-25 | Contractor Design Completed | Yes | Introduce inlets, pipelines, and a sub-surface collection tank to gather, channel, and temporarily hold stormwater, helping to minimise water build-up |  |  |  | Parsons
63 | Al Wathbah | الشامخة -شارع العايد | 24.4078 | 54.7358 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-11-22 | Construction Phase | Yes | Introduce depressions, a lifting station, and emptying lines to gather, transfer, and release accumulated stormwater, helping to minimise water build-up | 2026-08-01 |  |  | Parsons
64 | Al Wathbah | الشامخة - تقاطع شارع دمية طحنون مع شارع الخزنه | 24.4182 | 54.8663 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-11-16 | Construction Phase | Yes | Establish depressions, a lifting station, and emptying lines to collect, move, and discharge accumulated stormwater, helping to alleviate surface water build-up at the identified hotspot. | 2026-08-01 |  |  | Parsons
65 | Al Wathbah | العدلة - شارع طوي بو صلف | 24.4114 | 54.8677 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-15 |  | 2026-12-07 | Contractor Design Completed | Yes | Introduce inlets, geocells, and pipelines, while adjusting road grading to guide stormwater effectively and minimise surface water accumulation |  |  |  | Parsons
66 | Al Wathbah | العدلة - شارع طوي اشعب | 24.3853 | 54.9003 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-09-17 | Construction Phase | Yes | Reprofile the terrain and lower accumulated sand levels to restore natural surface flow paths and improve stormwater movement, thereby reducing water build-up | 2026-08-20 |  |  | Parsons
67 | Al Wathbah | عزب العدلة | 24.3869 | 54.9001 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 1 | 250 | 27000 | 72000 | 99000 | 0 | 0 |  | 0 | [6 empty] | Yes | N/A |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | Hand over phase | N/A | Descoped | 2026-07-26 | 2026-09-01 |  | Parsons
68 | Al Wathbah | مدخل المحاجر في العدلة | 24.3831 | 54.895 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | N/A |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | Hand over phase | N/A | Descoped | 2026-07-26 | 2026-09-01 |  | Parsons
69 | Al Wathbah | مزارع العدلة | 24.3082 | 54.8788 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 1 | 250 | 27000 | 72000 | 99000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | N/A |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | Hand over phase | N/A | Descoped | 2026-07-26 | 2026-09-01 |  | Parsons
70 | Al Wathbah | الفاية الصناعية | 24.4523 | 54.3841 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-17 |  | 2026-12-17 | Contractor Design Phase | [5 empty] | Parsons
71 | Island | مواقف سيارات حديقه ام الامارات- المشرف / شارع الند ، غرب 24/2 | 24.4054 | 54.4707 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 |  | 2026-10-10 | Concept Design and IDAS review stage | N/A |  |  |  |  | AECOM
72 | Island | الدوار المؤدي الى نادي ضباط الشرطة. | 24.4359 | 54.3954 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 |  | 2026-11-28 | Concept Design and IDAS review stage | N/A |  |  |  |  | AECOM
73 | Island | المشرف / غرب52 / شارع احمد بن سعيد الرميثي | 24.4624 | 54.3763 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
74 | Island | تقاطع شارع الشيخ راشد بن سعيد مع تقاطع شارع الشيخة فاطمة بنت مبارك (مقابل مبنى دائرة الاشغال سابقا) | 24.4673 | 54.3343 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
75 | Island | شارع اليزوة – الخالدية مقابل (سبينس- الكورنيش) | 24.4574 | 54.319 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 |  |  | 3 | [5 empty] | 259200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-05 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
76 | Island | شارع الكورنيش (مدخل بوابة قصر الامارات) | 24.4639 | 54.3766 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 | 2 |  | 1 | [5 empty] | 756000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-10 | Concept Design and IDAS review stage | [5 empty] | AECOM
77 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4646 | 54.3658 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Permitting and Work Phase | Yes |  |  |  |  | AECOM
78 | Island | مواقف سيارات مستشفي جلوبال كير | 24.479 | 54.3624 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
79 | Island | شارع المطار مقابل قصر المنهل | 24.4544 | 54.3378 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Permitting and Work Phase | Yes |  |  |  |  | AECOM
80 | Island | مرسي البطين جوار مبني تبريد | 24.4731 | 54.3201 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-19 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
81 | Island | بجوار مواقف سيارات المارينا مول | 24.4672 | 54.3781 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-27 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
82 | Island | مدارس التكنولوجيا التطبيقيه بمنطقه ال نهيان | 24.4694 | 54.3851 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-19 | Concept Design and IDAS review stage | Yes |  |  |  |  | AECOM
83 | Island | شارع الشيخة فاطمة بنت مبارك - مقابل مدرسة الامارات الوطنية | 24.4559 | 54.3946 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-11 |  | 2027-01-11 | Contractor Design Phase | [5 empty] | Parsons
84 | Island | حوض E-25 - قريب من مبنى مبادلة | 24.4792 | 54.6399 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 7 | 2 |  | 5 | [5 empty] | 550800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-12 |  | 2027-01-23 | Contractor Design Completed | Yes | Enhance the existing network and introduce kerb inlets and pipes to improve stormwater collection and conveyance, helping to reduce surface water accumulation |  |  |  | Parsons
85 | Al Shahama | شارع الشيخ زايد بين مجمع جسور ياس و جسر المطار بالاتجاهين | 24.3735 | 54.5219 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-02 | 2026-09-11 | 2026-12-31 | Construction Phase | Yes |  | 2026-09-05 |  |  | Parsons
86 | Mussafah | نفق الصناعية الاول باتجاه الداخل | 24.3465 | 54.5226 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 4 | 1 | 3 | [6 empty] | 918000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
87 | Mussafah | نفق الصناعية الثاني باتجاه الداخل | 24.4106 | 54.6815 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 1 | 1 | [6 empty] | 529200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
88 | Al Shahama | مخرج الجسر من الشامخة للفلاح باتجاه دبي | 24.4025 | 54.6703 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-12-20 | Construction Phase | Yes | Introduce depressions, a lifting station, and emptying lines to collect, transfer, and discharge stormwater, reducing local water accumulation and alleviating flooding | 2026-08-19 |  |  | Parsons
89 | Al Shahama | مخرج جسر سويحان للقادم من جسر كرم الشام باتجاه الشامخة الفلاح | 24.3914 | 54.5291 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60000 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-12-23 | Construction Phase | Yes | Propose depressions, lifting station and emptying lines | 2026-08-19 |  |  | Parsons
90 | Zayed | شارع الخليج العربي المخرج المؤدي لشارع العين | 24.347 | 54.5289 | Very High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-09-11 | 2027-01-12 | Construction Phase | Yes | Introduce inlets and pipelines to collect and convey stormwater runoff, improving surface water management and reducing water accumulation | 2026-08-25 |  |  | Parsons
91 | Zayed | جسر تعليم القيادة بالاتجاهين | 24.313 | 54.6036 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 0 |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-30 |  | 2026-07-30 | Hand over phase | N/A |  | 2026-06-30 | 2026-07-30 |  | Parsons
92 | Zayed | جسر المفرق للقادم من مدينة شخبوط الطبية باتجاه ابوظبي | 24.4242 | 54.7646 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 |  | 2026-09-01 | Construction Phase |  |  | 2026-07-30 |  |  | Parsons
93 | Al Shahama | شارع محمد بن راشد للقادم من دبي تم تحويل الحركة باتجاه الشامخة | 24.3886 | 54.5401 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-11-23 | Construction Phase | Yes | Introduce inlets, flush inlets, manholes, inspection shafts, catch basins, geocell soakaways, SW mainline, outfall, and pipelines to improve stormwater collection and conveyance. | 2026-08-19 |  |  | Parsons
94 | Zayed | Abu Dhabi–Al Ain Road, entrance to the service road before the Mazyad Mall Bridge, outbound direction. | 24.5429 | 54.6941 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 2 | [7 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-09-11 | 2027-01-12 | Construction Phase | Yes | Provide inlets, pipelines and grated channel to efficiently capture and convey stormwater runoff, improving surface drainage and limiting water accumulation | 2026-08-21 |  |  | Parsons
95 | Al Shahama | النفق المودي للشهامة للقادم من روضة الريف | 24.4188 | 54.7506 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 60000 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-26 |  | 2026-10-12 | Contractor Design Phase | [5 empty] | Parsons
96 | Al Wathbah | طريق سويحان بعد جسر الفلاح الشامخة باتجاه سويحان | 24.4025 | 54.5725 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 17 | 15 |  | 2 | [5 empty] | 5194800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2027-01-09 | Construction Phase | Yes |  | 2026-08-19 |  |  | Parsons
97 | Zayed | على طول شارع ذياب بن عيسى في مدينة خليفة أ بالاتجاهين | 24.3205 | 54.6125 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 |  | 2026-07-11 | Hand over phase | N/A | Introduce inlets and pipelines to effectively collect and carry stormwater runoff, enhancing surface drainage and reducing water build-up | 2026-07-05 | 2026-07-11 |  | Parsons
98 | Zayed | شارع الشيخ مكتوم بن راشد مقابل مستشفى شخبوط باتجاه الغربية | 24.3461 | 54.5731 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 6 |  | 4 | 2 | [5 empty] | 950400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-09-08 | Construction Phase | Yes |  | 2026-08-02 |  |  | Parsons
99 | Zayed | طريق ابوظبي العين قبل جسر محوي باتجاه الداخل | 24.3726 | 54.6562 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 2 | [7 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 |  | 2026-09-11 | Construction Phase | Yes | Propose ditches and culverts | 2026-08-11 |  |  | Parsons
100 | Al Wathbah | شارع الشيخ مكتوم بن راشد عن حسر كرم الشام (الشوامخ) باتجاه دبي | 24.4406 | 54.6002 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 |  |  | 1200000 | 60000 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-17 | 2026-09-11 | 2026-11-27 | Construction Phase | Yes | Provide ditches and culverts to guide and convey stormwater runoff, improving surface drainage and minimising water accumulation | 2026-08-15 |  |  | Parsons
101 | Zayed | مدينة خليفة | 24.4149 | 54.502 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-06 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-06 | 2026-07-13 |  | Parsons
102 | Zayed | مدينة خليفة | 24.4112 | 54.5082 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-09-11 | 2027-01-12 | Construction Phase | Yes | Provide double inlets and pipelines to improve stormwater collection and conveyance, helping to minimise surface water accumulation and alleviate flooding | 2026-08-25 |  |  | Parsons
103 | Zayed | منطقة ربدان | 24.4028 | 54.5272 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-03 |  | 2026-12-01 | Contractor Design Completed | Yes | Provide inlets, gate valves, storage geocells, and pipelines to collect, control, temporarily retain, and convey stormwater, reducing surface water accumulation |  |  |  | Parsons
104 | Zayed | منطقة ربدان | 24.3493 | 54.6215 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-09-11 | 2027-01-12 | Construction Phase | Yes | Introduce inlets at suitable locations to capture stormwater runoff efficiently, improve surface drainage, and minimise water accumulation | 2026-08-25 |  |  | Parsons
105 | Zayed | منطقة ربدان | 24.365 | 54.6482 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 |  | 2026-09-30 | Contractor Design Completed | Yes |  |  |  |  | Parsons
106 | Zayed | مدينة شخبوط | 24.405 | 54.5193 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 | 1 |  | 2 | [5 empty] | 253800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 |  | 2026-09-22 | Construction Phase |  |  | 2026-08-06 |  |  | Parsons
107 | Zayed | مدينة شخبوط | 24.3306 | 54.5368 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-08 |  | 2026-11-12 | Contractor Design Completed | Yes | Provide strategically positioned inlets and pipelines to capture and convey stormwater efficiently, improving drainage conditions and reducing water accumulation |  |  |  | Parsons
108 | Zayed | منطقة ربدان | 24.4074 | 54.5026 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2026-10-18 | Contractor Design Phase | [5 empty] | Parsons
109 | Zayed | مدينة محمد بن زايد | 24.3831 | 54.5948 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-19 |  | 2026-11-23 | Contractor Design Completed | Yes | Provide pipelines, geocell storage, suitable grading, and inlets between the geocells to guide, retain, and convey stormwater, reducing water accumulation |  |  |  | Parsons
110 | Zayed | مدينة زايد | 24.3796 | 54.5576 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 |  | 2026-08-10 | Hand over phase | N/A |  | 2026-07-05 | 2026-07-30 |  | Parsons
111 | Zayed | مدينة زايد | 24.4187 | 54.4962 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-25 |  | 2026-09-16 | Construction Phase |  |  | 2026-07-25 |  |  | Parsons
112 | Zayed | ساس النخل - مدينة زايد | 24.3925 | 54.5033 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-11-25 | Contractor Design Completed | Yes |  |  |  |  | Parsons
113 | Zayed | ربدان - ساس النخل | 24.4237 | 54.5229 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-22 |  | 2027-01-31 | Contractor Design Phase | [5 empty] | Parsons
114 | Zayed | شارع جبر بن راشد الحلامي - طريق ساس النخل | 24.308 | 54.5813 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 3 |  |  | 3 | [5 empty] | 259200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-09 |  | 2026-12-12 | Contractor Design Completed | Yes | Introduce flush inlets, standard inlets, and pipelines to improve stormwater collection and conveyance, helping to minimise surface water build-up |  |  |  | Parsons
115 | Zayed | مدينة محمد بن زايد | 24.3846 | 54.633 | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 |  | 2026-12-10 | Contractor Design Completed | Yes | Provide inlets and soakaways to capture and disperse stormwater runoff, reducing surface water build-up and alleviating flooding |  |  |  | Parsons
116 | Zayed | مدينة زايد | 24.3542 | 54.6106 | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-15 |  | 2026-08-17 | Hand over phase | N/A |  | 2026-07-15 | 2026-08-05 |  | Parsons
117 | Zayed | مدينة زايد | 24.3665 | 54.6067 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-21 |  | 2026-08-16 | Hand over phase | N/A |  | 2026-07-21 | 2026-08-16 |  | Parsons
118 | Zayed | مدينة زايد | 24.3403 | 54.5579 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-12 |  | 2026-08-14 | Hand over phase | N/A |  | 2026-07-12 | 2026-07-30 |  | Parsons
119 | Zayed | مدينة محمد بن زايد - شارع خليفة بن خميس الديهلي | 24.2968 | 54.5634 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-28 |  | 2026-10-11 | Contractor Design Phase | [5 empty] | Parsons
120 | Zayed | مدينة محمد بن زايد | 24.3686 | 54.6005 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 |  | 2026-09-15 | Contractor Design Completed | Yes | Provide soakaways at suitable locations to collect and disperse stormwater runoff, reducing surface water build-up and easing flooding |  |  |  | Parsons
121 | Zayed | Zayed City | 24.3994 | 54.5932 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-22 |  | 2026-07-30 | Hand over phase | N/A |  | 2026-07-22 | 2026-08-23 |  | Parsons
122 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4106 | 54.4965 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 |  | 2026-09-22 | Contractor Design Phase |  | Adjust the road levels to improve surface water flow and minimise water accumulation |  |  |  | Parsons
123 | Zayed | ربدان - شارع راشد بن جابر الهاملي | 24.3176 | 54.5332 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 1 | 250 | 27000 | 72000 | 99000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-11-20 | Contractor Design Completed | Yes | Introduce geocell storage, refined grading, and pipelines to accommodate, retain, and convey stormwater runoff, helping to limit surface water build-up |  |  |  | Parsons
124 | Zayed | مدينة محمد بن زايد | 24.3896 | 54.6092 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-09-17 | Contractor Design Phase | [5 empty] | Parsons
125 | Zayed | مدينة محمد بن زايد - MZ 17 | 24.379 | 54.5851 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-09-29 | Contractor Design Phase | [5 empty] | Parsons
126 | Zayed | مدينة زايد | 24.4029 | 54.5038 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 |  | 2026-09-30 | Hand over phase | Yes | Provide riprap protection and a trapezoidal channel to safely guide stormwater flows, protect the channel from erosion, and minimise water accumulation | 2026-07-02 | 2026-08-06 |  | Parsons
127 | Zayed | ربدان | 24.4097 | 54.6368 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-25 | Construction Phase | Yes | Provide geocell storage, suitable grading, and pipelines to manage and temporarily retain stormwater runoff, improving surface drainage and reducing water accumulation | 2026-08-10 |  |  | Parsons
128 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4102 | 54.6436 | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-09-11 | 2027-01-12 | Contractor Design Completed | Yes | Provide spillways to safely direct excess stormwater away from the affected area, reducing surface water build-up and limiting flood impacts |  |  |  | Parsons
129 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.3704 | 54.6183 | High | Yes | ADM Developer | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-09-11 | 2027-01-12 | Contractor Design Completed | Yes | Introduce inlets, pipelines, and spillways to collect, convey, and safely direct excess stormwater, reducing surface water build-up and easing flood impacts |  |  |  | Parsons
130 | Zayed | مدينة زايد | 24.4334 | 54.5769 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-28 |  | 2026-10-06 | Contractor Design Phase | [5 empty] | Parsons
131 | Zayed | مدينة خليفة | 24.4283 | 54.7364 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-04 | 2026-07-11 |  | Parsons
132 | Al Shahama | مدينة الفلاح | 24.5196 | 54.6716 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 1 | 250 | 27000 | 72000 | 99000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-03 |  | 2027-01-23 | Contractor Design Completed | Yes | Provide inlets, pipelines, and a geocellular tank area to capture, convey, and temporarily retain stormwater, helping to minimise surface water build-up |  |  |  | Parsons
133 | Al Shahama | الشهامة | 24.326 | 54.5162 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-26 |  | 2027-01-30 | Contractor Design Completed | Yes | Introduce inlets, pipelines, and a road hump to guide stormwater towards the drainage system and reduce surface water accumulation |  |  |  | Parsons
134 | Mussafah | مصفح صناعية | 24.6264 | 54.7119 | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 4 | 4 | [7 empty] | 669600 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
135 | Al Shahama | الباهية | 24.1576 | 54.8458 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-24 | Concept Design and IDAS review stage | N/A |  |  |  |  | AECOM
136 | Al Wathbah | طريق رزين | 24.4615 | 54.702 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2026-12-21 | Contractor Design Phase | [5 empty] | Parsons
137 | Al Shahama | شارع خليفة بن زايد - الريف | 24.2609 | 54.673 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-09-09 | Construction Phase | Yes | Provide catch basins, a pond, and pipelines to collect, temporarily retain, and convey stormwater, reducing surface water build-up and mitigating flooding | 2026-08-01 |  |  | Parsons
138 | Al Wathbah | الوثبة جنوب | 24.4258 | 54.7426 | Low | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 14400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2026-12-21 | Contractor Design Completed | Yes | Provide inlets and pipelines, adjust the road profile, and introduce a swale to guide runoff towards the drainage system and minimise surface water accumulation |  |  |  | Parsons
139 | Al Shahama | مدينة الفلاح | 24.436 | 54.6253 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-02 |  | 2027-01-23 | Contractor Design Completed | Yes | Introduce inlets, pipelines, and a geocellular tank area to collect, convey, and temporarily store stormwater, helping to reduce surface water build-up |  |  |  | Parsons
140 | Zayed | مدينة خليفة - دوار طيران الرئاسة | 24.35 | 54.4939 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 | 3 | [7 empty] | 1004400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 |  | 2026-07-25 | Hand over phase | N/A |  | 2026-07-18 | 2026-07-25 |  | Parsons
141 | Mussafah | مصفح صناعية | 24.3855 | 54.8443 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
142 | Al Wathbah | طريق الحفار | 24.5965 | 54.695 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-15 |  | 2026-12-03 | Contractor Design Phase | [5 empty] | Parsons
143 | Al Shahama | الرحبة | 24.2968 | 54.6285 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-02 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
144 | Al Wathbah | شارع بني ياس بالقرب من محطة البترول | 24.3514 | 54.7125 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-12 | Contractor Design Phase | [5 empty] | Parsons
145 | Al Wathbah | مدينة الرياض | 24.2625 | 54.6587 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-30 |  | 2026-12-21 | Contractor Design Phase | [5 empty] | Parsons
146 | Al Wathbah | الوثبة جنوب | 24.642 | 54.6575 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-26 | Contractor Design Phase | [5 empty] | Parsons
147 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.6811 | 54.6692 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-10 | Permitting and Work Phase | Yes |  |  |  |  | AECOM
148 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.6959 | 54.7814 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-18 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
149 | Al Shahama | شارع مكتوم بن راشد | 24.4711 | 54.6709 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-26 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
150 | Al Shahama | شارع سلطان بن زايد - الريف | 24.5973 | 54.9097 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-09-11 | Contractor Design Completed | Yes | Provide inlets, manholes, and pipelines to effectively collect and convey stormwater, improving drainage performance and reducing surface water accumulation |  |  |  | Parsons
151 | Al Shahama | طريق الطف | 24.7557 | 54.7337 | Low | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-08 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
152 | Al Shahama | الصدر- شارع عويد | 24.7631 | 54.7003 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-16 | Permitting and Work Phase | Yes |  | 2026-06-24 |  |  | AECOM
153 | Al Shahama | خليفة الصناعية - 6 | 24.4322 | 54.7315 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  | 1 | [6 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-24 | Permitting and Work Phase | Yes |  | 2026-06-10 |  |  | AECOM
154 | Al Shahama | مدينة الفلاح | 24.4395 | 54.7408 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | [5 empty] | 43200 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-22 |  | 2027-01-23 | Contractor Design Completed | Yes | Provide a geocellular tank area to temporarily retain stormwater runoff, helping to reduce surface water build-up and alleviate floodin |  |  |  | Parsons
155 | Al Shahama | مدينة الفلاح | 24.3074 | 54.6051 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 3 | 750 | 81000 | 216000 | 297000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-22 |  | 2027-01-23 | Contractor Design Completed | Yes | Introduce inlets, pipelines, and a geocellular tank area to capture, convey, and temporarily retain stormwater runoff, helping to minimise surface water build-up |  |  |  | Parsons
156 | Al Wathbah | طريق أبو ظبي - العين | 24.4613 | 54.7361 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-09-14 | Contractor Design Phase | [5 empty] | Parsons
157 | Al Shahama | مدينة الفلاح | 24.6864 | 54.7736 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-09-11 | Construction Phase | Yes | Propose uPVC and HDPE pipelines and construct reinforced concrete manholes, top-entry sand trap inlets, gravel filling, grouted rip-rap, and a modular geocell soakaway system. | 2026-08-01 |  |  | Parsons
158 | Al Shahama | شارع مكتوم بن راشد باتجاه السمحة القديمة | 24.7976 | 54.8637 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-24 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
159 | Al Shahama | دوار على شارع مكتوم بن راشد | 24.2812 | 54.6473 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  | 2 | [6 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-02 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
160 | Al Wathbah | طريق أبو ظبي - العين | 24.4583 | 54.3414 | Medium | Yes | Developer | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 10 | 2500 | 270000 | 720000 | 990000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-13 | Contractor Design Phase | [5 empty] | Parsons
161 | Island | خلف مدرسه الامام الغزالي- شارع مطر المهيري - غرب 16 | 24.437 | 54.3736 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
162 | Island | شارع المطلع - شارع الخليج العربي - غرب 52 | 24.4507 | 54.3348 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-27 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
163 | Island | مرسي البطين جوار مرسى اليخوت 1 | 24.4607 | 54.3575 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
164 | Island | شارع خليفة بن شخبوط - غرب 17-1- مواقف سيارات مدرسه هزاع بن زايد الاول | 24.457 | 54.3552 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
165 | Island | تقاطع شارع الخليج العربي مع شارع الشيخ هزاع | 24.445 | 54.4379 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
166 | Island | شارع الشيخ زايد بن سلطان تقاطع شارع ظفير -النفق | 24.4214 | 54.4818 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
167 | Island | مناره المقطع - جوار جسر المقطع | 24.4741 | 54.3748 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
168 | Island | جراند الامارات - شارع هزاع بن زايد تقاطع شارع الشيخ سلطلن بن زايد | 24.4831 | 54.3758 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-11 | Permitting and Work Phase | Yes |  |  |  |  | AECOM
169 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع الفلاح | 24.4848 | 54.3636 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
170 | Island | مقابل فندق كرستال ابو ظبي- شرق 14 بالقرب من مركز مدينة زايد للتسوق | 24.4891 | 54.3699 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
171 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع زايد الأول | 24.425 | 54.4108 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
172 | Island | شارع الظفرة تقاطع شارع الخليج العربي- جوار دوار مجلس المشرف | 24.4928 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
173 | Island | شارع زايد بن سلطان بين تقاطع شاع زايد الأول وشارع محمد بن بطي ال حامد - مقابل مطعم قصر الهند | 24.4145 | 54.4314 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
174 | Island | منطقه المزون | 24.4279 | 54.4108 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-27 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
175 | Island | شارع الظفرة بين شارع راشد بن زايد وشارع الخليج العربي | 24.4339 | 54.4033 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-16 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
176 | Island | شارع سلامة بن بطي بين شارع راشد بن زايد وشارع الخليج العربي | 24.417 | 54.47 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
177 | Island | مدخل منطقة روضة ابوظبي من شارع الشيخ راشد بن سعيد- قرب مطار البطين | 24.4704 | 54.3701 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
178 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع هزاع | 24.459 | 54.3814 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Permitting and Work Phase | Yes |  |  |  |  | AECOM
179 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع الشيخ محمد بن خليفة- مقابل محمصه الامراء | 24.4617 | 54.3936 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
180 | Island | منطقة المعمورة - بجانب مبنى دائرة البلديات والنقل | 24.5406 | 54.4836 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 |  | 3 | [6 empty] | 583200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-12 |  | 2027-01-23 | Contractor Design Completed | Yes | Upgrade the catchment and provide geocells to improve stormwater management, enhance runoff retention, and reduce surface water accumulation |  |  |  | Parsons
181 | Island | جزيره الجبيل - شارع خليفه بن زايد | 24.482 | 54.4047 | Low | Yes | مطور | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
182 | Island | دوار شارع الحريه - جزيره الريم | 24.5385 | 54.4396 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
183 | Island | جزيره السعديات - جوار مسجد الحمد | 24.4444 | 54.3952 | Medium | Yes | مطور | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
184 | Island | شارع الشيخ راشد بن سعيد - جسر الجوازات | 24.4397 | 54.4118 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 5 |  |  | 5 | [5 empty] | 432000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
185 | Island | شارع سلطان بن زايد من تقاطغ شارع سلامة بن بطي الى شارع الظفرة- مقابل مطعم اليمن السعيد شارع المرور | 24.4724 | 54.3927 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
186 | Island | مدخل قصر البحر | 24.5171 | 54.3729 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | [5 empty] | 615600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-29 |  | 2027-01-23 | Contractor Design Completed | Yes | Upgrade the existing network. |  |  |  | Parsons
187 | Island | مينا زايد تابع للمطور | 24.4235 | 54.4444 | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
188 | Island | الشارع من أرض المعارض لدوار الجوية- شارع السفارات | 24.3473 | 54.5254 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-25 | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
189 | Mussafah | نفق المصفح الثاني باتجاه الخارج | 24.5431 | 54.6917 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 2 | [7 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Critical Infrastructure | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
190 | Al Shahama | الشهامة الجديدة | 24.461 | 54.6111 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-09-11 | 2026-12-11 | Contractor Design Completed | Yes | Propose grading with Gravel, openings, replace concrete barrier with steel barriers, provide spillway behind the opening and the barrier, propose inlets and pipelines |  |  |  | Parsons
191 | Al Shahama | نفق ياس | 24.3924 | 54.5486 | High | Yes | Developer (ICT) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-09-11 | 2027-01-12 | Contractor Design Phase | [5 empty] | Parsons
192 | Zayed | طريق الخليج العربي مقابل ملعب الكريكت | 24.3772 | 54.551 | Very High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Fast- tracked | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-09-11 | 2027-01-12 | Construction Phase | Yes | Introduce inlets to efficiently capture stormwater runoff, improving surface drainage and reducing water accumulation | 2026-08-21 |  |  | Parsons
193 | Zayed | قبل الجسر المؤدي لمحمد بن زايد | 24.3032 | 54.6275 | High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  | 1 | [6 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2026-10-20 | Contractor Design Phase | [5 empty] | Parsons
194 | Al Wathbah | بحيرة بني ياس | 24.3094 | 54.6156 | Very High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 | 1 | [7 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-28 |  | 2026-12-28 | Contractor Design Completed | Yes | Provide GRP pipes, manholes, and a lifting station, with pipeline construction through NDRC and suitable routing for the perforated line to improve stormwater conveyance. |  |  |  | Parsons
195 | Al Wathbah | شارع الزود - بني ياس | 24.2921 | 54.5592 | High | Yes | Private | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 13 | 3 | 6 | 4 | [5 empty] | 2516400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 1200000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-25 |  | 2026-12-30 | Contractor Design Completed | Yes | Propose GRP lines up to 7.5m deep, alongside reinforced concrete manholes, inlets, and NDRC thrust boring. Earthworks and road reinstatements involve subbase preparation, kerbs, and asphalt reinstatement. Finally, demolition covers removing existing networks, structure flushing, and operational over-pumping systems. |  |  |  | Parsons
196 | Zayed | قبل الجسر المؤدي للمفرق الصناعية | 24.3244 | 54.5305 | Very High | Yes | Private | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 |  | 1600000 | 0 | 60000 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor Design Phase | [5 empty] | Parsons
197 | Zayed | شارع النصيلة- مدينة محمد بن زايد | 24.3263 | 54.5841 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 4 |  |  | 4 | [5 empty] | 345600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-09-11 | Contractor Design Phase | [5 empty] | Parsons
198 | Zayed | شارع النصيلة- مدينة محمد بن زايد - قبل الجسر | 24.3278 | 54.5859 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 4 | 4 | [7 empty] | 1339200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-09-11 | 2026-10-01 | Construction Phase | Yes | Provide spillways and a linear pond to safely accommodate and temporarily retain excess stormwater, reducing surface water build-up and mitigating flood impacts | 2026-09-01 |  |  | Parsons
199 | Zayed | الجسر المؤدي الى المصفح - طريق أبو ظبي - العين | 24.3598 | 54.6677 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 2 | [7 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Detailed | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | 2026-10-08 | Construction Phase | Yes | Introduce inlets, manholes, and pipelines to collect and convey stormwater efficiently, enhancing drainage performance and reducing surface water accumulation | 2026-08-10 |  |  | Parsons
200 | Al Wathbah | الشوامخ - تقاطع شارع طوي القامة مع شارع المورد | 24.4244 | 54.5449 | High | Yes | Mainland | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 5 | 1250 | 135000 | 360000 | 495000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-26 |  | 2027-01-23 | Contractor Design Completed | Yes | Provide inlets, storage geocells, and pipelines to capture, temporarily retain, and convey stormwater runoff, helping to minimise surface water build-up |  |  |  | Parsons
201 | Zayed | مدينة خليفة | 24.3958 | 54.555 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 |  | 2026-07-10 | Hand over phase | N/A |  | 2026-07-03 | 2026-07-10 |  | Parsons
202 | Zayed | مدينة خليفة | 24.4297 | 54.5634 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-04 | 2026-07-11 |  | Parsons
203 | Zayed | مدينة خليفة | 24.4264 | 54.535 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 |  | 2026-07-10 | Hand over phase | N/A |  | 2026-07-03 | 2026-07-10 |  | Parsons
204 | Zayed | مدينة خليفة | 24.4482 | 54.6131 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-28 |  | 2026-10-15 | Contractor Design Completed | Yes | Provide suitably located inlets to capture stormwater runoff effectively, improve surface drainage, and minimise water accumulation |  |  |  | Parsons
205 | Zayed | مدينة خليفة - طريق المطار | 24.4467 | 54.6181 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-09-11 | 2026-11-26 | Contractor Design Completed | Yes | Provide strategically positioned inlets and pipelines to capture and convey stormwater runoff, enhancing drainage efficiency and reducing surface water accumulation |  |  |  | Parsons
206 | Zayed | مدينة خليفة | 24.4668 | 54.3829 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-13 | 2026-09-11 | 2027-01-12 | Hand over phase | N/A |  | 2026-07-13 | 2026-07-18 |  | Parsons
207 | Island | جسر دلما | 24.2821 | 54.5414 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 | 3 | [7 empty] | 1004400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-10 |  | 2027-01-06 | Contractor Design Completed | Yes | Upgrade the existing network. |  |  |  | Parsons
208 | Mussafah | مدخل قاعدة الظفرة الجوية | 24.3826 | 54.5106 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 6 |  | 6 | [6 empty] | 1166400 |  | 0 | 0 | 0 | 0 | 0 |  | 1600000 | 1200000 | 100000 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-15 |  | 2027-01-30 | Contractor Design Phase |  | Introduce new inlets and pipes to efficiently collect and convey stormwater runoff, improving drainage conditions and reducing surface water accumulation |  |  |  | Parsons
209 | Mussafah | مصفح صناعية - قطاع 3 | 24.3674 | 54.4811 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | [5 empty] | 183600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
210 | Mussafah | مصفح صناعية - قطاع M19 | 24.3574 | 54.4723 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 2 | [5 empty] | 183600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
211 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3567 | 54.4724 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
212 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3463 | 54.5125 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
213 | Mussafah | مصفح صناعية - قطاع M34 | 24.3284 | 54.5262 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 5 | 1 | 3 | 1 | [5 empty] | 1004400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-09-22 |  | 2026-11-28 | Concept Design and IDAS review stage | No
214 | Mussafah | مصفح صناعية | 24.3218 | 54.5048 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 4 | 2 | 2 | [6 empty] | 529200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Critical Infrastructure |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
215 | Mussafah | مصفح صناعية - ICAD I | 24.3268 | 54.4839 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
216 | Mussafah | مصفح صناعية - ICAD I | 24.3362 | 54.4781 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
217 | Mussafah | مصفح صناعية - قطاع M42 | 24.3438 | 54.4807 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
218 | Mussafah | مصفح صناعية - قطاع M43 | 24.3575 | 54.5142 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
219 | Mussafah | مصفح صناعية - قطاع M32_02 | 24.3607 | 54.5204 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | Ongoing assessment as design develop’
220 | Mussafah | مصفح صناعية - قطاع M24 | 24.3741 | 54.5364 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-09-22 |  | T.B.C | Concept Design and IDAS review stage | No
221 | Zayed | مدينة محمد بن زايد - Z9_01 | 24.3733 | 54.5395 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 3 | 1 |  | 2 | [5 empty] | 507600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 |  | 2026-09-29 | Contractor Design Phase | [5 empty] | Parsons
222 | Zayed | مدينة محمد بن زايد - Z1 | 24.36 | 54.5372 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 1 | 250 | 27000 | 72000 | 99000 | 0 | 0 |  | 0 | [6 empty] | Yes | Fast- tracked |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 |  | 2026-09-20 | Contractor Design Phase | [5 empty] | Parsons
223 | Zayed | مدينة محمد بن زايد - Z9 | 24.353 | 54.5554 | High | Yes | Private area | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 1 |  | 1 | [5 empty] | 421200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor Design Phase | [5 empty] | Parsons
224 | Zayed | مدينة محمد بن زايد - Z5 | 24.3514 | 54.5527 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-06 | Contractor Design Phase | [5 empty] | Parsons
225 | Zayed | مدينة محمد بن زايد - Z8 | 24.3474 | 54.538 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-20 |  | 2026-11-30 | Contractor Design Phase
226 | Zayed | مدينة محمد بن زايد - Z9 | 24.3451 | 54.5352 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 |  | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-30 | Contractor Design Phase | [5 empty] | Parsons
227 | Zayed | مدينة محمد بن زايد - ME9 | 24.3385 | 54.5324 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | [5 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
228 | Zayed | مدينة محمد بن زايد - ME9 | 24.3359 | 54.5357 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
229 | Zayed | مدينة محمد بن زايد - ME10 | 24.3291 | 54.5384 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
230 | Zayed | مدينة محمد بن زايد - ME11 | 24.3268 | 54.5389 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
231 | Zayed | مدينة محمد بن زايد - ME11 | 24.3157 | 54.5398 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
232 | Zayed | مدينة محمد بن زايد - Z20 | 24.3153 | 54.5508 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
233 | Zayed | مدينة محمد بن زايد - Z24 | 24.3168 | 54.5556 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
234 | Zayed | مدينة محمد بن زايد - Z23 | 24.2966 | 54.5551 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
235 | Zayed | مدينة محمد بن زايد - Z30 | 24.2997 | 54.5587 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
236 | Zayed | مدينة محمد بن زايد - Z30 | 24.3017 | 54.5645 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
237 | Zayed | مدينة محمد بن زايد - Z30 | 24.295 | 54.5672 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
238 | Zayed | مدينة محمد بن زايد - Z30 | 24.3018 | 54.5744 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network
239 | Zayed | مدينة محمد بن زايد - Z31 | 24.3017 | 54.5839 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
240 | Zayed | مدينة محمد بن زايد - Z34 | 24.3021 | 54.5813 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
241 | Zayed | مدينة محمد بن زايد - Z34 | 24.304 | 54.5828 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
242 | Zayed | مدينة محمد بن زايد - Z34 | 24.3022 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
243 | Zayed | مدينة محمد بن زايد - Z34 | 24.3047 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
244 | Zayed | مدينة محمد بن زايد - Z34 | 24.3076 | 54.5916 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
245 | Zayed | مدينة محمد بن زايد - Z35 | 24.3161 | 54.5864 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
246 | Zayed | مدينة محمد بن زايد - Z35 | 24.3227 | 54.577 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
247 | Zayed | مدينة محمد بن زايد - Z33 | 24.3192 | 54.5782 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
248 | Zayed | مدينة محمد بن زايد - Z33 | 24.323 | 54.5754 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
249 | Zayed | مدينة محمد بن زايد - Z33 | 24.3223 | 54.5688 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
250 | Zayed | مدينة محمد بن زايد - Z22 | 24.3222 | 54.5645 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
251 | Zayed | مدينة محمد بن زايد - Z22 | 24.3241 | 54.5623 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network
252 | Zayed | مدينة محمد بن زايد - Z22 | 24.3232 | 54.5577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
253 | Zayed | مدينة محمد بن زايد - Z21 | 24.3334 | 54.5579 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
254 | Zayed | مدينة محمد بن زايد - Z15 | 24.3437 | 54.5546 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
255 | Zayed | مدينة محمد بن زايد - Z13 | 24.3422 | 54.5636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [10 empty] | Ongoing assessment as design develop’
256 | Zayed | مدينة محمد بن زايد - Z13_01 | 24.3356 | 54.5782 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
257 | Zayed | مدينة محمد بن زايد - Z36 | 24.2868 | 54.5897 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
258 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2818 | 54.5849 | Low | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
259 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.256 | 54.6342 | Low | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
260 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.4179 | 54.4945 | Low | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
261 | Zayed | ربدان - RB1 | 24.4149 | 54.4926 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
262 | Zayed | ربدان - RB2 | 24.407 | 54.515 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
263 | Zayed | ربدان - RB7 | 24.4024 | 54.4879 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | Zayed | ربدان - RB14 | 24.3984 | 54.5024 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-15 |  | 2026-11-25 | Contractor Design Phase
265 | Zayed | ربدان - RB28 | 24.3947 | 54.5009 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-22 |  | 2027-01-31 | Contractor Design Phase | [5 empty] | Parsons
266 | Zayed | ربدان - RB28 | 24.4142 | 54.5066 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-10 |  | 2026-12-15 | Contractor Design Phase
267 | Zayed | المخرج الى طريق دبي - من طريق أبو ظبي العين | 24.4193 | 54.5136 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Fast- tracked | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-25 | Contractor Design Phase | [5 empty] | Parsons
268 | Zayed | المخرج الى شارع الشيخ زايد - ساس النخل | 24.4116 | 54.5139 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-03 | Contractor Design Phase | [5 empty] | Parsons
269 | Zayed | SW17_مدينة خليفة - 01 | 24.4163 | 54.5465 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
270 | Zayed | مدينة خليفة - SW17 - وطني | 24.4148 | 54.5432 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
271 | Zayed | مدينة خليفة - SW17 - وطني | 24.4144 | 54.5405 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
272 | Zayed | مدينة خليفة - SW17 - وطني | 24.4145 | 54.5393 | High | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | [5 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-25 |  | 2026-12-20 | Contractor Design Phase
273 | Zayed | مدينة خليفة | 24.4144 | 54.5411 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  | 1 | [6 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-06 | Contractor Design Phase | [5 empty] | Parsons
274 | Zayed | مدينة خليفة | 24.4132 | 54.5576 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | Zayed | مدينة خليفة - SW13 | 24.4197 | 54.5586 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
276 | Zayed | مدينة خليفة - SW2 | 24.4147 | 54.5641 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
277 | Zayed | مدينة خليفة - SW3 | 24.41 | 54.5645 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
278 | Zayed | مدينة خليفة - SW4 | 24.3978 | 54.5738 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-15 |  | 2026-12-10 | Contractor Design Phase
279 | Zayed | مدينة خليفة - شارع المطار بالاتجاه لأبو ظبي | 24.4195 | 54.5683 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2026-10-22 | Contractor Design Completed | Yes | Provide inlets, grading, geocell storage, and pipelines to direct, temporarily retain, and convey stormwater runoff, reducing surface water build-up |  |  |  | Parsons
280 | Zayed | مدينة خليفة - SE3 | 24.4184 | 54.5832 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
281 | Zayed | مدينة خليفة - SE13 | 24.414 | 54.5885 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
282 | Zayed | مدينة خليفة - SE24 | 24.4092 | 54.5924 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
283 | Zayed | مدينة خليفة - SE26 | 24.4016 | 54.5785 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
284 | Zayed | مدينة خليفة - SE6 | 24.4027 | 54.5843 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
285 | Zayed | مدينة خليفة - SE16 | 24.4045 | 54.592 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
286 | Zayed | مدينة خليفة - SE26 | 24.407 | 54.6048 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | Zayed | مدينة خليفة - SE36 | 24.4124 | 54.6033 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
288 | Zayed | مدينة خليفة - SE38 | 24.4158 | 54.6016 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | Zayed | مدينة خليفة - SE35 | 24.43 | 54.5817 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | Zayed | مدينة خليفة - SE44 | 24.4365 | 54.5869 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
291 | Zayed | مدينة خليفة - SE47 | 24.44 | 54.5905 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | Zayed | مدينة خليفة - SE47 | 24.4264 | 54.6002 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
293 | Zayed | مدينة خليفة - SE40 | 24.4343 | 54.5597 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
294 | Zayed | مدينة خليفة - الراحة - RBW13 | 24.4384 | 54.5776 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-20 |  | 2026-12-20 | Contractor Design Phase
295 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4427 | 54.5933 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-02 |  | 2026-10-24 | Contractor Design Completed | Yes | Establish a linear pond to temporarily retain stormwater runoff, helping to control surface water build-up and reduce flood impacts |  |  |  | Parsons
296 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4094 | 54.6638 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-08 |  | 2026-11-03 | Contractor Design Completed | Yes | Provide a linear pond to temporarily retain stormwater runoff, helping to manage excess water and minimise surface water accumulation |  |  |  | Parsons
297 | Zayed | مدينة شخبوط - طريق سويحان باتجاه الى طريق المفرق | 24.3781 | 54.5951 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 2 | 2 | [7 empty] | 669600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 60000 | [6 empty] | Yes | D |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-30 |  | 2026-10-13 | Contractor Design Phase | [5 empty] | Parsons
298 | Zayed | مدينة زايد - MZ6 | 24.3826 | 54.6024 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | Zayed | مدينة زايد - MZ6 | 24.3867 | 54.6059 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | Zayed | مدينة زايد - MZ7 | 24.3819 | 54.6087 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
301 | Zayed | مدينة زايد - MZ7 | 24.3691 | 54.6046 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | Zayed | مدينة زايد - MZ10 | 24.3657 | 54.6032 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
303 | Zayed | مدينة زايد - MZ1 | 24.3604 | 54.6 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
304 | Zayed | مدينة زايد - MZ1 | 24.3892 | 54.6189 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | Zayed | مدينة زايد - MZ8 | 24.3922 | 54.6221 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
306 | Zayed | مدينة زايد - MZ9 | 24.349 | 54.6085 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
307 | Zayed | مدينة شخبوط - MSH7 | 24.3519 | 54.611 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
308 | Zayed | مدينة شخبوط - MSH7 | 24.348 | 54.6131 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
309 | Zayed | مدينة شخبوط - MSH7 | 24.35 | 54.6163 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
310 | Zayed | مدينة شخبوط - MSH5 | 24.3503 | 54.6186 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
311 | Zayed | مدينة شخبوط - MSH5 | 24.3443 | 54.6165 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
312 | Zayed | مدينة شخبوط - MSH5 | 24.3453 | 54.6214 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
313 | Zayed | مدينة شخبوط - MSH3 | 24.3373 | 54.6237 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
314 | Zayed | مدينة شخبوط - MSH1 | 24.3423 | 54.6272 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
315 | Zayed | مدينة شخبوط - MSH2 | 24.3436 | 54.6316 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
316 | Zayed | مدينة شخبوط - MSH1 | 24.3583 | 54.637 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
317 | Zayed | مدينة شخبوط - MSH15 | 24.3643 | 54.6345 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
318 | Zayed | مدينة شخبوط - MSH14 | 24.3697 | 54.6488 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
319 | Zayed | مدينة شخبوط - MSH17 | 24.3727 | 54.6467 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
320 | Zayed | مدينة شخبوط - MSH19 | 24.3721 | 54.6428 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
321 | Zayed | مدينة شخبوط - MSH19 | 24.3774 | 54.6306 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
322 | Zayed | مدينة شخبوط - MSH23 | 24.3756 | 54.6454 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
323 | Zayed | مدينة شخبوط - MSH20 | 24.388 | 54.6396 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | Zayed | مدينة شخبوط - MSH24 | 24.3174 | 54.6355 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
325 | Al Wathbah | بني ياس - EB1_03 | 24.3068 | 54.6446 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | Al Wathbah | بني ياس - EB6_01 | 24.2999 | 54.6381 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | Al Wathbah | بني ياس - EB7_B | 24.293 | 54.6517 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | Al Wathbah | بني ياس -EB10_A | 24.2888 | 54.6342 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | Al Wathbah | بني ياس -WB3_A | 24.3089 | 54.6456 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | Al Wathbah | بني ياس -EB11_01 | 24.3256 | 54.6376 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | Al Wathbah | بني ياس -EB1_04 | 24.3431 | 54.6493 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
332 | Al Wathbah | الشوامخ - SHM10 | 24.3498 | 54.6551 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
333 | Al Wathbah | الشوامخ - SHM9 | 24.3535 | 54.6619 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
334 | Al Wathbah | الشوامخ - SHM9 | 24.362 | 54.6552 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
335 | Al Wathbah | الشوامخ - SHM3 | 24.3681 | 54.6603 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
336 | Al Wathbah | الشوامخ - SHM2 | 24.3771 | 54.6636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
337 | Al Wathbah | الشوامخ - SHM1 | 24.3969 | 54.704 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | Al Wathbah | الشامخة - SH10 | 24.3834 | 54.7167 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
339 | Al Wathbah | الشامخة - SH11 | 24.3692 | 54.7154 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
340 | Al Wathbah | الشامخة - SH14 | 24.3287 | 54.7804 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
341 | Al Wathbah | مدينة الرياض - RD26 | 24.3325 | 54.7441 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | [5 empty] | 502200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
342 | Al Wathbah | مدينة الرياض - RD32 | 24.3562 | 54.7382 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | Al Wathbah | مدينة الرياض - RD11 | 24.3769 | 54.7572 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0
344 | Al Wathbah | مدينة الرياض - RD7 | 24.433 | 54.7399 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | Al Shahama | الفلاح - 1E | 24.431 | 54.7432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | Al Shahama | الفلاح - 1E | 24.4412 | 54.7333 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | Al Shahama | الفلاح - 1E | 24.4464 | 54.7381 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | Al Shahama | الفلاح - 1D | 24.4577 | 54.7377 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | Al Shahama | الفلاح - 1C | 24.4563 | 54.7178 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | Al Shahama | الفلاح - 1B | 24.5108 | 54.6005 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | Al Shahama | جزيرة ياس - YN3 | 24.504 | 54.596 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
352 | Al Shahama | جزيرة ياس - YN3 | 24.4977 | 54.6225 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | [5 empty] | 334800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
353 | Al Shahama | جزيرة ياس - YN7 | 24.5421 | 54.6796 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | Al Shahama | الباهية - Al Shahamah Old | 24.546 | 54.6293 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | Al Shahama | الباهية - Al Bahyah New | 24.5467 | 54.6367 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | Al Shahama | الباهية - Al Bahyah New | 24.5584 | 54.6798 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | Al Shahama | الباهية - Al Shahamah Old | 24.5655 | 54.6872 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | Al Shahama | الرحبة - Rahbah_A | 24.5663 | 54.6859 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
359 | Al Shahama | الرحبة - Rahbah_A | 24.5695 | 54.6862 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
360 | Al Shahama | الرحبة - Rahbah_A | 24.5769 | 54.6871 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
361 | Al Shahama | الرحبة - Rahbah_C | 24.6021 | 54.6998 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
362 | Al Shahama | الرحبة - Rahbah_G | 24.6241 | 54.7104 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
363 | Al Shahama | الرحبة - السمحة | 24.6542 | 54.7605 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
364 | Al Shahama | السمحة - Al Samhah East | 24.661 | 54.7647 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
365 | Al Shahama | السمحة - Al Samhah East | 24.6718 | 54.7741 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
366 | Al Shahama | السمحة -Al Samhah East Old | 24.6781 | 54.7753 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
367 | Al Shahama | السمحة -Al Samhah East Old | 24.6712 | 54.7479 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | Al Shahama | السمحة -Samhah_V | 24.6716 | 54.7581 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | Al Shahama | السمحة -Samhah_T | 24.6859 | 54.7676 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
370 | Al Shahama | السمحة -Al Samhah West Old_ | 24.1767 | 54.7566 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | Al Wathbah | Qasr Al Wathbah South | 24.2383 | 54.6337 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
372 | Al Wathbah | Al Dhafrah East | 24.2607 | 54.7083 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | Al Wathbah | Al Nahdah Al Askariah | 24.2634 | 54.7013 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | Al Wathbah | Al Nahdah Al Askariah | 24.2677 | 54.6937 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | Al Wathbah | Al Nahdah Al Askariah | 24.4633 | 54.3288 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-12 |  | 2026-12-12 | Contractor Design Phase
376 | Island | جوار نيشن تاور | 24.4656 | 54.3357 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
377 | Island | شارع الاواصر | 24.4661 | 54.3366 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
378 | Island | شارع الاواصر | 24.4664 | 54.335 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
379 | Island | ابراج الساحل | 24.4659 | 54.3345 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
380 | Island | اسبنس الكورنيش | 24.4696 | 54.3374 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
381 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4628 | 54.3411 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
382 | Island | خلف مدرسه سابس العالميه | 24.4626 | 54.3407 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
383 | Island | خلف مدرسه سابس العالميه | 24.4695 | 54.3377 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
384 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4848 | 54.3536 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
385 | Island | كليه ابو ظبي للاداره | 24.4835 | 54.358 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
386 | Island | شارع المطار مدخل قصر الحصن | 24.4792 | 54.3579 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
387 | Island | صيدليه الملا منطقه الخالديه | 24.4705 | 54.364 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | Island | مدينه خليفه الطبيه | 24.4691 | 54.3587 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | [5 empty] | 129600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | Island | مجلس المنهل | 24.4641 | 54.3728 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Concept Design and IDAS review stage | No
390 | Island | مجمع الكرامه | 24.4653 | 54.3744 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
391 | Island | خلف فندق فلايجيو شارع المطار | 24.4645 | 54.3745 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | TBC | Permitting and Work Phase | Yes |  |  |  |  | AECOM
392 | Island | خلف فندق فلايجيو شارع المطار | 24.4636 | 54.3777 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Concept Design and IDAS review stage | No
393 | Island | شارع الشيخه فاطمه اتجاه البطين تقاطع شارع المطار | 24.4646 | 54.3757 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
394 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4597 | 54.3733 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | TBC | Permitting and Work Phase | Yes |  |  |  |  | AECOM
395 | Island | تقاطع الشيخه فاطمه مع شارع الكرامه | 24.4575 | 54.371 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
396 | Island | صيدليه المركز الامريكي جوار مجمع ليوا | 24.4551 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
397 | Island | خلف المركز الامريكي | 24.4421 | 54.3678 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | Island | خلف مركز القاضي الطبي | 24.4425 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | Island | دوار الفروسيه 1 | 24.4431 | 54.3734 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | Island | جوار مجمع حدائق المشرف | 24.4465 | 54.3757 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
401 | Island | دوار الفروسيه 2 | 24.4351 | 54.3768 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | Island | اسفل جسر شارع الخليج العربي | 24.4473 | 54.3897 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | Island | جوار مبني الهويه والجنسيه 1 | 24.4477 | 54.3886 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
404 | Island | جوار مبني الهويه والجنسيه 2 | 24.4514 | 54.3551 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Concept Design and IDAS Review Stage | No
405 | Island | مسجد خالد بن الوليد منطقه البطين | 24.4514 | 54.3368 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
406 | Island | مرسي البطين جوار مرسى اليخوت 2 | 24.4544 | 54.3818 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
407 | Island | حديقه ام الامارات 2 | 24.5151 | 54.3925 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Concept Design and IDAS Review Stage | No
408 | Island | جسر شارع الشيخ خليفه بن زايد اتجاه السعديات | 24.5322 | 54.3661 | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
409 | Island | مينا زايد تابع للمطور | 24.5221 | 54.3682 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | Island | مينا زايد تابع للمطور | 24.5136 | 54.3685 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | Island | مينا زايد تابع للمطور | 24.502 | 54.377 | High | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Concept Design and IDAS Review Stage | No
412 | Island | فندق هلا ارجان- الزاهية | 24.4982 | 54.3727 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
413 | Island | مواقف سيارات خلف فندق نهال | 24.5013 | 54.3696 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
414 | Island | مستشفي الكورنيش | 24.5088 | 54.3794 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Concept Design and IDAS Review Stage | No
415 | Island | خلف المركز الاجتماعي الهندي | 24.5116 | 54.3834 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
416 | Island | مواقف سيارات سوق السجاد | 24.5121 | 54.3825 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 2 | 500 | 54000 | 144000 | 198000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-09-15 | Hand over phase | N/A |  |  | 2026-08-03 |  | AECOM
417 | Island | مواقف سيارات سوق السجاد | 24.5091 | 54.3824 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Concept Design and IDAS Review Stage | No
418 | Island | شارع خليفه بن زايد تقاطع شارع المينا | 24.5021 | 54.3813 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
419 | Island | جسر الماريا شارع حمدان بن محمد | 24.4956 | 54.374 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
420 | Island | شارع السلام قبل تقاطع شارع حمدان | 24.4919 | 54.378 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-22 |  | TBC | Concept Design and IDAS Review Stage | No |  |  |  |  | AECOM
421 | Island | جوار بنك ابو ظبي الاول - شارع السلام | 24.4902 | 54.3807 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
422 | Island | شارع الريم جوار مطعم جاد | 24.489 | 54.3831 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
423 | Island | جوار فندق جنه شارع الفلاح | 24.4846 | 54.3788 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
424 | Island | جوار مجمع طاقه 1 | 24.4835 | 54.3779 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | Island | جوار مجمع طاقه 2 | 24.486 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | Island | مواقف شارع السلام محال تاجير السيارات 1 | 24.485 | 54.3821 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | Island | مواقف شارع السلام محال تاجير السيارات 2 | 24.4818 | 54.3799 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | Island | مواقف حافلات مدرسه الشيخه فاطمه 1 | 24.4823 | 54.3796 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | Island | مواقف حافلات مدرسه الشيخه فاطمه 2 | 24.4815 | 54.3848 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | Island | جوار السفاره السريلانكيه | 24.4805 | 54.3823 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Concept Design and IDAS Review Stage | No
431 | Island | خلف مسجد حمد خليفه الخلفان | 24.4785 | 54.3816 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | TBC | Permitting and Work Phase | Yes |  |  |  |  | AECOM
432 | Island | مواقف مستشفي برجيل شارع الدفاع | 24.4892 | 54.3671 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | TBC | Permitting and Work Phase | Yes |  |  |  |  | AECOM
433 | Island | جوار مدرسه الايمان الخاصه | 24.4859 | 54.3712 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | Island | جوار مسجد عبد الرحيم خوري | 24.4847 | 54.3667 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | Island | شارع المرور مقابل سوق الذهب | 24.4859 | 54.366 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | Island | شارع المرور مقابل سوق الذهب | 24.4843 | 54.3644 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | Island | مواقف سوق الذهب | 24.4787 | 54.3697 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | Island | تقاطع شارع المرور مع شارع الفلاح | 24.4775 | 54.3715 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | Island | فندق النخيل شارع المرور | 24.4731 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | Island | خلف جراند الامارات شارع المرور | 24.4733 | 54.3683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | Island | جوار كنتاكي شارع المطار | 24.4704 | 54.3701 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | Island | فندق ماريوت شارع المطار | 24.4726 | 54.3803 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | Island | منطقه ال نهيان " محلات الشوكلاته " | 24.4634 | 54.372 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | Island | مجمع الكرامه | 24.4613 | 54.3749 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
445 | Island | مبني تدوير " الاشغال سابقا " | 24.4674 | 54.3689 | Very High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Concept Design and IDAS review stage | No
446 | Island | شارع ماء سلوان مقابل صحه مستشفي خليفه | 24.4625 | 54.3709 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
447 | Island | مجمع الكرامه | 24.4613 | 54.3699 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
448 | Island | شارع الكرامه | 24.4634 | 54.3673 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
449 | Island | روضه ابو ظبي للاطفال | 24.4543 | 54.3863 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
450 | Island | مطعم المزراب الشعبي | 24.4513 | 54.3925 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | Island | نادي الجزيره | 24.4449 | 54.3989 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | Island | خلف جامعه خليفه | 24.4437 | 54.4062 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
453 | Island | مسجد حمزه بن عبد المطلب | 24.4357 | 54.4114 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | Island | حديقه قاف " حديقه الملك حمد " | 24.4379 | 54.4136 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
455 | Island | خياط البيت السعيد - شارع المرور | 24.4355 | 54.4168 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
456 | Island | مركز فحص المركبات - ادنوك شارع المرور | 24.4378 | 54.4193 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | Island | كليه الشرطه | 24.4389 | 54.4185 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | Island | خلف مسجد سيف بن حارب المنصوري | 24.425 | 54.4186 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Concept Design and IDAS review stage | No
459 | Island | الدفاع المدني - القبيسات | 24.4245 | 54.4151 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
460 | Island | مسجد السيد يوسف الهاشمي | 24.4333 | 54.4034 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 31-Sep-2026 |  | TBC | Concept Design and IDAS review stage | No |  |  |  |  | AECOM
461 | Island | شارع سلامه بنت بطيء | 24.4315 | 54.4094 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
462 | Island | شارع المدرسه | 24.4267 | 54.4132 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
463 | Island | مقابل اكادميه ابو ظبي للسباحه | 24.4251 | 54.4099 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
464 | Island | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | 24.4397 | 54.4297 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | Island | شرق 43 | 24.4254 | 54.4254 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | Island | جوار مسجد جبريل | 24.4346 | 54.4317 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | Island | شارع الخرطوم - مدرسه الريم | 24.4361 | 54.4371 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
468 | Island | منطقه السعاده 1 | 24.4413 | 54.4351 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
469 | Island | منطقه السعاده 2 | 24.4402 | 54.4476 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | [5 empty] | 129600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
470 | Island | مجمع اوريكس | 24.4402 | 54.4518 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | Island | محطه ادنوك - جوار مجمع الظبي | 24.4378 | 54.4591 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | Island | مدخل قصر المينا مع شارع المروج | 24.4192 | 54.4567 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
473 | Island | دوار مدينه زايد الرياضيه | 24.4203 | 54.4617 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
474 | Island | ملاعب منطقه الروضه " غرب مطار البطين " | 24.4178 | 54.4647 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
475 | Island | منطقه الروضه " الابراج السكنيه " | 24.404 | 54.475 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
476 | Island | حديقه نادي الضباط | 24.4018 | 54.4696 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | [5 empty] | 216000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
477 | Island | اكادميه الرياضه النسائيه | 24.4034 | 54.4648 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | Island | مجمع هيلز ابو ظبي | 24.4036 | 54.4817 | Medium | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | Island | حديقه نادي الضباط | 24.4089 | 54.4797 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
480 | Island | مواقف واحه الكرامه | 24.4186 | 54.4467 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
481 | Island | مقابل دائره القضاء - شارع النوفل | 24.2512 | 54.4773 | High | No | N/A | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Concept Design and IDAS review stage | No
482 | Mussafah | طريق E-11 باتجاه الغويفات | 24.2094 | 54.8215 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 4 | 1000 | 108000 | 288000 | 396000 | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Concept Design and IDAS review stage | No |  |  |  |  | Parsons
483 | Al Wathbah | طريق E30 باتجاه العزب | 24.5742 | 55.176 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [7 empty] | Contractor Design
484 | Al Shahama | طريق E16 | 24.2982 | 54.7121 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
485 | Al Wathbah | شارع الخير | 24.3875 | 54.5247 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-15 |  | 2026-12-15 | Contractor Design Phase
486 | Zayed | شارع E30- جسر المصفح - الفلتر باتجاه خليفة | 24.3916 | 54.5423 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 1 |  | 1 | [6 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Yes | Quick Wins |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-09-11 | 2027-01-12 | Hand over phase | N/A |  | 2026-07-18 | 2026-08-11 |  | Parsons
487 | Zayed | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | 24.3716 | 54.6513 | Very High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | [5 empty] | 388800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 60000 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | 2026-10-25 |  | 2026-12-25 | Contractor Design Phase
488 | Zayed | دوار كرم الشام - مدينة شخبوط | 24.3715 | 54.6481 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | [6 empty] | Under Assessment | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [7 empty] | Contractor Design
489 | Zayed | شارع مطر بن خادم المهيري- مدينة شخبوط | 24.4871 | 54.6344 | High | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | 2026-10-30 |  | 2026-12-30 | Contractor Design Phase
490 | Al Shahama | شارع E12- من مجمع ياس باتجاه دبي | 24.1659 | 54.3382 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 0 | 0 | 0 | 0 | 2 |  |  | 2 | [5 empty] | 172800 |  | 0 | 0 | 0 | 0 | 0 | 33000 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-11-09 |  | 2026-12-29 | Contractor Design Completed | Yes | Regrade road levels and provide a gravel-lined swale with spillways to guide and safely convey stormwater runoff, reducing surface water accumulation |  |  |  | Parsons
491 | Mussafah | منطقة الأريام | 24.303228 | 54.4499 | Low | Yes | مطور | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
492 | Mussafah | ايكاد 2 | 24.2994 | 54.677 | High | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 194400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | 2026-10-01 |  | T.B.C | Concept Design and IDAS review stage | No
493 | Al Wathbah | مدينة الرياض - شارع الخير | 24.2478 | 54.1654 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 0 | 0 | 0 | 0 | 4 | 4 | [7 empty] | 1339200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-20 |  | 2026-12-30 | Contractor Design Phase | [5 empty] | Parsons
494 | Mussafah | منطقة النوف | 24.2105 | 54.8397 | Low | Yes | مطور | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
495 | Al Wathbah | ظهارة الطيب - أبو ظبي | 24.2881 | 54.6911 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 86400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
496 | Al Wathbah | مدينة الرياض - حوض 144 | 24.2167 | 54.4065 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0
497 | Mussafah | منطقة الأريام | 24.209 | 54.9138 | Low | Yes | مطور | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 32400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
498 | Al Wathbah | عزب دهان - الوافية | 24.5997 | 54.8401 | Medium | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 43200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
499 | Al Shahama | منطقة العجبان | 24.3108 | 54.5006 | Low | Yes | Private | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 28800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
500 | Mussafah | ايكاد 3 | 24.195870 | 54.9685 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | Al Wathbah | عزب دهان | 24.676 | 54.8319 | Low | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 14400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
502 | Al Shahama | مزارع عجبان - شارع عويد | 24.2996 | 54.4905 | Low | Yes | Private | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 28800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | Absense of Drainage Network
503 | Mussafah | ايكاد 3 | 24.254018 | 54.8251 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
504 | Al Wathbah | منطقة طريق الحفار | 24.299677 | 54.4849 | Low | No | N/A | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | [5 empty] | 14400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | [12 empty] | Absense of Drainage Network
505 | Mussafah | ايكاد 3 | 24.284 | 54.8305 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [5 empty] | 97200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
506 | Al Wathbah | أكادمية الدفاع المدني - طريق الحفار | 24.284 | 54.8305 | Low | Yes | Private Area | No | Absense of Drainage Network |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | [5 empty] | 28800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outfalls | Across | [13 empty] | 72 | 37 | 35 | 0 | [5 empty] | 19191600

## Exec Summary (hidden)
DMT Stormwater Resilience - Exec Summary
Region | Abu Dhabi
Configurable deadline
| Deadline_Date >> | 2027-02-14
SLIDE 1 - Region Overview
Overview & Criticality
Metric | Count | % of total
Total stormwater hotspots | 251
Very high | 2 | 0.7968%
High | 21 | 8.367%
Medium | 216 | 86.06%
Low | 12 | 4.781%
Highly critical (Very High + High) | 23 | 9.163%
Critical (Medium + Low) | 228 | 90.84%
Coverage (who owns the hotspot area)
Coverage | Count | % of total
Covered by Municipality (developer blank/No) | 199 | 79.28%
Covered by Private Entities / Developers | 52 | 20.72%
Root cause
Root cause | Count | % of total
Topography & Road Engineering | 179 | 71.31%
Inadequate Design Capacity | 1 | 0.3984%
Absence of Drainage Network | 71 | 28.29%
251
SLIDE 2 - Municipality Emergency Response Plan
Emergency Response - Daily Rate
Metric | Highly Critical | Critical | Total (w/o outfalls) | Total (w/ outfalls)
Hotspots covered | 23 | 228 | 251
Manpower (headcount) | 26 | 239 | 265 | 315 | Totals are daily
Diesel pumps (qty) | 41 | 339 | 380 | 380 | Totals are daily
Combination tankers (qty) | 0 | 0 | 0 | 0
Manpower budget (AED) | 640224 | 5885136 | 114480 | Totals are daily
Pumps budget (AED) | 2355696 | 20084976 | 393696 | Totals are daily
Tankers budget (AED) | 0 | 0 | 0
Outfalls & Siphons Budget (AED) |  |  | 199440 | Manpower: 50 (50% outfalls) | Pumps: 69 (12') + 20 (8')
Daily Emergency Budget (AED) |  |  | 707616
Additional Construction Work
Metric | Highly Critical | Critical | Total
Concrete Barriers Budget (AED) | 0 | 0 | 0
Sand Barriers Budget (AED) | 0 | 0 | 0
Detention Ponds Budget (AED) | 6000000 | 70500000 | 76500000
Collection Chambers Budget (AED) | 60000 | 0 | 60000
Total Additional Construction Work Budget (AED) | 6060000 | 70500000 | 76560000
Total Emergency Response Budget (10+2) 10 active rainfall days + 20% contingency
Metric |  |  | Total
Manpower budget (AED) |  |  | 1373760
Pumps budget (AED) |  |  | 4724352
Tankers budget (AED) |  |  | 0
Outfalls & Siphons Budget (AED) |  |  | 2393280 | Manpower:50 (50% outfalls) | Pumps: 69 (12') + 20 (8')
Additional Construction Work (AED) |  |  | 76560000
Total Emergency Response Budget (AED) |  |  | 8491392
Total ERP + Construction Budget (AED) |  |  | 85051392
Total Emergency Response Budget (Active 10+2 +Standby 3 months at 50% cost)
Metric |  |  | Total
Manpower budget (AED) |  |  | 6525360 | 24 hours, 90 standby days (3 months at 50% cost), 10 rainfall active days with 20% contingency (10+2)
Pumps budget (AED) |  |  | 22440672
Tankers budget (AED) |  |  | 41040000
Outfalls & Siphons Budget (AED) |  |  | 2393280 | Manpower: 50 (50% outfalls) | Pumps: 69 (12') + 20 (8') | no Standby cost for owned Pumps
Additional Construction Work (AED) |  |  | 76560000
Total Emergency Response Budget (AED) |  |  | 72399312
Total ERP + Construction Budget (AED) |  |  | 148959312

## Exec Sum Input (hidden)
[11 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [23 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan | [23 empty] | PROJECTS REGISTER (paste from IDD file > 'AD_Projects Register')
Hotspot_ID | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Check | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Check2 | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Covered by Construction? | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD_Design_Category | IDD_Intervention_Type | IDD_Owner | IDD_Mobilization_Date | IDD_Completion_Date_Raw | CPDS_CIP_ID | IDD_Status | Dup_Check | Criticality_Tier | Is_Highly_Critical | Is_Critical | Is_Private_Developer | Root_Cause_Category | IDD_Covered | Reg_Approved_Budget | Reg_Covered_Hotspots | IDD_Budget_Per_Hotspot | Muni_Emergency_Budget | ADM_Pond_Work_Flag | IDD_Pond_Work_Flag | ADM_IDD_Pond_Overlap_Flag | Pond_Overlap_Note | IDD_Completion_Date | IDD_Timeline_Status | CIP_ID | CPDS_ID | Project_Name | Classification | Start_Date | Resolution_End_Date | Forecasted_End_Date | Approved_Budget_AED | Covered_Hotspots | Additional_Budget_AED | Additional_Hotspots | Budget_Per_Hotspot
209 | Mussafah | مصفح صناعية - قطاع 3 | 24.3826 | 54.5106 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 0 | 180576 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 3 | 180576 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 229824 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
210 | Mussafah | مصفح صناعية - قطاع M19 | 24.3674 | 54.4811 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 0 | 180576 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 2 | 49248 | 3 | 180576 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 229824 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
211 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3578 | 54.4721 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
212 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3567 | 54.4724 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
213 | Mussafah | مصفح صناعية - قطاع M34 | 24.3463 | 54.5125 | High | No | N/A | Yes | The network needs an upgrade |  | 4 | 20736 | 77760 | 0 | 98496 | 5 | 1 | 3 | 1 | 2160 | 4320 | 864 | 7344 | 88128 | 330480 | 0 | 418608 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 4 | 98496 | 5 | 418608 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 517104 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
215 | Mussafah | مصفح صناعية - ICAD I | 24.3218 | 54.5048 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
216 | Mussafah | مصفح صناعية - ICAD I | 24.3268 | 54.4839 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
217 | Mussafah | مصفح صناعية - قطاع M42 | 24.3362 | 54.4781 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
218 | Mussafah | مصفح صناعية - قطاع M43 | 24.3438 | 54.4807 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
219 | Mussafah | مصفح صناعية - قطاع M32_02 | 24.3575 | 54.5142 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
220 | Mussafah | مصفح صناعية - قطاع M24 | 24.3607 | 54.5204 | Low | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
225 | Zayed | مدينة محمد بن زايد - Z8 | 24.3514 | 54.5527 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
227 | Zayed | مدينة محمد بن زايد - ME9 | 24.3451 | 54.5352 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  | 2 |  | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 0 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 164160 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 188784 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
228 | Zayed | مدينة محمد بن زايد - ME9 | 24.3385 | 54.5324 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
229 | Zayed | مدينة محمد بن زايد - ME10 | 24.3359 | 54.5357 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 4 |  |  | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 0 | 196992 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 2 | 49248 | 4 | 196992 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 246240 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
230 | Zayed | مدينة محمد بن زايد - ME11 | 24.3291 | 54.5384 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
231 | Zayed | مدينة محمد بن زايد - ME11 | 24.3268 | 54.5389 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
232 | Zayed | مدينة محمد بن زايد - Z20 | 24.3157 | 54.5398 | Medium | Yes | under developer(Npc) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
233 | Zayed | مدينة محمد بن زايد - Z24 | 24.3153 | 54.5508 | Medium | Yes | under developer(Npc) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
234 | Zayed | مدينة محمد بن زايد - Z23 | 24.3168 | 54.5556 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
235 | Zayed | مدينة محمد بن زايد - Z30 | 24.2966 | 54.5551 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
236 | Zayed | مدينة محمد بن زايد - Z30 | 24.2997 | 54.5587 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
237 | Zayed | مدينة محمد بن زايد - Z30 | 24.3017 | 54.5645 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
238 | Zayed | مدينة محمد بن زايد - Z30 | 24.295 | 54.5672 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 1020864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
239 | Zayed | مدينة محمد بن زايد - Z31 | 24.3018 | 54.5744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
240 | Zayed | مدينة محمد بن زايد - Z34 | 24.3017 | 54.5839 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
241 | Zayed | مدينة محمد بن زايد - Z34 | 24.3021 | 54.5813 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
242 | Zayed | مدينة محمد بن زايد - Z34 | 24.304 | 54.5828 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
243 | Zayed | مدينة محمد بن زايد - Z34 | 24.3022 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
244 | Zayed | مدينة محمد بن زايد - Z34 | 24.3047 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
245 | Zayed | مدينة محمد بن زايد - Z35 | 24.3076 | 54.5916 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
246 | Zayed | مدينة محمد بن زايد - Z35 | 24.3161 | 54.5864 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
247 | Zayed | مدينة محمد بن زايد - Z33 | 24.3227 | 54.577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
248 | Zayed | مدينة محمد بن زايد - Z33 | 24.3192 | 54.5782 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
249 | Zayed | مدينة محمد بن زايد - Z33 | 24.323 | 54.5754 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
250 | Zayed | مدينة محمد بن زايد - Z22 | 24.3223 | 54.5688 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
251 | Zayed | مدينة محمد بن زايد - Z22 | 24.3222 | 54.5645 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
252 | Zayed | مدينة محمد بن زايد - Z22 | 24.3241 | 54.5623 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
253 | Zayed | مدينة محمد بن زايد - Z21 | 24.3232 | 54.5577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
254 | Zayed | مدينة محمد بن زايد - Z15 | 24.3334 | 54.5579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
255 | Zayed | مدينة محمد بن زايد - Z13 | 24.3437 | 54.5546 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
256 | Zayed | مدينة محمد بن زايد - Z13_01 | 24.3422 | 54.5636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
257 | Zayed | مدينة محمد بن زايد - Z36 | 24.3356 | 54.5782 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
258 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2868 | 54.5897 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 856704 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
259 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2818 | 54.5849 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 856704 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
260 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.256 | 54.6342 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
261 | Zayed | ربدان - RB1 | 24.4179 | 54.4945 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
262 | Zayed | ربدان - RB2 | 24.4149 | 54.4926 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
263 | Zayed | ربدان - RB7 | 24.407 | 54.515 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
264 | Zayed | ربدان - RB14 | 24.4024 | 54.4879 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
266 | Zayed | ربدان - RB28 | 24.3947 | 54.5009 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
269 | Zayed | SW17_مدينة خليفة - 01 | 24.4116 | 54.5139 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
270 | Zayed | مدينة خليفة - SW17 - وطني | 24.4163 | 54.5465 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
271 | Zayed | مدينة خليفة - SW17 - وطني | 24.4148 | 54.5432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
272 | Zayed | مدينة خليفة - SW17 - وطني | 24.4144 | 54.5405 | High | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  | 2 |  | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 0 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 164160 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 188784 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
274 | Zayed | مدينة خليفة | 24.4144 | 54.5411 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
275 | Zayed | مدينة خليفة - SW13 | 24.4132 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
276 | Zayed | مدينة خليفة - SW2 | 24.4197 | 54.5586 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
277 | Zayed | مدينة خليفة - SW3 | 24.4147 | 54.5641 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
278 | Zayed | مدينة خليفة - SW4 | 24.41 | 54.5645 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
280 | Zayed | مدينة خليفة - SE3 | 24.4195 | 54.5683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
281 | Zayed | مدينة خليفة - SE13 | 24.4184 | 54.5832 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
282 | Zayed | مدينة خليفة - SE24 | 24.414 | 54.5885 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
283 | Zayed | مدينة خليفة - SE26 | 24.4092 | 54.5924 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
284 | Zayed | مدينة خليفة - SE6 | 24.4016 | 54.5785 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
285 | Zayed | مدينة خليفة - SE16 | 24.4027 | 54.5843 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
286 | Zayed | مدينة خليفة - SE26 | 24.4045 | 54.592 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
287 | Zayed | مدينة خليفة - SE36 | 24.407 | 54.6048 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
288 | Zayed | مدينة خليفة - SE38 | 24.4124 | 54.6033 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
289 | Zayed | مدينة خليفة - SE35 | 24.4158 | 54.6016 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
290 | Zayed | مدينة خليفة - SE44 | 24.43 | 54.5817 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
291 | Zayed | مدينة خليفة - SE47 | 24.4365 | 54.5869 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
292 | Zayed | مدينة خليفة - SE47 | 24.44 | 54.5905 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
293 | Zayed | مدينة خليفة - SE40 | 24.4264 | 54.6002 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
294 | Zayed | مدينة خليفة - الراحة - RBW13 | 24.4343 | 54.5597 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
298 | Zayed | مدينة زايد - MZ6 | 24.3781 | 54.5951 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
299 | Zayed | مدينة زايد - MZ6 | 24.3826 | 54.6024 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
300 | Zayed | مدينة زايد - MZ7 | 24.3867 | 54.6059 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
301 | Zayed | مدينة زايد - MZ7 | 24.3819 | 54.6087 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
302 | Zayed | مدينة زايد - MZ10 | 24.3691 | 54.6046 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
303 | Zayed | مدينة زايد - MZ1 | 24.3657 | 54.6032 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
304 | Zayed | مدينة زايد - MZ1 | 24.3604 | 54.6 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
305 | Zayed | مدينة زايد - MZ8 | 24.3892 | 54.6189 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
306 | Zayed | مدينة زايد - MZ9 | 24.3922 | 54.6221 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
307 | Zayed | مدينة شخبوط - MSH7 | 24.349 | 54.6085 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
308 | Zayed | مدينة شخبوط - MSH7 | 24.3519 | 54.611 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
309 | Zayed | مدينة شخبوط - MSH7 | 24.348 | 54.6131 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
310 | Zayed | مدينة شخبوط - MSH5 | 24.35 | 54.6163 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
311 | Zayed | مدينة شخبوط - MSH5 | 24.3503 | 54.6186 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
312 | Zayed | مدينة شخبوط - MSH5 | 24.3443 | 54.6165 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
313 | Zayed | مدينة شخبوط - MSH3 | 24.3453 | 54.6214 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
314 | Zayed | مدينة شخبوط - MSH1 | 24.3373 | 54.6237 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
315 | Zayed | مدينة شخبوط - MSH2 | 24.3423 | 54.6272 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
316 | Zayed | مدينة شخبوط - MSH1 | 24.3436 | 54.6316 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
317 | Zayed | مدينة شخبوط - MSH15 | 24.3583 | 54.637 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
318 | Zayed | مدينة شخبوط - MSH14 | 24.3643 | 54.6345 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
319 | Zayed | مدينة شخبوط - MSH17 | 24.3697 | 54.6488 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
320 | Zayed | مدينة شخبوط - MSH19 | 24.3727 | 54.6467 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
321 | Zayed | مدينة شخبوط - MSH19 | 24.3721 | 54.6428 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
322 | Zayed | مدينة شخبوط - MSH23 | 24.3774 | 54.6306 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
323 | Zayed | مدينة شخبوط - MSH20 | 24.3756 | 54.6454 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
324 | Zayed | مدينة شخبوط - MSH24 | 24.388 | 54.6396 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
325 | Al Wathbah | بني ياس - EB1_03 | 24.3174 | 54.6355 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
326 | Al Wathbah | بني ياس - EB6_01 | 24.3068 | 54.6446 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
327 | Al Wathbah | بني ياس - EB7_B | 24.2999 | 54.6381 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
328 | Al Wathbah | بني ياس -EB10_A | 24.293 | 54.6517 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
329 | Al Wathbah | بني ياس -WB3_A | 24.2888 | 54.6342 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
330 | Al Wathbah | بني ياس -EB11_01 | 24.3089 | 54.6456 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
331 | Al Wathbah | بني ياس -EB1_04 | 24.3256 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
332 | Al Wathbah | الشوامخ - SHM10 | 24.3431 | 54.6493 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
333 | Al Wathbah | الشوامخ - SHM9 | 24.3498 | 54.6551 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
334 | Al Wathbah | الشوامخ - SHM9 | 24.3535 | 54.6619 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
335 | Al Wathbah | الشوامخ - SHM3 | 24.362 | 54.6552 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
336 | Al Wathbah | الشوامخ - SHM2 | 24.3681 | 54.6603 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
337 | Al Wathbah | الشوامخ - SHM1 | 24.3771 | 54.6636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
338 | Al Wathbah | الشامخة - SH10 | 24.3969 | 54.704 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
339 | Al Wathbah | الشامخة - SH11 | 24.3834 | 54.7167 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
340 | Al Wathbah | الشامخة - SH14 | 24.3692 | 54.7154 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
341 | Al Wathbah | مدينة الرياض - RD26 | 24.3287 | 54.7804 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 | 3 |  |  | 6480 | 0 | 0 | 6480 | 77760 | 291600 | 0 | 369360 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 2 | 49248 | 3 | 369360 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 418608 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
342 | Al Wathbah | مدينة الرياض - RD32 | 24.3325 | 54.7441 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
343 | Al Wathbah | مدينة الرياض - RD11 | 24.3562 | 54.7382 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
344 | Al Wathbah | مدينة الرياض - RD7 | 24.3769 | 54.7572 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
345 | Al Shahama | الفلاح - 1E | 24.433 | 54.7399 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
346 | Al Shahama | الفلاح - 1E | 24.431 | 54.7432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
347 | Al Shahama | الفلاح - 1E | 24.4412 | 54.7333 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
348 | Al Shahama | الفلاح - 1D | 24.4464 | 54.7381 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
349 | Al Shahama | الفلاح - 1C | 24.4577 | 54.7377 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
350 | Al Shahama | الفلاح - 1B | 24.4563 | 54.7178 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
351 | Al Shahama | جزيرة ياس - YN3 | 24.5108 | 54.6005 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
352 | Al Shahama | جزيرة ياس - YN3 | 24.504 | 54.596 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
353 | Al Shahama | جزيرة ياس - YN7 | 24.4977 | 54.6225 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
354 | Al Shahama | الباهية - Al Shahamah Old | 24.5421 | 54.6796 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
355 | Al Shahama | الباهية - Al Bahyah New | 24.546 | 54.6293 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
356 | Al Shahama | الباهية - Al Bahyah New | 24.5467 | 54.6367 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
357 | Al Shahama | الباهية - Al Shahamah Old | 24.5584 | 54.6798 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
358 | Al Shahama | الرحبة - Rahbah_A | 24.5655 | 54.6872 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
359 | Al Shahama | الرحبة - Rahbah_A | 24.5663 | 54.6859 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
360 | Al Shahama | الرحبة - Rahbah_A | 24.5695 | 54.6862 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
361 | Al Shahama | الرحبة - Rahbah_C | 24.5769 | 54.6871 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
362 | Al Shahama | الرحبة - Rahbah_G | 24.6021 | 54.6998 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
363 | Al Shahama | الرحبة - السمحة | 24.6241 | 54.7104 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
364 | Al Shahama | السمحة - Al Samhah East | 24.6542 | 54.7605 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
365 | Al Shahama | السمحة - Al Samhah East | 24.661 | 54.7647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
366 | Al Shahama | السمحة -Al Samhah East Old | 24.6718 | 54.7741 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
367 | Al Shahama | السمحة -Al Samhah East Old | 24.6781 | 54.7753 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
368 | Al Shahama | السمحة -Samhah_V | 24.6712 | 54.7479 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
369 | Al Shahama | السمحة -Samhah_T | 24.6716 | 54.7581 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
370 | Al Shahama | السمحة -Al Samhah West Old_ | 24.6859 | 54.7676 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
371 | Al Wathbah | Qasr Al Wathbah South | 24.1767 | 54.7566 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
372 | Al Wathbah | Al Dhafrah East | 24.2383 | 54.6337 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
373 | Al Wathbah | Al Nahdah Al Askariah | 24.2607 | 54.7083 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
374 | Al Wathbah | Al Nahdah Al Askariah | 24.2634 | 54.7013 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
375 | Al Wathbah | Al Nahdah Al Askariah | 24.2677 | 54.6937 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
387 | Island | صيدليه الملا منطقه الخالديه | 24.4792 | 54.3579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
388 | Island | مدينه خليفه الطبيه | 24.4705 | 54.364 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  |  | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 0 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 3 | 147744 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 196992 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
389 | Island | مجلس المنهل | 24.4691 | 54.3587 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
392 | Island | خلف فندق فلايجيو شارع المطار | 24.4645 | 54.3745 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
397 | Island | خلف المركز الامريكي | 24.4551 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
398 | Island | خلف مركز القاضي الطبي | 24.4421 | 54.3678 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
399 | Island | دوار الفروسيه 1 | 24.4425 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
400 | Island | جوار مجمع حدائق المشرف | 24.4431 | 54.3734 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
401 | Island | دوار الفروسيه 2 | 24.4465 | 54.3757 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
402 | Island | اسفل جسر شارع الخليج العربي | 24.4351 | 54.3768 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
403 | Island | جوار مبني الهويه والجنسيه 1 | 24.4473 | 54.3897 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
404 | Island | جوار مبني الهويه والجنسيه 2 | 24.4477 | 54.3886 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
406 | Island | مرسي البطين جوار مرسى اليخوت 2 | 24.4514 | 54.3368 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
407 | Island | حديقه ام الامارات 2 | 24.4544 | 54.3818 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
409 | Island | مينا زايد تابع للمطور | 24.5322 | 54.3661 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
410 | Island | مينا زايد تابع للمطور | 24.5221 | 54.3682 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
411 | Island | مينا زايد تابع للمطور | 24.5136 | 54.3685 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
413 | Island | مواقف سيارات خلف فندق نهال | 24.4982 | 54.3727 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
414 | Island | مستشفي الكورنيش | 24.5013 | 54.3696 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
417 | Island | مواقف سيارات سوق السجاد | 24.5121 | 54.3825 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
421 | Island | جوار بنك ابو ظبي الاول - شارع السلام | 24.4919 | 54.378 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
422 | Island | شارع الريم جوار مطعم جاد | 24.4902 | 54.3807 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
423 | Island | جوار فندق جنه شارع الفلاح | 24.489 | 54.3831 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
424 | Island | جوار مجمع طاقه 1 | 24.4846 | 54.3788 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
425 | Island | جوار مجمع طاقه 2 | 24.4835 | 54.3779 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
426 | Island | مواقف شارع السلام محال تاجير السيارات 1 | 24.486 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
427 | Island | مواقف شارع السلام محال تاجير السيارات 2 | 24.485 | 54.3821 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
428 | Island | مواقف حافلات مدرسه الشيخه فاطمه 1 | 24.4818 | 54.3799 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
429 | Island | مواقف حافلات مدرسه الشيخه فاطمه 2 | 24.4823 | 54.3796 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
430 | Island | جوار السفاره السريلانكيه | 24.4815 | 54.3848 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
433 | Island | جوار مدرسه الايمان الخاصه | 24.4892 | 54.3671 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
434 | Island | جوار مسجد عبد الرحيم خوري | 24.4859 | 54.3712 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
435 | Island | شارع المرور مقابل سوق الذهب | 24.4847 | 54.3667 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
436 | Island | شارع المرور مقابل سوق الذهب | 24.4859 | 54.366 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
437 | Island | مواقف سوق الذهب | 24.4843 | 54.3644 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
438 | Island | تقاطع شارع المرور مع شارع الفلاح | 24.4787 | 54.3697 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
439 | Island | فندق النخيل شارع المرور | 24.4775 | 54.3715 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
440 | Island | خلف جراند الامارات شارع المرور | 24.4731 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
441 | Island | جوار كنتاكي شارع المطار | 24.4733 | 54.3683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
442 | Island | فندق ماريوت شارع المطار | 24.4704 | 54.3701 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
443 | Island | منطقه ال نهيان " محلات الشوكلاته " | 24.4726 | 54.3803 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
444 | Island | مجمع الكرامه | 24.4634 | 54.372 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
445 | Island | مبني تدوير " الاشغال سابقا " | 24.4613 | 54.3749 | Very High | No | N/A | Yes | Inadequate Design Capacity |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 0 |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Inadequate Design Capacity | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
446 | Island | شارع ماء سلوان مقابل صحه مستشفي خليفه | 24.4674 | 54.3689 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
447 | Island | مجمع الكرامه | 24.4625 | 54.3709 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
448 | Island | شارع الكرامه | 24.4613 | 54.3699 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
449 | Island | روضه ابو ظبي للاطفال | 24.4634 | 54.3673 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
450 | Island | مطعم المزراب الشعبي | 24.4543 | 54.3863 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
451 | Island | نادي الجزيره | 24.4513 | 54.3925 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 4 |  |  | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 0 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 4 | 196992 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 246240 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
452 | Island | خلف جامعه خليفه | 24.4449 | 54.3989 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
453 | Island | مسجد حمزه بن عبد المطلب | 24.4437 | 54.4062 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
454 | Island | حديقه قاف " حديقه الملك حمد " | 24.4357 | 54.4114 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
455 | Island | خياط البيت السعيد - شارع المرور | 24.4379 | 54.4136 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
456 | Island | مركز فحص المركبات - ادنوك شارع المرور | 24.4355 | 54.4168 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
457 | Island | كليه الشرطه | 24.4378 | 54.4193 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
458 | Island | خلف مسجد سيف بن حارب المنصوري | 24.4389 | 54.4185 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
461 | Island | شارع سلامه بنت بطيء | 24.4333 | 54.4034 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
462 | Island | شارع المدرسه | 24.4315 | 54.4094 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
463 | Island | مقابل اكادميه ابو ظبي للسباحه | 24.4267 | 54.4132 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
464 | Island | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | 24.4251 | 54.4099 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
465 | Island | شرق 43 | 24.4397 | 54.4297 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
466 | Island | جوار مسجد جبريل | 24.4254 | 54.4254 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
467 | Island | شارع الخرطوم - مدرسه الريم | 24.4346 | 54.4317 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
468 | Island | منطقه السعاده 1 | 24.4361 | 54.4371 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
469 | Island | منطقه السعاده 2 | 24.4413 | 54.4351 | Medium | No | N/A | No | Absense of Drainage Network |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  |  | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 0 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 3 | 147744 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 196992 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
470 | Island | مجمع اوريكس | 24.4402 | 54.4476 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
471 | Island | محطه ادنوك - جوار مجمع الظبي | 24.4402 | 54.4518 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 4 |  |  | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 0 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 4 | 196992 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 246240 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
472 | Island | مدخل قصر المينا مع شارع المروج | 24.4378 | 54.4591 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
473 | Island | دوار مدينه زايد الرياضيه | 24.4192 | 54.4567 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
474 | Island | ملاعب منطقه الروضه " غرب مطار البطين " | 24.4203 | 54.4617 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
475 | Island | منطقه الروضه " الابراج السكنيه " | 24.4178 | 54.4647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
476 | Island | حديقه نادي الضباط | 24.404 | 54.475 | Medium | No | N/A | No | Absense of Drainage Network |  | 4 | 20736 | 77760 | 0 | 98496 | 5 |  |  | 5 | 0 | 0 | 4320 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 4 | 98496 | 5 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 344736 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
477 | Island | اكادميه الرياضه النسائيه | 24.4018 | 54.4696 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
478 | Island | مجمع هيلز ابو ظبي | 24.4034 | 54.4648 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
479 | Island | حديقه نادي الضباط | 24.4036 | 54.4817 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
480 | Island | مواقف واحه الكرامه | 24.4089 | 54.4797 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
481 | Island | مقابل دائره القضاء - شارع النوفل | 24.4186 | 54.4467 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
483 | Al Wathbah | طريق E30 باتجاه العزب | 24.2094 | 54.8215 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
484 | Al Shahama | طريق E16 | 24.5742 | 55.176 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
485 | Al Wathbah | شارع الخير | 24.2982 | 54.7121 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
487 | Zayed | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | 24.3916 | 54.5423 | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  | 2 |  | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 0 | 164160 | 0 | 0 | 0 | 0 | 750000 | 60000 | Yes | 1 | 24624 | 2 | 164160 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 998784 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
488 | Zayed | دوار كرم الشام - مدينة شخبوط | 24.3716 | 54.6513 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
489 | Zayed | شارع مطر بن خادم المهيري- مدينة شخبوط | 24.3715 | 54.6481 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
491 | Mussafah | منطقة الأريام | 24.1659 | 54.3382 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
492 | Mussafah | ايكاد 2 | 24.303228 | 54.4499 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
494 | Mussafah | منطقة النوف | 24.2478 | 54.1654 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
495 | Al Wathbah | ظهارة الطيب - أبو ظبي | 24.2105 | 54.8397 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
496 | Al Wathbah | مدينة الرياض - حوض 144 | 24.2881 | 54.6911 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
497 | Mussafah | منطقة الأريام | 24.2167 | 54.4065 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
498 | Al Wathbah | عزب دهان - الوافية | 24.209 | 54.9138 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
499 | Al Shahama | منطقة العجبان | 24.5997 | 54.8401 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
500 | Mussafah | ايكاد 3 | 24.3108 | 54.5006 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
501 | Al Wathbah | عزب دهان | 24.195870 | 54.9685 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
502 | Al Shahama | مزارع عجبان - شارع عويد | 24.676 | 54.8319 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
503 | Mussafah | ايكاد 3 | 24.2996 | 54.4905 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
504 | Al Wathbah | منطقة طريق الحفار | 24.254018 | 54.8251 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
505 | Mussafah | ايكاد 3 | 24.299677 | 54.4849 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
506 | Al Wathbah | أكادمية الدفاع المدني - طريق الحفار | 24.284 | 54.8305 | Low | Yes | Private Area | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[11 empty] | 265 |  |  |  | 6525360 | 380 | 38 | 28 | 314 | [7 empty] | 22440672 |  |  |  |  | 76500000 | 60000 |  |  | 6525360 | 380
Note on BQ2: Must match the CPDS_CIP_ID values in the hotspot table for the CAPEX lookup to work.

## Full List (hidden)
[11 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [20 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan
[38 empty] | Select Yes or No | Select one: Critical Infrastructure, Detailed Design, Fast-Track, or Quick Win | Provide the primary solution such as inlet, pipe, Upgrade to Catchment , Pond / Spillway, etc | Select one: Permanent, Interim, or Temporary | Please specify if additional budget is required for this hotspot (Yes/No) | Provide the requested budget for each applicable hotspot. If a single project spans multiple hotspots, list the budget only once under the primary hotspot. For all other covered hotspot entries, replace the budget with: "Included in Hotspot #X budget." | Provide the current rainfall design event, including the return period | Provide the existing network’s technical or hydraulic capacit | Provide the future or target rainfall design event, including the return period | Provide the future or target network capacity after the planned intervention | Provide the estimated floodwater volume managed by network after intervention | Provide the expected number of hours required for floodwater to recede after intervention | Revise the planned mobilization date | Revise the planned completion date | Select one: Contractor Design phase, Parsons Verification Phase, IDAS Review Phase, Municipality Permitting Phase, Implementation phase, Hand Over Phase | Select Yes or No. Enter Yes only after formal approval has been issued. | Provide the actual mobilization date (only after actual mobilization) | Provide the actual completion date (only after actual completion) | Select one: Not Started, On Track, Delayed, or Completed | Provide the full name of the accountable IDD owner.
Hotspot_ID | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD Interventoin Planned | IDD_Design_Category | Design Solution | Type of Intervention | Additional Budget Requirment | Additional Budget Requested | Hotspot Network Rain Design Event (Current) | Hotspot Network Design Technical Capacity (Current) | Hotspot Network Rain Design Event (Future) | Hotspot Network Design Technical Capacity (Future) | Flood Volume Capacity after Intervention | Associated recovery time after intervention | Planned_IDD_Mobilization_Date | Planned_IDD_Completion_Date | Project Stage | Approval from IDAS secured (Yes/No) | Actual_Mobilization_Date | Actual_Completion_Date | Intervention status | IDD_Owner_Name | Is_Private_Developer | Root_Cause_Category | IDD_Covered | IDD_Completion_Date2 | IDD_Timeline_Status
1 | Al Shahama | نفق الشهامة | 24.546 | 54.691 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-21 | #REF!
2 | Al Shahama | شارع الشيخ زايد بن سلطان | 24.4927 | 54.6493 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 | 2026-12-09 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-09 | #REF!
3 | Al Shahama | مجمع الجسور ياس | 24.4858 | 54.6449 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
4 | Al Shahama | نفق الشهامة الجديدة المؤدي الى ديرفيلدز مول | 24.5378 | 54.6848 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-09 | 2027-01-26 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-26 | #REF!
5 | Al Shahama | جسر الشهامة نادي الوحدة | 24.5611 | 54.6953 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-21 | #REF!
6 | Al Shahama | نفق كيزاد | 24.7287 | 54.8168 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Lowering Project | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 | 2026-12-31 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
7 | Al Shahama | روضة الريف – شارع الشهد | 24.4622 | 54.68 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
8 | Al Shahama | خليفة الصناعية - شارع غناضة | 24.7304 | 54.7793 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-10-08 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-08 | #REF!
9 | Al Shahama | منطقة الفلاح 4 | 24.4185 | 54.7241 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-11-30 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-30 | #REF!
10 | Al Shahama | منطقة الفلاح 1 | 24.4213 | 54.7472 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-25 | #REF!
11 | Al Shahama | ياس الحي الاماراتي | 24.4989 | 54.6024 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-08 | 2027-01-26 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-26 | #REF!
12 | Al Shahama | الباهية - شارع عجيج – الباهية مدرسة أميتي | 24.5313 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 | 2026-12-11 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-11 | #REF!
13 | Al Shahama | شارع عجيج - الصدر | 24.5934 | 54.6515 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-29 | 2027-02-16 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2027-02-16 | #REF!
14 | Mussafah | شارع سلطان بن محمد القبيسي - بعد الجسر المؤدي الى المصفح- الأول | 24.3736 | 54.5229 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
15 | Mussafah | مدينة الامارات الانسانية | 24.3789 | 54.5129 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
16 | Mussafah | Sector 17 | 24.3656 | 54.4832 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
17 | Mussafah | Sector 2 | 24.3779 | 54.5221 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
18 | Mussafah | Sector 15 | 24.3736 | 54.4826 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
19 | Mussafah | Sector 1 | 24.3792 | 54.5178 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
20 | Mussafah | Sector 1 | 24.3825 | 54.5234 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
21 | Zayed | مدخل مصفح القادم من شارع الخليج العربي | 24.3941 | 54.5186 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-12 | 2026-09-05 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-05 | #REF!
22 | Mussafah | Sector 9 | 24.3686 | 54.4914 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
23 | Mussafah | دوار دينا تريد | 24.2884 | 54.5646 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-12-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-25 | #REF!
24 | Mussafah | مستودعات البلدية | 24.2934 | 54.581 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-12-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-11 | #REF!
25 | Mussafah | طريق حميم | 24.1494 | 54.4205 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 | 2026-12-26 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-26 | #REF!
26 | Al Wathbah | مدينة الرياض - شارع طوي القايمة | 24.3314 | 54.7084 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-12-13 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-13 | #REF!
27 | Al Wathbah | مدينة الرياض - شارع الخير | 24.3432 | 54.7578 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-12-15 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
28 | Al Wathbah | مدينة الرياض - شارع العصري بن حمودة الظاهري | 24.3257 | 54.7446 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 | 2026-12-15 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
29 | Al Wathbah | مدينة الرياض -شارع الرياض | 24.333 | 54.7652 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-12-16 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-16 | #REF!
30 | Al Wathbah | مدينة الرياض -شارع النهضة | 24.3273 | 54.7042 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 | 2026-12-13 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-13 | #REF!
31 | Al Wathbah | مدينة الرياض -شارع الميثاق | 24.3307 | 54.7001 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-12-06 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-06 | #REF!
32 | Al Wathbah | مدينة الرياض - شارع سيح القطع | 24.3364 | 54.7356 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 | 2026-12-21 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-21 | #REF!
33 | Al Wathbah | مدينة الرياض - شارع الصنوبر | 24.3415 | 54.7524 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 | 2026-12-13 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-13 | #REF!
34 | Al Wathbah | شارع الشيخ محمد بن راشد | 24.3732 | 54.729 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-09-14 | 2D modelling |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-14 | #REF!
35 | Al Wathbah | خلف مسلخ بني ياس | 24.3037 | 54.6711 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 | 2026-10-02 | 2D modelling |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
36 | Al Wathbah | الشوامخ - شارع خضيرمان | 24.3535 | 54.649 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 | 2027-02-03 | Parsons Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-02-03 | #REF!
37 | Al Wathbah | الشوامخ - مدخل ومخرج المزن | 24.3505 | 54.6802 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 | 2026-12-15 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
38 | Al Wathbah | شارع الشوامخ | 24.3855 | 54.6702 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 | 2026-09-07 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-07 | #REF!
39 | Al Wathbah | دوار - الشوامخ 12 | 24.3843 | 54.6745 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 | 2026-09-08 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-08 | #REF!
40 | Al Wathbah | مدينة الرياض -شارع الخير | 24.3221 | 54.749 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-12-17 | 2D Modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-17 | #REF!
41 | Al Wathbah | الشوامخ 7 - شارع بدع بوحصية | 24.3721 | 54.6705 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-12-21 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-21 | #REF!
42 | Al Wathbah | مسجد الشيخة عفراء بنت زايد ال نهيان | 24.1836 | 54.9937 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-30 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-30 | #REF!
43 | Al Wathbah | الختم القديمة - بجوار حديقة الختم | 24.1881 | 54.9966 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-11-26 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-26 | #REF!
44 | Al Wathbah | بني ياس - شارع اليال | 24.3293 | 54.6331 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-11-30 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-30 | #REF!
45 | Al Wathbah | بني ياس -شارع اليال | 24.3218 | 54.6427 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 | 2026-11-12 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
46 | Al Wathbah | بني ياس -شارع اليال | 24.3144 | 54.6534 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 | 2026-08-10 | Permitting Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-08-10 | #REF!
47 | Al Wathbah | بني ياس - شارع اليال | 24.3069 | 54.6633 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 | 2026-08-10 | Permitting Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-08-10 | #REF!
48 | Al Wathbah | بني ياس - شارع الشيخ محمد بن راشد | 24.2888 | 54.6549 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-15 | 2026-09-14 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-14 | #REF!
49 | Al Wathbah | بني ياس - شارع الخويرة | 24.3044 | 54.6281 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 | 2026-12-27 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-27 | #REF!
50 | Al Wathbah | نفق الوثبة | 24.2693 | 54.6681 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2027-01-24 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-24 | #REF!
51 | Al Wathbah | نفق النهضة | 24.2417 | 54.7368 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-20 | 2027-01-01 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-01 | #REF!
52 | Al Wathbah | الوثبة - شارع الحفظة | 24.2681 | 54.673 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2026-12-20 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-20 | #REF!
53 | Al Wathbah | الوثبة جنوب | 24.2663 | 54.6578 | Medium | Yes | Developer (Al Dar) | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-12 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Absence of Drainage Network | #REF! | 2026-11-12 | #REF!
54 | Al Wathbah | بني ياس - شارع الجزائر | 24.2758 | 54.6451 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-03-12 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-03-12 | #REF!
55 | Al Wathbah | الوثبة - شارع الرسوخ - بجانب منتزة الوثبة | 24.2458 | 54.7097 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 | 2026-11-18 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-18 | #REF!
56 | Al Wathbah | الوثبة - شارع النهضة | 24.269 | 54.684 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 | 2026-12-07 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-07 | #REF!
57 | Al Wathbah | بني ياس - شارع السهل | 24.2701 | 54.6498 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 | 2026-12-18 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-18 | #REF!
58 | Al Wathbah | الشامخة - بالقرب من الشامخة مول | 24.3999 | 54.7328 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2026-12-19 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-19 | #REF!
59 | Al Wathbah | الشامخة - شارع احمد بن شملان الفلاحي | 24.3937 | 54.7044 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-12-17 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
60 | Al Wathbah | الشامخة - تقاطع شارع الترشيد مع شارع ام الثعالب | 24.411 | 54.747 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-12-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-23 | #REF!
61 | Al Wathbah | الشامخة -شارع محمد بن شبيب المهيري | 24.3954 | 54.6943 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-12-24 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-24 | #REF!
62 | Al Wathbah | الشامخة -شارع الرضى | 24.3759 | 54.6992 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 | 2026-12-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-25 | #REF!
63 | Al Wathbah | الشامخة -شارع العايد | 24.3507 | 54.6832 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-11-22 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-22 | #REF!
64 | Al Wathbah | الشامخة - تقاطع شارع دمية طحنون مع شارع الخزنه | 24.4078 | 54.7358 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-11-16 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-16 | #REF!
65 | Al Wathbah | العدلة - شارع طوي بو صلف | 24.4182 | 54.8663 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-03-12 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-03-12 | #REF!
66 | Al Wathbah | العدلة - شارع طوي اشعب | 24.4114 | 54.8677 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-09-17 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-17 | #REF!
67 | Al Wathbah | عزب العدلة | 24.3853 | 54.9003 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 | 2026-10-02 | N/A | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
68 | Al Wathbah | مدخل المحاجر في العدلة | 24.3869 | 54.9001 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 | 2026-10-02 | N/A | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
69 | Al Wathbah | مزارع العدلة | 24.3831 | 54.895 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 | 2026-10-02 | N/A | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
70 | Al Wathbah | الفاية الصناعية | 24.3082 | 54.8788 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
71 | Island | مواقف سيارات حديقه ام الامارات- المشرف / شارع الند ، غرب 24/2 | 24.4523 | 54.3841 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-10-10 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-10-10 | #REF!
72 | Island | الدوار المؤدي الى نادي ضباط الشرطة. | 24.4054 | 54.4707 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 | 2026-11-28 | Parsons Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-28 | #REF!
73 | Island | المشرف / غرب52 / شارع احمد بن سعيد الرميثي | 24.4359 | 54.3954 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 | 2026-11-28 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-28 | #REF!
74 | Island | تقاطع شارع الشيخ راشد بن سعيد مع تقاطع شارع الشيخة فاطمة بنت مبارك (مقابل مبنى دائرة الاشغال سابقا) | 24.4624 | 54.3763 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Hand over phase | N/A |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
75 | Island | شارع اليزوة – الخالدية مقابل (سبينس- الكورنيش) | 24.4673 | 54.3343 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-05 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-05 | #REF!
76 | Island | شارع الكورنيش (مدخل بوابة قصر الامارات) | 24.4574 | 54.319 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-10 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-10 | #REF!
77 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4639 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Critical Infrastructure | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
78 | Island | مواقف سيارات مستشفي جلوبال كير | 24.4646 | 54.3658 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Implementation Phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
79 | Island | شارع المطار مقابل قصر المنهل | 24.479 | 54.3624 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
80 | Island | مرسي البطين جوار مبني تبريد | 24.4544 | 54.3378 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-19 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-19 | #REF!
81 | Island | بجوار مواقف سيارات المارينا مول | 24.4731 | 54.3201 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-27 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-27 | #REF!
82 | Island | مدارس التكنولوجيا التطبيقيه بمنطقه ال نهيان | 24.4672 | 54.3781 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-19 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-19 | #REF!
83 | Island | شارع الشيخة فاطمة بنت مبارك - مقابل مدرسة الامارات الوطنية | 24.4694 | 54.3851 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
84 | Island | حوض E-25 - قريب من مبنى مبادلة | 24.4618 | 54.3936 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 | 2026-11-16 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-16 | #REF!
85 | Al Shahama | شارع الشيخ زايد بين مجمع جسور ياس و جسر المطار بالاتجاهين | 24.4749 | 54.6365 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-09-11 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
86 | Mussafah | نفق الصناعية الاول باتجاه الداخل | 24.3735 | 54.5219 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
87 | Mussafah | نفق الصناعية الثاني باتجاه الداخل | 24.3465 | 54.5226 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
88 | Al Shahama | مخرج الجسر من الشامخة للفلاح باتجاه دبي | 24.4106 | 54.6815 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-14 | 2026-12-20 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-20 | #REF!
89 | Al Shahama | مخرج جسر سويحان للقادم من جسر كرم الشام باتجاه الشامخة الفلاح | 24.4025 | 54.6703 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-15 | 2026-12-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-23 | #REF!
90 | Zayed | شارع الخليج العربي المخرج المؤدي لشارع العين | 24.3914 | 54.5291 | Very High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-16 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
91 | Zayed | جسر تعليم القيادة بالاتجاهين | 24.347 | 54.5289 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-30 | 2026-07-30 | Implementation Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-30 | #REF!
92 | Zayed | جسر المفرق للقادم من مدينة شخبوط الطبية باتجاه ابوظبي | 24.313 | 54.6036 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 | 2026-09-01 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-01 | #REF!
93 | Al Shahama | شارع محمد بن راشد للقادم من دبي تم تحويل الحركة باتجاه الشامخة | 24.4242 | 54.7646 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 | 2026-11-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-23 | #REF!
94 | Zayed | شارع ابوظبي - العين مدخل شارع الخدمات قبل جسر مزيد مول باتجاه الخارج | 24.3886 | 54.5401 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-01 | 2026-12-28 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-28 | #REF!
95 | Al Shahama | النفق المودي للشهامة للقادم من روضة الريف | 24.5429 | 54.6941 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-21 | #REF!
96 | Al Wathbah | طريق سويحان بعد جسر الفلاح الشامخة باتجاه سويحان | 24.4188 | 54.7506 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | Parsons Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
97 | Zayed | على طول شارع ذياب بن عيسى في مدينة خليفة أ بالاتجاهين | 24.4025 | 54.5725 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 | 2026-07-11 | Implementation Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-11 | #REF!
98 | Zayed | شارع الشيخ مكتوم بن راشد مقابل مستشفى شخبوط باتجاه الغربية | 24.3205 | 54.6125 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-02 | 2026-09-08 | Implementation Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-08 | #REF!
99 | Zayed | طريق ابوظبي العين قبل جسر محوي باتجاه الداخل | 24.3461 | 54.5731 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-10 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-10 | #REF!
100 | Al Wathbah | شارع الشيخ مكتوم بن راشد عن حسر كرم الشام (الشوامخ) باتجاه دبي | 24.3726 | 54.6562 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-27 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-27 | #REF!
101 | Zayed | مدينة خليفة | 24.4406 | 54.6002 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-06 | 2026-07-11 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-11 | #REF!
102 | Zayed | مدينة خليفة | 24.4149 | 54.502 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
103 | Zayed | منطقة ربدان | 24.4112 | 54.5082 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 | 2026-10-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-23 | #REF!
104 | Zayed | منطقة ربدان | 24.4028 | 54.5272 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-10 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-10 | #REF!
105 | Zayed | منطقة ربدان | 24.3493 | 54.6215 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-15 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-15 | #REF!
106 | Zayed | مدينة شخبوط | 24.365 | 54.6482 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 | 2026-09-22 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-22 | #REF!
107 | Zayed | مدينة شخبوط | 24.405 | 54.5193 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 | 2026-10-27 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-27 | #REF!
108 | Zayed | منطقة ربدان | 24.3306 | 54.5368 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-20 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-20 | #REF!
109 | Zayed | مدينة محمد بن زايد | 24.4074 | 54.5026 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-10-30 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-30 | #REF!
110 | Zayed | مدينة زايد | 24.3831 | 54.5948 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 | 2026-08-10 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-08-10 | #REF!
111 | Zayed | مدينة زايد | 24.3796 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-25 | 2026-09-16 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
112 | Zayed | ساس النخل - مدينة زايد | 24.4187 | 54.4962 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-02 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-02 | #REF!
113 | Zayed | ربدان - ساس النخل | 24.3925 | 54.5033 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
114 | Zayed | شارع جبر بن راشد الحلامي - طريق ساس النخل | 24.4237 | 54.5229 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-10 | #REF!
115 | Zayed | مدينة محمد بن زايد | 24.308 | 54.5813 | High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
116 | Zayed | مدينة زايد | 24.3846 | 54.633 | High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
117 | Zayed | مدينة زايد | 24.3542 | 54.6106 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
118 | Zayed | مدينة زايد | 24.3665 | 54.6067 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
119 | Zayed | مدينة محمد بن زايد - شارع خليفة بن خميس الديهلي | 24.3403 | 54.5579 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-13 | [5 empty] | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-13 | #REF!
120 | Zayed | مدينة محمد بن زايد | 24.2968 | 54.5634 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-15 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-15 | #REF!
121 | Zayed | Zayed City | 24.3686 | 54.6005 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-22 | 2026-07-30 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-07-30 | #REF!
122 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.3994 | 54.5932 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-10-03 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-03 | #REF!
123 | Zayed | ربدان - شارع راشد بن جابر الهاملي | 24.4106 | 54.4965 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 | 2026-10-24 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-24 | #REF!
124 | Zayed | مدينة محمد بن زايد | 24.3176 | 54.5332 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-17 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-17 | #REF!
125 | Zayed | مدينة محمد بن زايد - MZ 17 | 24.3896 | 54.6092 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-29 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-29 | #REF!
126 | Zayed | مدينة زايد | 24.379 | 54.5851 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-08-15 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-08-15 | #REF!
127 | Zayed | ربدان | 24.4029 | 54.5038 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-25 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-25 | #REF!
128 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4097 | 54.6368 | High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-08-15 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-08-15 | #REF!
129 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4102 | 54.6436 | High | Yes | ADM Developer | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-08-15 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-08-15 | #REF!
130 | Zayed | مدينة زايد | 24.3704 | 54.6183 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-06 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-06 | #REF!
131 | Zayed | مدينة خليفة | 24.4334 | 54.5769 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 | 2026-07-11 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-07-11 | #REF!
132 | Al Shahama | مدينة الفلاح | 24.4283 | 54.7364 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-10-23 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-23 | #REF!
133 | Al Shahama | الشهامة | 24.5196 | 54.6716 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-26 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-26 | #REF!
134 | Mussafah | مصفح صناعية | 24.326 | 54.5162 | Medium | Yes | مطور | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
135 | Al Shahama | الباهية | 24.6264 | 54.7119 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-24 | Implementation Phase | Yes |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-24 | #REF!
136 | Al Wathbah | طريق رزين | 24.1576 | 54.8458 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
137 | Al Shahama | شارع خليفة بن زايد - الريف | 24.4615 | 54.702 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-09-09 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-09 | #REF!
138 | Al Wathbah | الوثبة جنوب | 24.2609 | 54.673 | Low | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
139 | Al Shahama | مدينة الفلاح | 24.4258 | 54.7426 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-02 | 2026-12-20 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-20 | #REF!
140 | Zayed | مدينة خليفة - دوار طيران الرئاسة | 24.436 | 54.6253 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-07-25 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-25 | #REF!
141 | Mussafah | مصفح صناعية | 24.35 | 54.4939 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
142 | Al Wathbah | طريق الحفار | 24.3855 | 54.8443 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-30 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-30 | #REF!
143 | Al Shahama | الرحبة | 24.5965 | 54.695 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-02 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-02 | #REF!
144 | Al Wathbah | شارع بني ياس بالقرب من محطة البترول | 24.2968 | 54.6285 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-12 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
145 | Al Wathbah | مدينة الرياض | 24.3514 | 54.7125 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-25 | 2026-12-21 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-21 | #REF!
146 | Al Wathbah | الوثبة جنوب | 24.2625 | 54.6587 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-30 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-30 | #REF!
147 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.642 | 54.6575 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-10 | Implementation Phase | Yes |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-10 | #REF!
148 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.6811 | 54.6692 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-18 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-18 | #REF!
149 | Al Shahama | شارع مكتوم بن راشد | 24.6959 | 54.7814 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-26 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-26 | #REF!
150 | Al Shahama | شارع سلطان بن زايد - الريف | 24.4711 | 54.6709 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
151 | Al Shahama | طريق الطف | 24.5973 | 54.9097 | Low | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Network New | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-08 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-12-08 | #REF!
152 | Al Shahama | الصدر- شارع عويد | 24.7557 | 54.7337 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-16 | Permitting Phase | Yes |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-12-16 | #REF!
153 | Al Shahama | خليفة الصناعية - 6 | 24.7631 | 54.7003 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-24 | Permitting Phase | Yes |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-12-24 | #REF!
154 | Al Shahama | مدينة الفلاح | 24.4322 | 54.7315 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-02-03 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-02-03 | #REF!
155 | Al Shahama | مدينة الفلاح | 24.4395 | 54.7408 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-02-03 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-02-03 | #REF!
156 | Al Wathbah | طريق أبو ظبي - العين | 24.3074 | 54.6051 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-18 | 2026-11-26 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-26 | #REF!
157 | Al Shahama | مدينة الفلاح | 24.4613 | 54.7361 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
158 | Al Shahama | شارع مكتوم بن راشد باتجاه السمحة القديمة | 24.6864 | 54.7736 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-24 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-24 | #REF!
159 | Al Shahama | دوار على شارع مكتوم بن راشد | 24.7976 | 54.8637 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-02 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2027-01-02 | #REF!
160 | Al Wathbah | طريق أبو ظبي - العين | 24.2812 | 54.6473 | Medium | Yes | Developer | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Contractor |  |  |  |  | Parsons | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
161 | Island | خلف مدرسه الامام الغزالي- شارع مطر المهيري - غرب 16 | 24.4583 | 54.3414 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
162 | Island | شارع المطلع - شارع الخليج العربي - غرب 52 | 24.437 | 54.3736 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-27 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-10-27 | #REF!
163 | Island | مرسي البطين جوار مرسى اليخوت 1 | 24.4507 | 54.3348 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-04 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-04 | #REF!
164 | Island | شارع خليفة بن شخبوط - غرب 17-1- مواقف سيارات مدرسه هزاع بن زايد الاول | 24.4607 | 54.3575 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-12-31 | #REF!
165 | Island | تقاطع شارع الخليج العربي مع شارع الشيخ هزاع | 24.457 | 54.3552 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-12 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
166 | Island | شارع الشيخ زايد بن سلطان تقاطع شارع ظفير -النفق | 24.445 | 54.4379 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-04 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-04 | #REF!
167 | Island | مناره المقطع - جوار جسر المقطع | 24.4214 | 54.4818 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-12 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
168 | Island | جراند الامارات - شارع هزاع بن زايد تقاطع شارع الشيخ سلطلن بن زايد | 24.4741 | 54.3748 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
169 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع الفلاح | 24.4831 | 54.3758 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
170 | Island | مقابل فندق كرستال ابو ظبي- شرق 14 بالقرب من مركز مدينة زايد للتسوق | 24.4848 | 54.3636 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-12 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
171 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع زايد الأول | 24.4891 | 54.3699 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
172 | Island | شارع الظفرة تقاطع شارع الخليج العربي- جوار دوار مجلس المشرف | 24.425 | 54.4108 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-04 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-04 | #REF!
173 | Island | شارع زايد بن سلطان بين تقاطع شاع زايد الأول وشارع محمد بن بطي ال حامد - مقابل مطعم قصر الهند | 24.4928 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
174 | Island | منطقه المزون | 24.4145 | 54.4314 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-27 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-27 | #REF!
175 | Island | شارع الظفرة بين شارع راشد بن زايد وشارع الخليج العربي | 24.4279 | 54.4108 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-09-16 | #REF!
176 | Island | شارع سلامة بن بطي بين شارع راشد بن زايد وشارع الخليج العربي | 24.4339 | 54.4033 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-20 | #REF!
177 | Island | مدخل منطقة روضة ابوظبي من شارع الشيخ راشد بن سعيد- قرب مطار البطين | 24.417 | 54.47 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-20 | #REF!
178 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع هزاع | 24.4704 | 54.3701 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
179 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع الشيخ محمد بن خليفة- مقابل محمصه الامراء | 24.459 | 54.3814 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
180 | Island | منطقة المعمورة - بجانب مبنى دائرة البلديات والنقل | 24.4617 | 54.3936 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 | 2026-11-14 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-14 | #REF!
181 | Island | جزيره الجبيل - شارع خليفه بن زايد | 24.5406 | 54.4836 | Low | Yes | مطور | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-11-20 | #REF!
182 | Island | دوار شارع الحريه - جزيره الريم | 24.482 | 54.4047 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-28 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-28 | #REF!
183 | Island | جزيره السعديات - جوار مسجد الحمد | 24.5385 | 54.4396 | Medium | Yes | مطور | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Contractor |  |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-12-31 | #REF!
184 | Island | شارع الشيخ راشد بن سعيد - جسر الجوازات | 24.4444 | 54.3952 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
185 | Island | شارع سلطان بن زايد من تقاطغ شارع سلامة بن بطي الى شارع الظفرة- مقابل مطعم اليمن السعيد شارع المرور | 24.4397 | 54.4118 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-28 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-28 | #REF!
186 | Island | مدخل قصر البحر | 24.4724 | 54.3927 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-29 | 2026-12-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-23 | #REF!
187 | Island | مينا زايد تابع للمطور | 24.5171 | 54.3729 | Medium | Yes | مطور | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | TRUE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
188 | Island | الشارع من أرض المعارض لدوار الجوية- شارع السفارات | 24.4235 | 54.4444 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-25 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-25 | #REF!
189 | Mussafah | نفق المصفح الثاني باتجاه الخارج | 24.3473 | 54.5254 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Critical Infrastructure |  | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
190 | Al Shahama | الشهامة الجديدة | 24.5431 | 54.6917 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-21 | #REF!
191 | Al Shahama | نفق ياس | 24.461 | 54.6111 | High | Yes | Developer (ICT) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-26 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2027-01-26 | #REF!
192 | Zayed | طريق الخليج العربي مقابل ملعب الكريكت | 24.3924 | 54.5486 | Very High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-16 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
193 | Zayed | قبل الجسر المؤدي لمحمد بن زايد | 24.3772 | 54.551 | High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-20 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-10-20 | #REF!
194 | Al Wathbah | بحيرة بني ياس | 24.3032 | 54.6275 | Very High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-12-28 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-28 | #REF!
195 | Al Wathbah | شارع الزود - بني ياس | 24.3094 | 54.6156 | High | Yes | Private | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 | 2026-12-30 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-30 | #REF!
196 | Zayed | قبل الجسر المؤدي للمفرق الصناعية | 24.2921 | 54.5592 | Very High | Yes | Private | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-01 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-01 | #REF!
197 | Zayed | شارع النصيلة- مدينة محمد بن زايد | 24.3244 | 54.5305 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-29 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-29 | #REF!
198 | Zayed | شارع النصيلة- مدينة محمد بن زايد - قبل الجسر | 24.3263 | 54.5841 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-01 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-01 | #REF!
199 | Zayed | الجسر المؤدي الى المصفح - طريق أبو ظبي - العين | 24.3278 | 54.5859 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-10-08 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-08 | #REF!
200 | Al Wathbah | الشوامخ - تقاطع شارع طوي القامة مع شارع المورد | 24.3598 | 54.6677 | High | Yes | Mainland | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-26 | 2026-11-11 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-11-11 | #REF!
201 | Zayed | مدينة خليفة | 24.4244 | 54.5449 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 | 2026-07-10 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-10 | #REF!
202 | Zayed | مدينة خليفة | 24.3958 | 54.555 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 | 2026-07-11 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-11 | #REF!
203 | Zayed | مدينة خليفة | 24.4297 | 54.5634 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 | 2026-07-10 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-07-10 | #REF!
204 | Zayed | مدينة خليفة | 24.4264 | 54.535 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 | 2026-10-05 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-05 | #REF!
205 | Zayed | مدينة خليفة - طريق المطار | 24.4482 | 54.6131 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 | 2026-10-22 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-22 | #REF!
206 | Zayed | مدينة خليفة | 24.4467 | 54.6181 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-25 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-25 | #REF!
207 | Island | جسر دلما | 24.4668 | 54.3829 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 | 2026-12-15 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
208 | Mussafah | مدخل قاعدة الظفرة الجوية | 24.2821 | 54.5414 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
209 | Mussafah | مصفح صناعية - قطاع 3 | 24.3826 | 54.5106 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 180576 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
210 | Mussafah | مصفح صناعية - قطاع M19 | 24.3674 | 54.4811 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 180576 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
211 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3578 | 54.4721 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
212 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3567 | 54.4724 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
213 | Mussafah | مصفح صناعية - قطاع M34 | 24.3463 | 54.5125 | High | No | N/A | Yes | The network needs an upgrade |  | 4 | 20736 | 77760 | 98496 | 5 | 1 | 3 | 1 | 2160 | 4320 | 864 | 7344 | 88128 | 330480 | 418608 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
214 | Mussafah | مصفح صناعية | 24.3284 | 54.5262 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Critical Infrastructure | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-16 | #REF!
215 | Mussafah | مصفح صناعية - ICAD I | 24.3218 | 54.5048 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
216 | Mussafah | مصفح صناعية - ICAD I | 24.3268 | 54.4839 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
217 | Mussafah | مصفح صناعية - قطاع M42 | 24.3362 | 54.4781 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
218 | Mussafah | مصفح صناعية - قطاع M43 | 24.3438 | 54.4807 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
219 | Mussafah | مصفح صناعية - قطاع M32_02 | 24.3575 | 54.5142 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
220 | Mussafah | مصفح صناعية - قطاع M24 | 24.3607 | 54.5204 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
221 | Zayed | مدينة محمد بن زايد - Z9_01 | 24.3741 | 54.5364 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-29 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-29 | #REF!
222 | Zayed | مدينة محمد بن زايد - Z1 | 24.3733 | 54.5395 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
223 | Zayed | مدينة محمد بن زايد - Z9 | 24.36 | 54.5372 | High | Yes | Private area | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-10 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-10 | #REF!
224 | Zayed | مدينة محمد بن زايد - Z5 | 24.353 | 54.5554 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-06 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-10-06 | #REF!
225 | Zayed | مدينة محمد بن زايد - Z8 | 24.3514 | 54.5527 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [6 empty] | 2026-09-22 |  | Contractor | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
226 | Zayed | مدينة محمد بن زايد - Z9 | 24.3474 | 54.538 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-22 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-22 | #REF!
227 | Zayed | مدينة محمد بن زايد - ME9 | 24.3451 | 54.5352 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
228 | Zayed | مدينة محمد بن زايد - ME9 | 24.3385 | 54.5324 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
229 | Zayed | مدينة محمد بن زايد - ME10 | 24.3359 | 54.5357 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
230 | Zayed | مدينة محمد بن زايد - ME11 | 24.3291 | 54.5384 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
231 | Zayed | مدينة محمد بن زايد - ME11 | 24.3268 | 54.5389 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
232 | Zayed | مدينة محمد بن زايد - Z20 | 24.3157 | 54.5398 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
233 | Zayed | مدينة محمد بن زايد - Z24 | 24.3153 | 54.5508 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
234 | Zayed | مدينة محمد بن زايد - Z23 | 24.3168 | 54.5556 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
235 | Zayed | مدينة محمد بن زايد - Z30 | 24.2966 | 54.5551 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
236 | Zayed | مدينة محمد بن زايد - Z30 | 24.2997 | 54.5587 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
237 | Zayed | مدينة محمد بن زايد - Z30 | 24.3017 | 54.5645 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
238 | Zayed | مدينة محمد بن زايد - Z30 | 24.295 | 54.5672 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
239 | Zayed | مدينة محمد بن زايد - Z31 | 24.3018 | 54.5744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
240 | Zayed | مدينة محمد بن زايد - Z34 | 24.3017 | 54.5839 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
241 | Zayed | مدينة محمد بن زايد - Z34 | 24.3021 | 54.5813 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
242 | Zayed | مدينة محمد بن زايد - Z34 | 24.304 | 54.5828 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
243 | Zayed | مدينة محمد بن زايد - Z34 | 24.3022 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
244 | Zayed | مدينة محمد بن زايد - Z34 | 24.3047 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
245 | Zayed | مدينة محمد بن زايد - Z35 | 24.3076 | 54.5916 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
246 | Zayed | مدينة محمد بن زايد - Z35 | 24.3161 | 54.5864 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
247 | Zayed | مدينة محمد بن زايد - Z33 | 24.3227 | 54.577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
248 | Zayed | مدينة محمد بن زايد - Z33 | 24.3192 | 54.5782 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
249 | Zayed | مدينة محمد بن زايد - Z33 | 24.323 | 54.5754 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
250 | Zayed | مدينة محمد بن زايد - Z22 | 24.3223 | 54.5688 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
251 | Zayed | مدينة محمد بن زايد - Z22 | 24.3222 | 54.5645 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
252 | Zayed | مدينة محمد بن زايد - Z22 | 24.3241 | 54.5623 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
253 | Zayed | مدينة محمد بن زايد - Z21 | 24.3232 | 54.5577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
254 | Zayed | مدينة محمد بن زايد - Z15 | 24.3334 | 54.5579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
255 | Zayed | مدينة محمد بن زايد - Z13 | 24.3437 | 54.5546 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
256 | Zayed | مدينة محمد بن زايد - Z13_01 | 24.3422 | 54.5636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
257 | Zayed | مدينة محمد بن زايد - Z36 | 24.3356 | 54.5782 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
258 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2868 | 54.5897 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
259 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2818 | 54.5849 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
260 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.256 | 54.6342 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
261 | Zayed | ربدان - RB1 | 24.4179 | 54.4945 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
262 | Zayed | ربدان - RB2 | 24.4149 | 54.4926 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
263 | Zayed | ربدان - RB7 | 24.407 | 54.515 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
264 | Zayed | ربدان - RB14 | 24.4024 | 54.4879 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
265 | Zayed | ربدان - RB28 | 24.3984 | 54.5024 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | [5 empty] | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
266 | Zayed | ربدان - RB28 | 24.3947 | 54.5009 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
267 | Zayed | المخرج الى طريق دبي - من طريق أبو ظبي العين | 24.4142 | 54.5066 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-25 | #REF!
268 | Zayed | المخرج الى شارع الشيخ زايد - ساس النخل | 24.4193 | 54.5136 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-03 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-03 | #REF!
269 | Zayed | SW17_مدينة خليفة - 01 | 24.4116 | 54.5139 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
270 | Zayed | مدينة خليفة - SW17 - وطني | 24.4163 | 54.5465 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
271 | Zayed | مدينة خليفة - SW17 - وطني | 24.4148 | 54.5432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
272 | Zayed | مدينة خليفة - SW17 - وطني | 24.4144 | 54.5405 | High | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
273 | Zayed | مدينة خليفة | 24.4145 | 54.5393 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-13 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-10-13 | #REF!
274 | Zayed | مدينة خليفة | 24.4144 | 54.5411 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
275 | Zayed | مدينة خليفة - SW13 | 24.4132 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
276 | Zayed | مدينة خليفة - SW2 | 24.4197 | 54.5586 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
277 | Zayed | مدينة خليفة - SW3 | 24.4147 | 54.5641 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
278 | Zayed | مدينة خليفة - SW4 | 24.41 | 54.5645 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
279 | Zayed | مدينة خليفة - شارع المطار بالاتجاه لأبو ظبي | 24.3978 | 54.5738 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2026-10-17 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-17 | #REF!
280 | Zayed | مدينة خليفة - SE3 | 24.4195 | 54.5683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
281 | Zayed | مدينة خليفة - SE13 | 24.4184 | 54.5832 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
282 | Zayed | مدينة خليفة - SE24 | 24.414 | 54.5885 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
283 | Zayed | مدينة خليفة - SE26 | 24.4092 | 54.5924 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
284 | Zayed | مدينة خليفة - SE6 | 24.4016 | 54.5785 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
285 | Zayed | مدينة خليفة - SE16 | 24.4027 | 54.5843 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
286 | Zayed | مدينة خليفة - SE26 | 24.4045 | 54.592 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
287 | Zayed | مدينة خليفة - SE36 | 24.407 | 54.6048 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
288 | Zayed | مدينة خليفة - SE38 | 24.4124 | 54.6033 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
289 | Zayed | مدينة خليفة - SE35 | 24.4158 | 54.6016 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
290 | Zayed | مدينة خليفة - SE44 | 24.43 | 54.5817 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
291 | Zayed | مدينة خليفة - SE47 | 24.4365 | 54.5869 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
292 | Zayed | مدينة خليفة - SE47 | 24.44 | 54.5905 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
293 | Zayed | مدينة خليفة - SE40 | 24.4264 | 54.6002 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
294 | Zayed | مدينة خليفة - الراحة - RBW13 | 24.4343 | 54.5597 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
295 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4384 | 54.5776 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-14 | 2026-10-26 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-26 | #REF!
296 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4427 | 54.5933 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-21 | 2026-10-31 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-31 | #REF!
297 | Zayed | مدينة شخبوط - طريق سويحان باتجاه الى طريق المفرق | 24.4094 | 54.6638 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | D |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-13 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-13 | #REF!
298 | Zayed | مدينة زايد - MZ6 | 24.3781 | 54.5951 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
299 | Zayed | مدينة زايد - MZ6 | 24.3826 | 54.6024 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
300 | Zayed | مدينة زايد - MZ7 | 24.3867 | 54.6059 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
301 | Zayed | مدينة زايد - MZ7 | 24.3819 | 54.6087 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
302 | Zayed | مدينة زايد - MZ10 | 24.3691 | 54.6046 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
303 | Zayed | مدينة زايد - MZ1 | 24.3657 | 54.6032 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
304 | Zayed | مدينة زايد - MZ1 | 24.3604 | 54.6 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
305 | Zayed | مدينة زايد - MZ8 | 24.3892 | 54.6189 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
306 | Zayed | مدينة زايد - MZ9 | 24.3922 | 54.6221 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
307 | Zayed | مدينة شخبوط - MSH7 | 24.349 | 54.6085 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
308 | Zayed | مدينة شخبوط - MSH7 | 24.3519 | 54.611 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
309 | Zayed | مدينة شخبوط - MSH7 | 24.348 | 54.6131 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
310 | Zayed | مدينة شخبوط - MSH5 | 24.35 | 54.6163 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
311 | Zayed | مدينة شخبوط - MSH5 | 24.3503 | 54.6186 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
312 | Zayed | مدينة شخبوط - MSH5 | 24.3443 | 54.6165 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
313 | Zayed | مدينة شخبوط - MSH3 | 24.3453 | 54.6214 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
314 | Zayed | مدينة شخبوط - MSH1 | 24.3373 | 54.6237 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
315 | Zayed | مدينة شخبوط - MSH2 | 24.3423 | 54.6272 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
316 | Zayed | مدينة شخبوط - MSH1 | 24.3436 | 54.6316 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
317 | Zayed | مدينة شخبوط - MSH15 | 24.3583 | 54.637 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
318 | Zayed | مدينة شخبوط - MSH14 | 24.3643 | 54.6345 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
319 | Zayed | مدينة شخبوط - MSH17 | 24.3697 | 54.6488 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
320 | Zayed | مدينة شخبوط - MSH19 | 24.3727 | 54.6467 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
321 | Zayed | مدينة شخبوط - MSH19 | 24.3721 | 54.6428 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
322 | Zayed | مدينة شخبوط - MSH23 | 24.3774 | 54.6306 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
323 | Zayed | مدينة شخبوط - MSH20 | 24.3756 | 54.6454 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
324 | Zayed | مدينة شخبوط - MSH24 | 24.388 | 54.6396 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
325 | Al Wathbah | بني ياس - EB1_03 | 24.3174 | 54.6355 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
326 | Al Wathbah | بني ياس - EB6_01 | 24.3068 | 54.6446 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
327 | Al Wathbah | بني ياس - EB7_B | 24.2999 | 54.6381 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
328 | Al Wathbah | بني ياس -EB10_A | 24.293 | 54.6517 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
329 | Al Wathbah | بني ياس -WB3_A | 24.2888 | 54.6342 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
330 | Al Wathbah | بني ياس -EB11_01 | 24.3089 | 54.6456 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
331 | Al Wathbah | بني ياس -EB1_04 | 24.3256 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
332 | Al Wathbah | الشوامخ - SHM10 | 24.3431 | 54.6493 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
333 | Al Wathbah | الشوامخ - SHM9 | 24.3498 | 54.6551 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
334 | Al Wathbah | الشوامخ - SHM9 | 24.3535 | 54.6619 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
335 | Al Wathbah | الشوامخ - SHM3 | 24.362 | 54.6552 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
336 | Al Wathbah | الشوامخ - SHM2 | 24.3681 | 54.6603 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
337 | Al Wathbah | الشوامخ - SHM1 | 24.3771 | 54.6636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
338 | Al Wathbah | الشامخة - SH10 | 24.3969 | 54.704 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
339 | Al Wathbah | الشامخة - SH11 | 24.3834 | 54.7167 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
340 | Al Wathbah | الشامخة - SH14 | 24.3692 | 54.7154 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
341 | Al Wathbah | مدينة الرياض - RD26 | 24.3287 | 54.7804 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 3 | 0 | 0 | 6480 | 0 | 0 | 6480 | 77760 | 291600 | 369360 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
342 | Al Wathbah | مدينة الرياض - RD32 | 24.3325 | 54.7441 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
343 | Al Wathbah | مدينة الرياض - RD11 | 24.3562 | 54.7382 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
344 | Al Wathbah | مدينة الرياض - RD7 | 24.3769 | 54.7572 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
345 | Al Shahama | الفلاح - 1E | 24.433 | 54.7399 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
346 | Al Shahama | الفلاح - 1E | 24.431 | 54.7432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
347 | Al Shahama | الفلاح - 1E | 24.4412 | 54.7333 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
348 | Al Shahama | الفلاح - 1D | 24.4464 | 54.7381 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
349 | Al Shahama | الفلاح - 1C | 24.4577 | 54.7377 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
350 | Al Shahama | الفلاح - 1B | 24.4563 | 54.7178 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
351 | Al Shahama | جزيرة ياس - YN3 | 24.5108 | 54.6005 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
352 | Al Shahama | جزيرة ياس - YN3 | 24.504 | 54.596 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
353 | Al Shahama | جزيرة ياس - YN7 | 24.4977 | 54.6225 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
354 | Al Shahama | الباهية - Al Shahamah Old | 24.5421 | 54.6796 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
355 | Al Shahama | الباهية - Al Bahyah New | 24.546 | 54.6293 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
356 | Al Shahama | الباهية - Al Bahyah New | 24.5467 | 54.6367 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
357 | Al Shahama | الباهية - Al Shahamah Old | 24.5584 | 54.6798 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
358 | Al Shahama | الرحبة - Rahbah_A | 24.5655 | 54.6872 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
359 | Al Shahama | الرحبة - Rahbah_A | 24.5663 | 54.6859 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
360 | Al Shahama | الرحبة - Rahbah_A | 24.5695 | 54.6862 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
361 | Al Shahama | الرحبة - Rahbah_C | 24.5769 | 54.6871 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
362 | Al Shahama | الرحبة - Rahbah_G | 24.6021 | 54.6998 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
363 | Al Shahama | الرحبة - السمحة | 24.6241 | 54.7104 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
364 | Al Shahama | السمحة - Al Samhah East | 24.6542 | 54.7605 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
365 | Al Shahama | السمحة - Al Samhah East | 24.661 | 54.7647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
366 | Al Shahama | السمحة -Al Samhah East Old | 24.6718 | 54.7741 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
367 | Al Shahama | السمحة -Al Samhah East Old | 24.6781 | 54.7753 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
368 | Al Shahama | السمحة -Samhah_V | 24.6712 | 54.7479 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
369 | Al Shahama | السمحة -Samhah_T | 24.6716 | 54.7581 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
370 | Al Shahama | السمحة -Al Samhah West Old_ | 24.6859 | 54.7676 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
371 | Al Wathbah | Qasr Al Wathbah South | 24.1767 | 54.7566 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
372 | Al Wathbah | Al Dhafrah East | 24.2383 | 54.6337 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
373 | Al Wathbah | Al Nahdah Al Askariah | 24.2607 | 54.7083 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
374 | Al Wathbah | Al Nahdah Al Askariah | 24.2634 | 54.7013 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
375 | Al Wathbah | Al Nahdah Al Askariah | 24.2677 | 54.6937 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
376 | Island | جوار نيشن تاور | 24.4633 | 54.3288 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
377 | Island | شارع الاواصر | 24.4656 | 54.3357 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
378 | Island | شارع الاواصر | 24.4661 | 54.3366 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
379 | Island | ابراج الساحل | 24.4664 | 54.335 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
380 | Island | اسبنس الكورنيش | 24.4659 | 54.3345 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
381 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4696 | 54.3373 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
382 | Island | خلف مدرسه سابس العالميه | 24.4628 | 54.3411 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
383 | Island | خلف مدرسه سابس العالميه | 24.4626 | 54.3407 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
384 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4695 | 54.3377 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
385 | Island | كليه ابو ظبي للاداره | 24.4848 | 54.3536 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
386 | Island | شارع المطار مدخل قصر الحصن | 24.4835 | 54.358 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
387 | Island | صيدليه الملا منطقه الخالديه | 24.4792 | 54.3579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
388 | Island | مدينه خليفه الطبيه | 24.4705 | 54.364 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 0 | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
389 | Island | مجلس المنهل | 24.4691 | 54.3587 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
390 | Island | مجمع الكرامه | 24.4641 | 54.3728 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
391 | Island | خلف فندق فلايجيو شارع المطار | 24.4653 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
392 | Island | خلف فندق فلايجيو شارع المطار | 24.4645 | 54.3745 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
393 | Island | شارع الشيخه فاطمه اتجاه البطين تقاطع شارع المطار | 24.4636 | 54.3777 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
394 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4646 | 54.3757 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
395 | Island | تقاطع الشيخه فاطمه مع شارع الكرامه | 24.4597 | 54.3733 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
396 | Island | صيدليه المركز الامريكي جوار مجمع ليوا | 24.4575 | 54.371 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
397 | Island | خلف المركز الامريكي | 24.4551 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
398 | Island | خلف مركز القاضي الطبي | 24.4421 | 54.3678 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
399 | Island | دوار الفروسيه 1 | 24.4425 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
400 | Island | جوار مجمع حدائق المشرف | 24.4431 | 54.3734 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
401 | Island | دوار الفروسيه 2 | 24.4465 | 54.3757 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
402 | Island | اسفل جسر شارع الخليج العربي | 24.4351 | 54.3768 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
403 | Island | جوار مبني الهويه والجنسيه 1 | 24.4473 | 54.3897 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
404 | Island | جوار مبني الهويه والجنسيه 2 | 24.4477 | 54.3886 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
405 | Island | مسجد خالد بن الوليد منطقه البطين | 24.4514 | 54.3551 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
406 | Island | مرسي البطين جوار مرسى اليخوت 2 | 24.4514 | 54.3368 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
407 | Island | حديقه ام الامارات 2 | 24.4544 | 54.3818 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
408 | Island | جسر شارع الشيخ خليفه بن زايد اتجاه السعديات | 24.5151 | 54.3925 | Medium | Yes | مطور | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
409 | Island | مينا زايد تابع للمطور | 24.5322 | 54.3661 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
410 | Island | مينا زايد تابع للمطور | 24.5221 | 54.3682 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
411 | Island | مينا زايد تابع للمطور | 24.5136 | 54.3685 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
412 | Island | فندق هلا ارجان- الزاهية | 24.502 | 54.377 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
413 | Island | مواقف سيارات خلف فندق نهال | 24.4982 | 54.3727 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
414 | Island | مستشفي الكورنيش | 24.5013 | 54.3696 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
415 | Island | خلف المركز الاجتماعي الهندي | 24.5088 | 54.3794 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
416 | Island | مواقف سيارات سوق السجاد | 24.5116 | 54.3834 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
417 | Island | مواقف سيارات سوق السجاد | 24.5121 | 54.3825 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
418 | Island | شارع خليفه بن زايد تقاطع شارع المينا | 24.5091 | 54.3824 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
419 | Island | جسر الماريا شارع حمدان بن محمد | 24.5021 | 54.3813 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
420 | Island | شارع السلام قبل تقاطع شارع حمدان | 24.4956 | 54.374 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
421 | Island | جوار بنك ابو ظبي الاول - شارع السلام | 24.4919 | 54.378 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
422 | Island | شارع الريم جوار مطعم جاد | 24.4902 | 54.3807 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
423 | Island | جوار فندق جنه شارع الفلاح | 24.489 | 54.3831 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
424 | Island | جوار مجمع طاقه 1 | 24.4846 | 54.3788 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
425 | Island | جوار مجمع طاقه 2 | 24.4835 | 54.3779 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
426 | Island | مواقف شارع السلام محال تاجير السيارات 1 | 24.486 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
427 | Island | مواقف شارع السلام محال تاجير السيارات 2 | 24.485 | 54.3821 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
428 | Island | مواقف حافلات مدرسه الشيخه فاطمه 1 | 24.4818 | 54.3799 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
429 | Island | مواقف حافلات مدرسه الشيخه فاطمه 2 | 24.4823 | 54.3796 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
430 | Island | جوار السفاره السريلانكيه | 24.4815 | 54.3848 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
431 | Island | خلف مسجد حمد خليفه الخلفان | 24.4805 | 54.3823 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
432 | Island | مواقف مستشفي برجيل شارع الدفاع | 24.4785 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
433 | Island | جوار مدرسه الايمان الخاصه | 24.4892 | 54.3671 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
434 | Island | جوار مسجد عبد الرحيم خوري | 24.4859 | 54.3712 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
435 | Island | شارع المرور مقابل سوق الذهب | 24.4847 | 54.3667 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
436 | Island | شارع المرور مقابل سوق الذهب | 24.4859 | 54.366 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
437 | Island | مواقف سوق الذهب | 24.4843 | 54.3644 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
438 | Island | تقاطع شارع المرور مع شارع الفلاح | 24.4787 | 54.3697 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
439 | Island | فندق النخيل شارع المرور | 24.4775 | 54.3715 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
440 | Island | خلف جراند الامارات شارع المرور | 24.4731 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
441 | Island | جوار كنتاكي شارع المطار | 24.4733 | 54.3683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
442 | Island | فندق ماريوت شارع المطار | 24.4704 | 54.3701 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
443 | Island | منطقه ال نهيان " محلات الشوكلاته " | 24.4726 | 54.3803 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
444 | Island | مجمع الكرامه | 24.4634 | 54.372 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
445 | Island | مبني تدوير " الاشغال سابقا " | 24.4613 | 54.3749 | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
446 | Island | شارع ماء سلوان مقابل صحه مستشفي خليفه | 24.4674 | 54.3689 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
447 | Island | مجمع الكرامه | 24.4625 | 54.3709 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
448 | Island | شارع الكرامه | 24.4613 | 54.3699 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
449 | Island | روضه ابو ظبي للاطفال | 24.4634 | 54.3673 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
450 | Island | مطعم المزراب الشعبي | 24.4543 | 54.3863 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
451 | Island | نادي الجزيره | 24.4513 | 54.3925 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
452 | Island | خلف جامعه خليفه | 24.4449 | 54.3989 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
453 | Island | مسجد حمزه بن عبد المطلب | 24.4437 | 54.4062 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
454 | Island | حديقه قاف " حديقه الملك حمد " | 24.4357 | 54.4114 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
455 | Island | خياط البيت السعيد - شارع المرور | 24.4379 | 54.4136 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
456 | Island | مركز فحص المركبات - ادنوك شارع المرور | 24.4355 | 54.4168 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
457 | Island | كليه الشرطه | 24.4378 | 54.4193 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
458 | Island | خلف مسجد سيف بن حارب المنصوري | 24.4389 | 54.4185 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
459 | Island | الدفاع المدني - القبيسات | 24.425 | 54.4186 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
460 | Island | مسجد السيد يوسف الهاشمي | 24.4245 | 54.4151 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintenance | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Hand over phase | N/A |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
461 | Island | شارع سلامه بنت بطيء | 24.4333 | 54.4034 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
462 | Island | شارع المدرسه | 24.4315 | 54.4094 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
463 | Island | مقابل اكادميه ابو ظبي للسباحه | 24.4267 | 54.4132 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
464 | Island | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | 24.4251 | 54.4099 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
465 | Island | شرق 43 | 24.4397 | 54.4297 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
466 | Island | جوار مسجد جبريل | 24.4254 | 54.4254 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
467 | Island | شارع الخرطوم - مدرسه الريم | 24.4346 | 54.4317 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
468 | Island | منطقه السعاده 1 | 24.4361 | 54.4371 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
469 | Island | منطقه السعاده 2 | 24.4413 | 54.4351 | Medium | No | N/A | No | Absense of Drainage Network |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 0 | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
470 | Island | مجمع اوريكس | 24.4402 | 54.4476 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
471 | Island | محطه ادنوك - جوار مجمع الظبي | 24.4402 | 54.4518 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
472 | Island | مدخل قصر المينا مع شارع المروج | 24.4378 | 54.4591 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
473 | Island | دوار مدينه زايد الرياضيه | 24.4192 | 54.4567 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
474 | Island | ملاعب منطقه الروضه " غرب مطار البطين " | 24.4203 | 54.4617 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
475 | Island | منطقه الروضه " الابراج السكنيه " | 24.4178 | 54.4647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
476 | Island | حديقه نادي الضباط | 24.404 | 54.475 | Medium | No | N/A | No | Absense of Drainage Network |  | 4 | 20736 | 77760 | 98496 | 5 | 0 | 0 | 5 | 0 | 0 | 4320 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
477 | Island | اكادميه الرياضه النسائيه | 24.4018 | 54.4696 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
478 | Island | مجمع هيلز ابو ظبي | 24.4034 | 54.4648 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
479 | Island | حديقه نادي الضباط | 24.4036 | 54.4817 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
480 | Island | مواقف واحه الكرامه | 24.4089 | 54.4797 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
481 | Island | مقابل دائره القضاء - شارع النوفل | 24.4186 | 54.4467 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
482 | Mussafah | طريق E-11 باتجاه الغويفات | 24.2512 | 54.4773 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | [5 empty] | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
483 | Al Wathbah | طريق E30 باتجاه العزب | 24.2094 | 54.8215 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
484 | Al Shahama | طريق E16 | 24.5742 | 55.176 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
485 | Al Wathbah | شارع الخير | 24.2982 | 54.7121 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
486 | Zayed | شارع E30- جسر المصفح - الفلتر باتجاه خليفة | 24.3875 | 54.5247 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-07-30 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-07-30 | #REF!
487 | Zayed | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | 24.3916 | 54.5423 | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 60000 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
488 | Zayed | دوار كرم الشام - مدينة شخبوط | 24.3716 | 54.6513 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
489 | Zayed | شارع مطر بن خادم المهيري- مدينة شخبوط | 24.3715 | 54.6481 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
490 | Al Shahama | شارع E12- من مجمع ياس باتجاه دبي | 24.4871 | 54.6344 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-26 | 2026-12-14 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-14 | #REF!
491 | Mussafah | منطقة الأريام | 24.1659 | 54.3382 | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
492 | Mussafah | ايكاد 2 | 24.303228 | 54.4499 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
493 | Al Wathbah | مدينة الرياض - شارع الخير | 24.2994 | 54.677 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 | 2026-12-30 | 2D modelling |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-30 | #REF!
494 | Mussafah | منطقة النوف | 24.2478 | 54.1654 | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
495 | Al Wathbah | ظهارة الطيب - أبو ظبي | 24.2105 | 54.8397 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
496 | Al Wathbah | مدينة الرياض - حوض 144 | 24.2881 | 54.6911 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
497 | Mussafah | منطقة الأريام | 24.2167 | 54.4065 | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
498 | Al Wathbah | عزب دهان - الوافية | 24.209 | 54.9138 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
499 | Al Shahama | منطقة العجبان | 24.5997 | 54.8401 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
500 | Mussafah | ايكاد 3 | 24.3108 | 54.5006 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
501 | Al Wathbah | عزب دهان | 24.195870 | 54.9685 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
502 | Al Shahama | مزارع عجبان - شارع عويد | 24.676 | 54.8319 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
503 | Mussafah | ايكاد 3 | 24.2996 | 54.4905 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
504 | Al Wathbah | منطقة طريق الحفار | 24.254018 | 54.8251 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
505 | Mussafah | ايكاد 3 | 24.299677 | 54.4849 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
506 | Al Wathbah | أكادمية الدفاع المدني - طريق الحفار | 24.284 | 54.8305 | Low | Yes | Private Area | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [6 empty] | Contractor | [5 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
Formulas:
IDD_Completion_Date2 = IF([Hotspot_ID]="","",IF(ISNUMBER([Planned_IDD_Completion_Date]),[Planned_IDD_Completion_Date],IF(TRIM(#REF!&"")<>"",IF(ISNUMBER(IFERROR(INDEX(#REF!,MATCH(#REF!,#REF!,0)),"")),IFERROR(INDEX(#REF!,MATCH(#REF!,#REF!,0)),""),"CLIENT INPUT REQUIRED"),"CLIENT INPUT REQUIRED")))

## ADM Rate Assumptions - Hourly (hidden)
Average Rental Rates Assumptions
Resources | 12" Pump | 8" Pump | 6'' Pump | Ele Pump &Gen. | Labour | Tankers
Duty rate/Hr | 90 | 60 | 36 | 40 | 18 | 250
Standby rate/Hr | 45 | 30 | 18 | 20 | 9 | 125

## ADM List (hidden)
[11 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [23 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan | [23 empty] | PROJECTS REGISTER (paste from IDD file > 'AD_Projects Register')
Hotspot_ID | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Check | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Check2 | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Covered by Construction? | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD_Design_Category | IDD_Intervention_Type | IDD_Owner | IDD_Mobilization_Date | IDD_Completion_Date_Raw | CPDS_CIP_ID | IDD_Status | Dup_Check | Criticality_Tier | Is_Highly_Critical | Is_Critical | Is_Private_Developer | Root_Cause_Category | IDD_Covered | Reg_Approved_Budget | Reg_Covered_Hotspots | IDD_Budget_Per_Hotspot | Muni_Emergency_Budget | ADM_Pond_Work_Flag | IDD_Pond_Work_Flag | ADM_IDD_Pond_Overlap_Flag | Pond_Overlap_Note | IDD_Completion_Date | IDD_Timeline_Status | CIP_ID | CPDS_ID | Project_Name | Classification | Start_Date | Resolution_End_Date | Forecasted_End_Date | Approved_Budget_AED | Covered_Hotspots | Additional_Budget_AED | Additional_Hotspots | Budget_Per_Hotspot
209 | Mussafah | مصفح صناعية - قطاع 3 | 24.3826 | 54.5106 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 0 | 180576 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 3 | 180576 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 229824 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
210 | Mussafah | مصفح صناعية - قطاع M19 | 24.3674 | 54.4811 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 0 | 180576 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 2 | 49248 | 3 | 180576 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 229824 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
211 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3578 | 54.4721 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
212 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3567 | 54.4724 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
213 | Mussafah | مصفح صناعية - قطاع M34 | 24.3463 | 54.5125 | High | No | N/A | Yes | The network needs an upgrade |  | 4 | 20736 | 77760 | 0 | 98496 | 5 | 1 | 3 | 1 | 2160 | 4320 | 864 | 7344 | 88128 | 330480 | 0 | 418608 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 4 | 98496 | 5 | 418608 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 517104 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
215 | Mussafah | مصفح صناعية - ICAD I | 24.3218 | 54.5048 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
216 | Mussafah | مصفح صناعية - ICAD I | 24.3268 | 54.4839 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
217 | Mussafah | مصفح صناعية - قطاع M42 | 24.3362 | 54.4781 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
218 | Mussafah | مصفح صناعية - قطاع M43 | 24.3438 | 54.4807 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
219 | Mussafah | مصفح صناعية - قطاع M32_02 | 24.3575 | 54.5142 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
220 | Mussafah | مصفح صناعية - قطاع M24 | 24.3607 | 54.5204 | Low | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
225 | Zayed | مدينة محمد بن زايد - Z8 | 24.3514 | 54.5527 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
227 | Zayed | مدينة محمد بن زايد - ME9 | 24.3451 | 54.5352 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  | 2 |  | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 0 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 164160 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 188784 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
228 | Zayed | مدينة محمد بن زايد - ME9 | 24.3385 | 54.5324 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
229 | Zayed | مدينة محمد بن زايد - ME10 | 24.3359 | 54.5357 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 4 |  |  | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 0 | 196992 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 2 | 49248 | 4 | 196992 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 246240 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
230 | Zayed | مدينة محمد بن زايد - ME11 | 24.3291 | 54.5384 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
231 | Zayed | مدينة محمد بن زايد - ME11 | 24.3268 | 54.5389 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
232 | Zayed | مدينة محمد بن زايد - Z20 | 24.3157 | 54.5398 | Medium | Yes | under developer(Npc) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
233 | Zayed | مدينة محمد بن زايد - Z24 | 24.3153 | 54.5508 | Medium | Yes | under developer(Npc) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
234 | Zayed | مدينة محمد بن زايد - Z23 | 24.3168 | 54.5556 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
235 | Zayed | مدينة محمد بن زايد - Z30 | 24.2966 | 54.5551 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
236 | Zayed | مدينة محمد بن زايد - Z30 | 24.2997 | 54.5587 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
237 | Zayed | مدينة محمد بن زايد - Z30 | 24.3017 | 54.5645 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
238 | Zayed | مدينة محمد بن زايد - Z30 | 24.295 | 54.5672 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 1020864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
239 | Zayed | مدينة محمد بن زايد - Z31 | 24.3018 | 54.5744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
240 | Zayed | مدينة محمد بن زايد - Z34 | 24.3017 | 54.5839 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
241 | Zayed | مدينة محمد بن زايد - Z34 | 24.3021 | 54.5813 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
242 | Zayed | مدينة محمد بن زايد - Z34 | 24.304 | 54.5828 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
243 | Zayed | مدينة محمد بن زايد - Z34 | 24.3022 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
244 | Zayed | مدينة محمد بن زايد - Z34 | 24.3047 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
245 | Zayed | مدينة محمد بن زايد - Z35 | 24.3076 | 54.5916 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
246 | Zayed | مدينة محمد بن زايد - Z35 | 24.3161 | 54.5864 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
247 | Zayed | مدينة محمد بن زايد - Z33 | 24.3227 | 54.577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
248 | Zayed | مدينة محمد بن زايد - Z33 | 24.3192 | 54.5782 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
249 | Zayed | مدينة محمد بن زايد - Z33 | 24.323 | 54.5754 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
250 | Zayed | مدينة محمد بن زايد - Z22 | 24.3223 | 54.5688 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
251 | Zayed | مدينة محمد بن زايد - Z22 | 24.3222 | 54.5645 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
252 | Zayed | مدينة محمد بن زايد - Z22 | 24.3241 | 54.5623 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
253 | Zayed | مدينة محمد بن زايد - Z21 | 24.3232 | 54.5577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
254 | Zayed | مدينة محمد بن زايد - Z15 | 24.3334 | 54.5579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
255 | Zayed | مدينة محمد بن زايد - Z13 | 24.3437 | 54.5546 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
256 | Zayed | مدينة محمد بن زايد - Z13_01 | 24.3422 | 54.5636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
257 | Zayed | مدينة محمد بن زايد - Z36 | 24.3356 | 54.5782 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
258 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2868 | 54.5897 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 856704 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
259 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2818 | 54.5849 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 856704 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
260 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.256 | 54.6342 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
261 | Zayed | ربدان - RB1 | 24.4179 | 54.4945 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
262 | Zayed | ربدان - RB2 | 24.4149 | 54.4926 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
263 | Zayed | ربدان - RB7 | 24.407 | 54.515 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
264 | Zayed | ربدان - RB14 | 24.4024 | 54.4879 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
266 | Zayed | ربدان - RB28 | 24.3947 | 54.5009 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
269 | Zayed | SW17_مدينة خليفة - 01 | 24.4116 | 54.5139 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
270 | Zayed | مدينة خليفة - SW17 - وطني | 24.4163 | 54.5465 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
271 | Zayed | مدينة خليفة - SW17 - وطني | 24.4148 | 54.5432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
272 | Zayed | مدينة خليفة - SW17 - وطني | 24.4144 | 54.5405 | High | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  | 2 |  | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 0 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 164160 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 188784 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
274 | Zayed | مدينة خليفة | 24.4144 | 54.5411 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
275 | Zayed | مدينة خليفة - SW13 | 24.4132 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
276 | Zayed | مدينة خليفة - SW2 | 24.4197 | 54.5586 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
277 | Zayed | مدينة خليفة - SW3 | 24.4147 | 54.5641 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
278 | Zayed | مدينة خليفة - SW4 | 24.41 | 54.5645 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
280 | Zayed | مدينة خليفة - SE3 | 24.4195 | 54.5683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
281 | Zayed | مدينة خليفة - SE13 | 24.4184 | 54.5832 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
282 | Zayed | مدينة خليفة - SE24 | 24.414 | 54.5885 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
283 | Zayed | مدينة خليفة - SE26 | 24.4092 | 54.5924 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
284 | Zayed | مدينة خليفة - SE6 | 24.4016 | 54.5785 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
285 | Zayed | مدينة خليفة - SE16 | 24.4027 | 54.5843 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
286 | Zayed | مدينة خليفة - SE26 | 24.4045 | 54.592 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
287 | Zayed | مدينة خليفة - SE36 | 24.407 | 54.6048 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
288 | Zayed | مدينة خليفة - SE38 | 24.4124 | 54.6033 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
289 | Zayed | مدينة خليفة - SE35 | 24.4158 | 54.6016 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
290 | Zayed | مدينة خليفة - SE44 | 24.43 | 54.5817 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
291 | Zayed | مدينة خليفة - SE47 | 24.4365 | 54.5869 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
292 | Zayed | مدينة خليفة - SE47 | 24.44 | 54.5905 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
293 | Zayed | مدينة خليفة - SE40 | 24.4264 | 54.6002 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
294 | Zayed | مدينة خليفة - الراحة - RBW13 | 24.4343 | 54.5597 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
298 | Zayed | مدينة زايد - MZ6 | 24.3781 | 54.5951 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
299 | Zayed | مدينة زايد - MZ6 | 24.3826 | 54.6024 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
300 | Zayed | مدينة زايد - MZ7 | 24.3867 | 54.6059 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
301 | Zayed | مدينة زايد - MZ7 | 24.3819 | 54.6087 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
302 | Zayed | مدينة زايد - MZ10 | 24.3691 | 54.6046 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
303 | Zayed | مدينة زايد - MZ1 | 24.3657 | 54.6032 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
304 | Zayed | مدينة زايد - MZ1 | 24.3604 | 54.6 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
305 | Zayed | مدينة زايد - MZ8 | 24.3892 | 54.6189 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
306 | Zayed | مدينة زايد - MZ9 | 24.3922 | 54.6221 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
307 | Zayed | مدينة شخبوط - MSH7 | 24.349 | 54.6085 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
308 | Zayed | مدينة شخبوط - MSH7 | 24.3519 | 54.611 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
309 | Zayed | مدينة شخبوط - MSH7 | 24.348 | 54.6131 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
310 | Zayed | مدينة شخبوط - MSH5 | 24.35 | 54.6163 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
311 | Zayed | مدينة شخبوط - MSH5 | 24.3503 | 54.6186 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
312 | Zayed | مدينة شخبوط - MSH5 | 24.3443 | 54.6165 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
313 | Zayed | مدينة شخبوط - MSH3 | 24.3453 | 54.6214 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
314 | Zayed | مدينة شخبوط - MSH1 | 24.3373 | 54.6237 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
315 | Zayed | مدينة شخبوط - MSH2 | 24.3423 | 54.6272 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
316 | Zayed | مدينة شخبوط - MSH1 | 24.3436 | 54.6316 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
317 | Zayed | مدينة شخبوط - MSH15 | 24.3583 | 54.637 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
318 | Zayed | مدينة شخبوط - MSH14 | 24.3643 | 54.6345 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
319 | Zayed | مدينة شخبوط - MSH17 | 24.3697 | 54.6488 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
320 | Zayed | مدينة شخبوط - MSH19 | 24.3727 | 54.6467 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
321 | Zayed | مدينة شخبوط - MSH19 | 24.3721 | 54.6428 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
322 | Zayed | مدينة شخبوط - MSH23 | 24.3774 | 54.6306 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
323 | Zayed | مدينة شخبوط - MSH20 | 24.3756 | 54.6454 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
324 | Zayed | مدينة شخبوط - MSH24 | 24.388 | 54.6396 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
325 | Al Wathbah | بني ياس - EB1_03 | 24.3174 | 54.6355 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
326 | Al Wathbah | بني ياس - EB6_01 | 24.3068 | 54.6446 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
327 | Al Wathbah | بني ياس - EB7_B | 24.2999 | 54.6381 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
328 | Al Wathbah | بني ياس -EB10_A | 24.293 | 54.6517 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
329 | Al Wathbah | بني ياس -WB3_A | 24.2888 | 54.6342 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
330 | Al Wathbah | بني ياس -EB11_01 | 24.3089 | 54.6456 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
331 | Al Wathbah | بني ياس -EB1_04 | 24.3256 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
332 | Al Wathbah | الشوامخ - SHM10 | 24.3431 | 54.6493 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
333 | Al Wathbah | الشوامخ - SHM9 | 24.3498 | 54.6551 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
334 | Al Wathbah | الشوامخ - SHM9 | 24.3535 | 54.6619 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
335 | Al Wathbah | الشوامخ - SHM3 | 24.362 | 54.6552 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
336 | Al Wathbah | الشوامخ - SHM2 | 24.3681 | 54.6603 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
337 | Al Wathbah | الشوامخ - SHM1 | 24.3771 | 54.6636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
338 | Al Wathbah | الشامخة - SH10 | 24.3969 | 54.704 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
339 | Al Wathbah | الشامخة - SH11 | 24.3834 | 54.7167 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
340 | Al Wathbah | الشامخة - SH14 | 24.3692 | 54.7154 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
341 | Al Wathbah | مدينة الرياض - RD26 | 24.3287 | 54.7804 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 | 3 |  |  | 6480 | 0 | 0 | 6480 | 77760 | 291600 | 0 | 369360 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 2 | 49248 | 3 | 369360 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 418608 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
342 | Al Wathbah | مدينة الرياض - RD32 | 24.3325 | 54.7441 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
343 | Al Wathbah | مدينة الرياض - RD11 | 24.3562 | 54.7382 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
344 | Al Wathbah | مدينة الرياض - RD7 | 24.3769 | 54.7572 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
345 | Al Shahama | الفلاح - 1E | 24.433 | 54.7399 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
346 | Al Shahama | الفلاح - 1E | 24.431 | 54.7432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
347 | Al Shahama | الفلاح - 1E | 24.4412 | 54.7333 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
348 | Al Shahama | الفلاح - 1D | 24.4464 | 54.7381 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
349 | Al Shahama | الفلاح - 1C | 24.4577 | 54.7377 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
350 | Al Shahama | الفلاح - 1B | 24.4563 | 54.7178 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
351 | Al Shahama | جزيرة ياس - YN3 | 24.5108 | 54.6005 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
352 | Al Shahama | جزيرة ياس - YN3 | 24.504 | 54.596 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 2 |  |  | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 270864 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
353 | Al Shahama | جزيرة ياس - YN7 | 24.4977 | 54.6225 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
354 | Al Shahama | الباهية - Al Shahamah Old | 24.5421 | 54.6796 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
355 | Al Shahama | الباهية - Al Bahyah New | 24.546 | 54.6293 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
356 | Al Shahama | الباهية - Al Bahyah New | 24.5467 | 54.6367 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
357 | Al Shahama | الباهية - Al Shahamah Old | 24.5584 | 54.6798 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
358 | Al Shahama | الرحبة - Rahbah_A | 24.5655 | 54.6872 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
359 | Al Shahama | الرحبة - Rahbah_A | 24.5663 | 54.6859 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
360 | Al Shahama | الرحبة - Rahbah_A | 24.5695 | 54.6862 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
361 | Al Shahama | الرحبة - Rahbah_C | 24.5769 | 54.6871 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
362 | Al Shahama | الرحبة - Rahbah_G | 24.6021 | 54.6998 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
363 | Al Shahama | الرحبة - السمحة | 24.6241 | 54.7104 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
364 | Al Shahama | السمحة - Al Samhah East | 24.6542 | 54.7605 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
365 | Al Shahama | السمحة - Al Samhah East | 24.661 | 54.7647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
366 | Al Shahama | السمحة -Al Samhah East Old | 24.6718 | 54.7741 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
367 | Al Shahama | السمحة -Al Samhah East Old | 24.6781 | 54.7753 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
368 | Al Shahama | السمحة -Samhah_V | 24.6712 | 54.7479 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
369 | Al Shahama | السمحة -Samhah_T | 24.6716 | 54.7581 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
370 | Al Shahama | السمحة -Al Samhah West Old_ | 24.6859 | 54.7676 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
371 | Al Wathbah | Qasr Al Wathbah South | 24.1767 | 54.7566 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
372 | Al Wathbah | Al Dhafrah East | 24.2383 | 54.6337 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
373 | Al Wathbah | Al Nahdah Al Askariah | 24.2607 | 54.7083 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
374 | Al Wathbah | Al Nahdah Al Askariah | 24.2634 | 54.7013 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
375 | Al Wathbah | Al Nahdah Al Askariah | 24.2677 | 54.6937 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
387 | Island | صيدليه الملا منطقه الخالديه | 24.4792 | 54.3579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
388 | Island | مدينه خليفه الطبيه | 24.4705 | 54.364 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  |  | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 0 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 3 | 147744 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 196992 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
389 | Island | مجلس المنهل | 24.4691 | 54.3587 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
392 | Island | خلف فندق فلايجيو شارع المطار | 24.4645 | 54.3745 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
397 | Island | خلف المركز الامريكي | 24.4551 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
398 | Island | خلف مركز القاضي الطبي | 24.4421 | 54.3678 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
399 | Island | دوار الفروسيه 1 | 24.4425 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
400 | Island | جوار مجمع حدائق المشرف | 24.4431 | 54.3734 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
401 | Island | دوار الفروسيه 2 | 24.4465 | 54.3757 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
402 | Island | اسفل جسر شارع الخليج العربي | 24.4351 | 54.3768 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
403 | Island | جوار مبني الهويه والجنسيه 1 | 24.4473 | 54.3897 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
404 | Island | جوار مبني الهويه والجنسيه 2 | 24.4477 | 54.3886 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
406 | Island | مرسي البطين جوار مرسى اليخوت 2 | 24.4514 | 54.3368 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
407 | Island | حديقه ام الامارات 2 | 24.4544 | 54.3818 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
409 | Island | مينا زايد تابع للمطور | 24.5322 | 54.3661 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
410 | Island | مينا زايد تابع للمطور | 24.5221 | 54.3682 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
411 | Island | مينا زايد تابع للمطور | 24.5136 | 54.3685 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
413 | Island | مواقف سيارات خلف فندق نهال | 24.4982 | 54.3727 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
414 | Island | مستشفي الكورنيش | 24.5013 | 54.3696 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
417 | Island | مواقف سيارات سوق السجاد | 24.5121 | 54.3825 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
421 | Island | جوار بنك ابو ظبي الاول - شارع السلام | 24.4919 | 54.378 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
422 | Island | شارع الريم جوار مطعم جاد | 24.4902 | 54.3807 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
423 | Island | جوار فندق جنه شارع الفلاح | 24.489 | 54.3831 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
424 | Island | جوار مجمع طاقه 1 | 24.4846 | 54.3788 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
425 | Island | جوار مجمع طاقه 2 | 24.4835 | 54.3779 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
426 | Island | مواقف شارع السلام محال تاجير السيارات 1 | 24.486 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
427 | Island | مواقف شارع السلام محال تاجير السيارات 2 | 24.485 | 54.3821 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
428 | Island | مواقف حافلات مدرسه الشيخه فاطمه 1 | 24.4818 | 54.3799 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
429 | Island | مواقف حافلات مدرسه الشيخه فاطمه 2 | 24.4823 | 54.3796 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
430 | Island | جوار السفاره السريلانكيه | 24.4815 | 54.3848 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
433 | Island | جوار مدرسه الايمان الخاصه | 24.4892 | 54.3671 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
434 | Island | جوار مسجد عبد الرحيم خوري | 24.4859 | 54.3712 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
435 | Island | شارع المرور مقابل سوق الذهب | 24.4847 | 54.3667 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
436 | Island | شارع المرور مقابل سوق الذهب | 24.4859 | 54.366 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
437 | Island | مواقف سوق الذهب | 24.4843 | 54.3644 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
438 | Island | تقاطع شارع المرور مع شارع الفلاح | 24.4787 | 54.3697 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
439 | Island | فندق النخيل شارع المرور | 24.4775 | 54.3715 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
440 | Island | خلف جراند الامارات شارع المرور | 24.4731 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
441 | Island | جوار كنتاكي شارع المطار | 24.4733 | 54.3683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
442 | Island | فندق ماريوت شارع المطار | 24.4704 | 54.3701 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
443 | Island | منطقه ال نهيان " محلات الشوكلاته " | 24.4726 | 54.3803 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
444 | Island | مجمع الكرامه | 24.4634 | 54.372 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
445 | Island | مبني تدوير " الاشغال سابقا " | 24.4613 | 54.3749 | Very High | No | N/A | Yes | Inadequate Design Capacity |  | 1 | 5184 | 19440 | 0 | 24624 | 2 | 0 |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Inadequate Design Capacity | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
446 | Island | شارع ماء سلوان مقابل صحه مستشفي خليفه | 24.4674 | 54.3689 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
447 | Island | مجمع الكرامه | 24.4625 | 54.3709 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
448 | Island | شارع الكرامه | 24.4613 | 54.3699 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
449 | Island | روضه ابو ظبي للاطفال | 24.4634 | 54.3673 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
450 | Island | مطعم المزراب الشعبي | 24.4543 | 54.3863 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
451 | Island | نادي الجزيره | 24.4513 | 54.3925 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 4 |  |  | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 0 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 4 | 196992 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 246240 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
452 | Island | خلف جامعه خليفه | 24.4449 | 54.3989 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
453 | Island | مسجد حمزه بن عبد المطلب | 24.4437 | 54.4062 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
454 | Island | حديقه قاف " حديقه الملك حمد " | 24.4357 | 54.4114 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
455 | Island | خياط البيت السعيد - شارع المرور | 24.4379 | 54.4136 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
456 | Island | مركز فحص المركبات - ادنوك شارع المرور | 24.4355 | 54.4168 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
457 | Island | كليه الشرطه | 24.4378 | 54.4193 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
458 | Island | خلف مسجد سيف بن حارب المنصوري | 24.4389 | 54.4185 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
461 | Island | شارع سلامه بنت بطيء | 24.4333 | 54.4034 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
462 | Island | شارع المدرسه | 24.4315 | 54.4094 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
463 | Island | مقابل اكادميه ابو ظبي للسباحه | 24.4267 | 54.4132 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
464 | Island | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | 24.4251 | 54.4099 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
465 | Island | شرق 43 | 24.4397 | 54.4297 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
466 | Island | جوار مسجد جبريل | 24.4254 | 54.4254 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
467 | Island | شارع الخرطوم - مدرسه الريم | 24.4346 | 54.4317 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
468 | Island | منطقه السعاده 1 | 24.4361 | 54.4371 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
469 | Island | منطقه السعاده 2 | 24.4413 | 54.4351 | Medium | No | N/A | No | Absense of Drainage Network |  | 2 | 10368 | 38880 | 0 | 49248 | 3 |  |  | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 0 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 3 | 147744 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 196992 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
470 | Island | مجمع اوريكس | 24.4402 | 54.4476 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
471 | Island | محطه ادنوك - جوار مجمع الظبي | 24.4402 | 54.4518 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 0 | 49248 | 4 |  |  | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 0 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | No | 2 | 49248 | 4 | 196992 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 246240 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
472 | Island | مدخل قصر المينا مع شارع المروج | 24.4378 | 54.4591 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
473 | Island | دوار مدينه زايد الرياضيه | 24.4192 | 54.4567 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
474 | Island | ملاعب منطقه الروضه " غرب مطار البطين " | 24.4203 | 54.4617 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
475 | Island | منطقه الروضه " الابراج السكنيه " | 24.4178 | 54.4647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
476 | Island | حديقه نادي الضباط | 24.404 | 54.475 | Medium | No | N/A | No | Absense of Drainage Network |  | 4 | 20736 | 77760 | 0 | 98496 | 5 |  |  | 5 | 0 | 0 | 4320 | 4320 | 51840 | 194400 | 0 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | No | 4 | 98496 | 5 | 246240 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 344736 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
477 | Island | اكادميه الرياضه النسائيه | 24.4018 | 54.4696 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
478 | Island | مجمع هيلز ابو ظبي | 24.4034 | 54.4648 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
479 | Island | حديقه نادي الضباط | 24.4036 | 54.4817 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
480 | Island | مواقف واحه الكرامه | 24.4089 | 54.4797 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
481 | Island | مقابل دائره القضاء - شارع النوفل | 24.4186 | 54.4467 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
483 | Al Wathbah | طريق E30 باتجاه العزب | 24.2094 | 54.8215 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
484 | Al Shahama | طريق E16 | 24.5742 | 55.176 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 73872 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
485 | Al Wathbah | شارع الخير | 24.2982 | 54.7121 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
487 | Zayed | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | 24.3916 | 54.5423 | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  | 2 |  | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 0 | 164160 | 0 | 0 | 0 | 0 | 750000 | 60000 | Yes | 1 | 24624 | 2 | 164160 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 998784 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
488 | Zayed | دوار كرم الشام - مدينة شخبوط | 24.3716 | 54.6513 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
489 | Zayed | شارع مطر بن خادم المهيري- مدينة شخبوط | 24.3715 | 54.6481 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 873120 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
491 | Mussafah | منطقة الأريام | 24.1659 | 54.3382 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
492 | Mussafah | ايكاد 2 | 24.303228 | 54.4499 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Highly Critical | 1 | 0 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
494 | Mussafah | منطقة النوف | 24.2478 | 54.1654 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
495 | Al Wathbah | ظهارة الطيب - أبو ظبي | 24.2105 | 54.8397 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
496 | Al Wathbah | مدينة الرياض - حوض 144 | 24.2881 | 54.6911 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 73872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
497 | Mussafah | منطقة الأريام | 24.2167 | 54.4065 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
498 | Al Wathbah | عزب دهان - الوافية | 24.209 | 54.9138 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
499 | Al Shahama | منطقة العجبان | 24.5997 | 54.8401 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
500 | Mussafah | ايكاد 3 | 24.3108 | 54.5006 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
501 | Al Wathbah | عزب دهان | 24.195870 | 54.9685 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
502 | Al Shahama | مزارع عجبان - شارع عويد | 24.676 | 54.8319 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
503 | Mussafah | ايكاد 3 | 24.2996 | 54.4905 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
504 | Al Wathbah | منطقة طريق الحفار | 24.254018 | 54.8251 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  |  | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 0 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | Yes | 1 | 24624 | 1 | 49248 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | FALSE | Absence of Drainage Network | FALSE |  |  | 0 | 823872 | TRUE | FALSE | FALSE | ADM pond/detention work only. | CLIENT INPUT REQUIRED | No specific plan
505 | Mussafah | ايكاد 3 | 24.299677 | 54.4849 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 0 | 24624 | 1 |  | 1 |  | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 0 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 1 | 82080 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Topography & Road Engineering | FALSE |  |  | 0 | 106704 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
506 | Al Wathbah | أكادمية الدفاع المدني - طريق الحفار | 24.284 | 54.8305 | Low | Yes | Private Area | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 0 | 24624 | 2 |  |  | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 0 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | No | 1 | 24624 | 2 | 98496 | 0 | 0 | [7 empty] | 1 | Critical | 0 | 1 | TRUE | Absence of Drainage Network | FALSE |  |  | 0 | 123120 | FALSE | FALSE | FALSE |  | CLIENT INPUT REQUIRED | No specific plan
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[14 empty] | 0 | [11 empty] | 0
[11 empty] | 265 |  |  |  | 6525360 | 380 | 38 | 28 | 314 | [7 empty] | 22440672 |  |  |  |  | 76500000 | 60000 |  |  | 6525360 | 380
Note on BQ2: Must match the CPDS_CIP_ID values in the hotspot table for the CAPEX lookup to work.

## Full List (inc previous 255) (hidden)
[17 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [20 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan
[44 empty] | Select Yes or No | Select one: Critical Infrastructure, Detailed Design, Fast-Track, or Quick Win | Provide the primary solution such as inlet, pipe, Upgrade to Catchment , Pond / Spillway, etc | Select one: Permanent, Interim, or Temporary | Please specify if additional budget is required for this hotspot (Yes/No) | Provide the requested budget for each applicable hotspot. If a single project spans multiple hotspots, list the budget only once under the primary hotspot. For all other covered hotspot entries, replace the budget with: "Included in Hotspot #X budget." | Provide the current rainfall design event, including the return period | Provide the existing network’s technical or hydraulic capacit | Provide the future or target rainfall design event, including the return period | Provide the future or target network capacity after the planned intervention | Provide the estimated floodwater volume managed by network after intervention | Provide the expected number of hours required for floodwater to recede after intervention | Revise the planned mobilization date | Revise the planned Phase 1 completion date | Revise the planned completion date | Select one: Contractor Design phase, Parsons Verification Phase, IDAS Review Phase, Municipality Permitting Phase, Implementation phase, Hand Over Phase | Select Yes or No. Enter Yes only after formal approval has been issued. |  | Provide the actual mobilization date (only after actual mobilization) | Provide the actual completion date (only after actual completion) | Select one: Not Started, On Track, Delayed, or Completed | Provide the full name of the accountable IDD owner.
# | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Latitude2 | Longitude3 | check L | Check Long | Hotspot_Location2 | Check A | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD Interventoin Planned | IDD_Design_Category | Design Solution | Type of Intervention | Additional Budget Requirment | Additional Budget Requested | Hotspot Network Rain Design Event (Current) | Hotspot Network Design Technical Capacity (Current) | Hotspot Network Rain Design Event (Future) | Hotspot Network Design Technical Capacity (Future) | Flood Volume Capacity after Intervention | Associated recovery time after intervention | Planned_IDD_Mobilization_Date | Critical Infrastructure Area Phase1 Solution Completion Date | Planned_IDD_Completion_Date | Project Stage | Approval from IDAS secured (Yes/No) | Design Description | Actual_Mobilization_Date | Actual_Completion_Date | Intervention status | IDD_Owner_Name | Original 255 List
1 | Al Shahama | نفق الشهامة | 24.546 | 54.691 | 24.546 | 54.691 | 0 | 0 | نفق الشهامة | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 331200 |  |  | 250000 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-28 | 2026-09-11 | 2026-12-11 | Contractor |  |  |  |  | 105 | Parsons | Yes
2 | Al Shahama | شارع الشيخ زايد بن سلطان | 24.4927 | 54.6493 | 24.4927 | 54.6493 | 0 | 0 | شارع الشيخ زايد بن سلطان | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-12-08 | Permitting Phase | Yes |  |  |  | 49 | Parsons | Yes
3 | Al Shahama | مجمع الجسور ياس | 24.4858 | 54.6449 | 24.4858 | 54.6449 | 0 | 0 | مجمع الجسور ياس | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 6 | [9 empty] | 596160 |  |  | 0 | 1100000 | 0 | 60000 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-09-11 | 2026-12-31 | Permitting Phase | Yes |  |  |  | 128 | Parsons | Yes
4 | Al Shahama | نفق الشهامة الجديدة المؤدي الى ديرفيلدز مول | 24.5378 | 54.6848 | 24.5378 | 54.6848 | 0 | 0 | نفق الشهامة الجديدة المؤدي الى ديرفيلدز مول | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-09 |  | 2027-01-29 | Contractor |  |  |  |  | 51 | Parsons | Yes
5 | Al Shahama | جسر الشهامة نادي الوحدة | 24.5611 | 54.6953 | 24.5611 | 54.6953 | 0 | 0 | جسر الشهامة نادي الوحدة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 3 | [9 empty] | 298080 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 |  | 2026-09-21 | Contractor | Yes |  |  |  | 31 | Parsons | Yes
6 | Al Shahama | نفق كيزاد | 24.7287 | 54.8168 | 24.7287 | 54.8168 | 0 | 0 | نفق كيزاد | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 298080 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Lowering Project | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 |  | 2026-12-31 | IDAS Review Phase |  |  |  |  | 154 | AECOM | Yes
7 | Al Shahama | روضة الريف – شارع الشهد | 24.4622 | 54.68 | 24.4622 | 54.68 | 0 | 0 | روضة الريف – شارع الشهد | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 496800 |  |  |  | 575000 | 0 | [7 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2026-12-11 | Contractor |  |  |  |  | 51 | Parsons | Yes
8 | Al Shahama | خليفة الصناعية - شارع غناضة | 24.7304 | 54.7793 | 24.7304 | 54.7793 | 0 | 0 | خليفة الصناعية - شارع غناضة | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 4 | [9 empty] | 662400 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-10-08 | IDAS Review Phase |  |  |  |  | 49 | AECOM | Yes
9 | Al Shahama | منطقة الفلاح 4 | 24.4185 | 54.7241 | 24.4185 | 54.7241 | 0 | 0 | منطقة الفلاح 4 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-11-30 | IDAS Review Phase | Yes |  |  |  | 90 | Parsons | Yes
10 | Al Shahama | منطقة الفلاح 1 | 24.4213 | 54.7472 | 24.4213 | 54.7472 | 0 | 0 | منطقة الفلاح 1 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-25 | IDAS Review Phase | Yes |  |  |  | 82 | Parsons | Yes
11 | Al Shahama | ياس الحي الاماراتي | 24.4989 | 54.6024 | 24.4989 | 54.6024 | 0 | 0 | ياس الحي الاماراتي | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-08 |  | 2027-01-26 | Contractor |  |  |  |  | 49 | Parsons | Yes
12 | Al Shahama | الباهية - شارع عجيج – الباهية مدرسة أميتي | 24.5313 | 54.6376 | 24.5313 | 54.6376 | 0 | 0 | الباهية - شارع عجيج – الباهية مدرسة أميتي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2026-12-11 | Contractor | Yes |  |  |  | 51 | Parsons | Yes
13 | Al Shahama | شارع عجيج - الصدر | 24.5934 | 54.6515 | 24.5934 | 54.6515 | 0 | 0 | شارع عجيج - الصدر | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-29 |  | 2027-02-16 | IDAS Review Phase |  |  |  |  | 171 | AECOM | Yes
14 | Mussafah | شارع سلطان بن محمد القبيسي - بعد الجسر المؤدي الى المصفح- الأول | 24.3736 | 54.5229 | 24.3736 | 54.5229 | 0 | 0 | شارع سلطان بن محمد القبيسي - بعد الجسر المؤدي الى المصفح- الأول | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
15 | Mussafah | مدينة الامارات الانسانية | 24.3789 | 54.5129 | 24.3789 | 54.5129 | 0 | 0 | مدينة الامارات الانسانية | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 13 | [9 empty] | 2003760 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
16 | Mussafah | Sector 17 | 24.3656 | 54.4832 | 24.3656 | 54.4832 | 0 | 0 | Sector 17 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 3 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
17 | Mussafah | Sector 2 | 24.3779 | 54.5221 | 24.3779 | 54.5221 | 0 | 0 | Sector 2 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 3 | [9 empty] | 579600 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
18 | Mussafah | Sector 15 | 24.3736 | 54.4826 | 24.3736 | 54.4826 | 0 | 0 | Sector 15 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
19 | Mussafah | Sector 1 | 24.3792 | 54.5178 | 24.3792 | 54.5178 | 0 | 0 | Sector 1 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
20 | Mussafah | Sector 1 | 24.3825 | 54.5234 | 24.3825 | 54.5234 | 0 | 0 | Sector 1 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
21 | Zayed | مدخل مصفح القادم من شارع الخليج العربي | 24.3941 | 54.5186 | 24.3941 | 54.5186 | 0 | 0 | مدخل مصفح القادم من شارع الخليج العربي | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 8 | [9 empty] | 1523520 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-09-11 | 2027-01-12 | Permitting Phase |  |  |  |  | 142 | Parsons | Yes
22 | Mussafah | Sector 9 | 24.3686 | 54.4914 | 24.3686 | 54.4914 | 0 | 0 | Sector 9 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 10 | [9 empty] | 1854720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Contractor |  |  |  |  | 122 | AECOM | Yes
23 | Mussafah | دوار دينا تريد | 24.2884 | 54.5646 | 24.2884 | 54.5646 | 0 | 0 | دوار دينا تريد | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 10 | [9 empty] | 1771920 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 |  | 2026-12-25 | IDAS Review Phase |  |  |  |  | 122 | Parsons | Yes
24 | Mussafah | مستودعات البلدية | 24.2934 | 54.581 | 24.2934 | 54.581 | 0 | 0 | مستودعات البلدية | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 10 | [9 empty] | 1771920 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 |  | 2026-12-11 | Permitting Phase | Yes |  |  |  | 107 | Parsons | Yes
25 | Mussafah | طريق حميم | 24.1494 | 54.4205 | 24.1494 | 54.4205 | 0 | 0 | طريق فرعي متفرع من طريق حميم مؤدي لمدينة حميم العمالية | FALSE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 3 | [9 empty] | 430560 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-12-26 | Permitting Phase | Yes |  |  |  | 118 | Parsons | Yes
26 | Al Wathbah | مدينة الرياض - شارع طوي القايمة | 24.3314 | 54.7084 | 24.3314 | 54.7084 | 0 | 0 | مدينة الرياض - شارع طوي القايمة | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-12-13 | 2D modelling |  |  | 2026-08-20 |  | 115 | Parsons | Yes
27 | Al Wathbah | مدينة الرياض - شارع الخير | 24.3432 | 54.7578 | 24.3432 | 54.7578 | 0 | 0 | مدينة الرياض - شارع الخير | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 |  | 2026-12-15 | 2D modelling |  |  |  |  | 113 | Parsons | Yes
28 | Al Wathbah | مدينة الرياض - شارع العصري بن حمودة الظاهري | 24.3257 | 54.7446 | 24.3257 | 54.7446 | 0 | 0 | مدينة الرياض - شارع العصري بن حمودة الظاهري | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | 2026-12-15 | 2D modelling |  |  |  |  | 106 | Parsons | Yes
29 | Al Wathbah | مدينة الرياض -شارع الرياض | 24.333 | 54.7652 | 24.333 | 54.7652 | 0 | 0 | مدينة الرياض -شارع الرياض | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 745200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 |  | 2026-12-16 | 2D modelling |  |  |  |  | 113 | Parsons | Yes
30 | Al Wathbah | مدينة الرياض -شارع النهضة | 24.3273 | 54.7042 | 24.3273 | 54.7042 | 0 | 0 | مدينة الرياض -شارع النهضة | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | 2026-12-13 | 2D modelling |  |  |  |  | 104 | Parsons | Yes
31 | Al Wathbah | مدينة الرياض -شارع الميثاق | 24.3307 | 54.7001 | 24.3307 | 54.7001 | 0 | 0 | مدينة الرياض -شارع الميثاق | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 |  | 2026-12-06 | 2D modelling |  |  |  |  | 104 | Parsons | Yes
32 | Al Wathbah | مدينة الرياض - شارع سيح القطع | 24.3364 | 54.7356 | 24.3364 | 54.7356 | 0 | 0 | مدينة الرياض - شارع سيح القطع | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 745200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 |  | 2026-12-21 | 2D modelling |  |  |  |  | 121 | Parsons | Yes
33 | Al Wathbah | مدينة الرياض - شارع الصنوبر | 24.3415 | 54.7524 | 24.3415 | 54.7524 | 0 | 0 | مدينة الرياض - شارع الصنوبر | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | 2026-12-13 | 2D modelling |  |  |  |  | 104 | Parsons | Yes
34 | Al Wathbah | شارع الشيخ محمد بن راشد | 24.3732 | 54.729 | 24.3732 | 54.729 | 0 | 0 | شارع الشيخ محمد بن راشد | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 4 | [9 empty] | 993600 |  |  |  |  | 900000 | 130000 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-09-11 | 2026-09-11 | 2D modelling |  |  |  |  | 19 | Parsons | Yes
35 | Al Wathbah | خلف مسلخ بني ياس | 24.3037 | 54.6711 | 24.3037 | 54.6711 | 0 | 0 | خلف مسلخ بني ياس | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-10-02 | 2D modelling |  |  |  |  | 33 | Parsons | Yes
36 | Al Wathbah | الشوامخ - شارع خضيرمان | 24.3535 | 54.649 | 24.3535 | 54.649 | 0 | 0 | الشوامخ - شارع خضيرمان | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2027-01-28 | Parsons Phase |  |  |  |  | 99 | Parsons | Yes
37 | Al Wathbah | الشوامخ - مدخل ومخرج المزن | 24.3505 | 54.6802 | 24.3505 | 54.6802 | 0 | 0 | الشوامخ - مدخل ومخرج المزن | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 |  | 2026-12-15 | Permitting Phase | Yes |  |  |  | 100 | Parsons | Yes
38 | Al Wathbah | شارع الشوامخ | 24.3855 | 54.6702 | 24.3855 | 54.6702 | 0 | 0 | شارع الشوامخ | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 |  | 2026-09-07 | IDAS Review Phase | Yes |  | 2026-06-13 |  | 86 | Parsons | Yes
39 | Al Wathbah | دوار - الشوامخ 12 | 24.3843 | 54.6745 | 24.3843 | 54.6745 | 0 | 0 | دوار - الشوامخ 12 | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 |  | 2026-09-08 | IDAS Review Phase | Yes |  | 2026-06-13 |  | 87 | Parsons | Yes
40 | Al Wathbah | مدينة الرياض -شارع الخير | 24.3221 | 54.749 | 24.3221 | 54.749 | 0 | 0 | مدينة الرياض -شارع الخير | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-12-17 | 2D Modelling |  |  |  |  | 104 | Parsons | Yes
41 | Al Wathbah | الشوامخ 7 - شارع بدع بوحصية | 24.3721 | 54.6705 | 24.3721 | 54.6705 | 0 | 0 | الشوامخ 7 - شارع بدع بوحصية | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-12-21 | IDAS Review Phase | yes |  |  |  | 111 | Parsons | Yes
42 | Al Wathbah | مسجد الشيخة عفراء بنت زايد ال نهيان | 24.1836 | 54.9937 | 24.1836 | 54.9937 | 0 | 0 | مسجد الشيخة عفراء بنت زايد ال نهيان | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-30 | Permitting Phase | Yes |  |  |  | 87 | Parsons | Yes
43 | Al Wathbah | الختم القديمة - بجوار حديقة الختم | 24.1881 | 54.9966 | 24.1881 | 54.9966 | 0 | 0 | الختم القديمة - بجوار حديقة الختم | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-11-26 | Permitting Phase | Yes |  |  |  | 86 | Parsons | Yes
44 | Al Wathbah | بني ياس - شارع اليال | 24.3293 | 54.6331 | 24.3293 | 54.6331 | 0 | 0 | بني ياس - شارع اليال | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 |  | 2026-11-30 | IDAS Review Phase |  |  |  |  | 86 | Parsons | Yes
45 | Al Wathbah | بني ياس -شارع اليال | 24.3218 | 54.6427 | 24.3218 | 54.6427 | 0 | 0 | بني ياس -شارع اليال | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 |  | 2026-11-12 | IDAS Review Phase |  |  |  |  | 67 | Parsons | Yes
46 | Al Wathbah | بني ياس -شارع اليال | 24.3144 | 54.6534 | 24.3144 | 54.6534 | 0 | 0 | بني ياس -شارع اليال | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 |  | 2026-08-25 | Permitting Phase | Yes |  | 2026-06-15 |  | 71 | Parsons | Yes
47 | Al Wathbah | بني ياس - شارع اليال | 24.3069 | 54.6633 | 24.3069 | 54.6633 | 0 | 0 | بني ياس - شارع اليال | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 |  | 2026-08-25 | Permitting Phase | Yes |  | 2026-06-15 |  | 71 | Parsons | Yes
48 | Al Wathbah | بني ياس - شارع الشيخ محمد بن راشد | 24.2888 | 54.6549 | 24.2888 | 54.6549 | 0 | 0 | بني ياس - شارع الشيخ محمد بن راشد | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-15 | 2026-09-11 | 2026-09-11 | IDAS Review Phase |  |  | 2026-08-15 |  | 27 | Parsons | Yes
49 | Al Wathbah | بني ياس - شارع الخويرة | 24.3044 | 54.6281 | 24.3044 | 54.6281 | 0 | 0 | بني ياس - شارع الخويرة- قرب بحيرة بني ياس | FALSE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-12-27 | Permitting Phase | Yes |  |  |  | 119 | Parsons | Yes
50 | Al Wathbah | نفق الوثبة | 24.2693 | 54.6681 | 24.2693 | 54.6681 | 0 | 0 | نفق الوثبة | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 993600 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2027-01-24 | Contractor |  |  |  |  | 139 | Parsons | Yes
51 | Al Wathbah | نفق النهضة | 24.2417 | 54.7368 | 24.2417 | 54.7368 | 0 | 0 | نفق النهضة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-20 |  | 2027-01-01 | Contractor |  |  |  |  | 103 | Parsons | Yes
52 | Al Wathbah | الوثبة - شارع الحفظة | 24.2681 | 54.673 | 24.2681 | 54.673 | 0 | 0 | الوثبة - شارع الحفظة | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-12-20 | Contractor |  |  |  |  | 104 | Parsons | Yes
53 | Al Wathbah | الوثبة جنوب | 24.2663 | 54.6578 | 24.2663 | 54.6578 | 0 | 0 | الوثبة جنوب | TRUE | Medium | Yes | Developer (Al Dar) | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-12 | IDAS Review Phase |  |  |  |  | 69 | Parsons | Yes
54 | Al Wathbah | بني ياس - شارع الجزائر | 24.2758 | 54.6451 | 24.2758 | 54.6451 | 0 | 0 | بني ياس - شارع الجزائر | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-07 | IDAS Review Phase | [5 empty] | Parsons | Yes
55 | Al Wathbah | الوثبة - شارع الرسوخ - بجانب منتزة الوثبة | 24.2458 | 54.7097 | 24.2458 | 54.7097 | 0 | 0 | الوثبة - شارع الرسوخ - بجانب منتزة الوثبة | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 |  | 2026-11-18 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
56 | Al Wathbah | الوثبة - شارع النهضة | 24.269 | 54.684 | 24.269 | 54.684 | 0 | 0 | الوثبة - شارع النهضة | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 |  | 2026-12-07 | Permitting Phase | Yes |  | 2026-08-06 |  |  | Parsons | Yes
57 | Al Wathbah | بني ياس - شارع السهل | 24.2701 | 54.6498 | 24.2701 | 54.6498 | 0 | 0 | بني ياس - شارع السهل | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 |  | 2026-12-18 | Permitting Phase | Yes |  | 2026-08-03 |  |  | Parsons | Yes
58 | Al Wathbah | الشامخة - بالقرب من الشامخة مول | 24.3999 | 54.7328 | 24.3999 | 54.7328 | 0 | 0 | الشامخة - بالقرب من الشامخة مول | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 400000 | 0 | 33000 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-12-19 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
59 | Al Wathbah | الشامخة - شارع احمد بن شملان الفلاحي | 24.3937 | 54.7044 | 24.3937 | 54.7044 | 0 | 0 | الشامخة - شارع احمد بن شملان الفلاحي | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-17 | IDAS Review Phase | [5 empty] | Parsons | Yes
60 | Al Wathbah | الشامخة - تقاطع شارع الترشيد مع شارع ام الثعالب | 24.411 | 54.747 | 24.411 | 54.747 | 0 | 0 | الشامخة - تقاطع شارع الترشيد مع شارع ام الثعالب | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-07 |  | 2026-12-23 | Permitting Phase | Yes |  | 2026-08-07 |  |  | Parsons | Yes
61 | Al Wathbah | الشامخة -شارع محمد بن شبيب المهيري | 24.3954 | 54.6943 | 24.3954 | 54.6943 | 0 | 0 | الشامخة -شارع محمد بن شبيب المهيري | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-24 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
62 | Al Wathbah | الشامخة -شارع الرضى | 24.3759 | 54.6992 | 24.3759 | 54.6992 | 0 | 0 | الشامخة -شارع الرضى | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-12-25 | IDAS Review Phase | Yes |  |  |  |  | Parsons | Yes
63 | Al Wathbah | الشامخة -شارع العايد | 24.3507 | 54.6832 | 24.3507 | 54.6832 | 0 | 0 | الشامخة -شارع العايد | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-11-22 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
64 | Al Wathbah | الشامخة - تقاطع شارع دمية طحنون مع شارع الخزنه | 24.4078 | 54.7358 | 24.4078 | 54.7358 | 0 | 0 | الشامخة - تقاطع شارع دمية طحنون مع شارع الخزنه | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-11-16 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
65 | Al Wathbah | العدلة - شارع طوي بو صلف | 24.4182 | 54.8663 | 24.4182 | 54.8663 | 0 | 0 | العدلة - شارع طوي بو صلف | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-07 | Contractor | Yes |  |  |  |  | Parsons | Yes
66 | Al Wathbah | العدلة - شارع طوي اشعب | 24.4114 | 54.8677 | 24.4114 | 54.8677 | 0 | 0 | العدلة - شارع طوي اشعب | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-09-17 | Permitting Phase | Yes |  | 2026-08-20 |  |  | Parsons | Yes
67 | Al Wathbah | عزب العدلة | 24.3853 | 54.9003 | 24.3853 | 54.9003 | 0 | 0 | عزب العدلة | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | N/A | N/A |  | 2026-07-26 |  |  | Parsons | Yes
68 | Al Wathbah | مدخل المحاجر في العدلة | 24.3869 | 54.9001 | 24.3869 | 54.9001 | 0 | 0 | مدخل المحاجر في العدلة | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | N/A | N/A |  | 2026-07-26 |  |  | Parsons | Yes
69 | Al Wathbah | مزارع العدلة | 24.3831 | 54.895 | 24.3831 | 54.895 | 0 | 0 | مزارع العدلة | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | N/A | N/A |  | 2026-07-26 |  |  | Parsons | Yes
70 | Al Wathbah | الفاية الصناعية | 24.3082 | 54.8788 | 24.3082 | 54.8788 | 0 | 0 | الفاية الصناعية | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-17 | Contractor | [5 empty] | Parsons | Yes
71 | Island | مواقف سيارات حديقه ام الامارات- المشرف / شارع الند ، غرب 24/2 | 24.4523 | 54.3841 | 24.4523 | 54.3841 | 0 | 0 | مواقف سيارات حديقه ام الامارات- المشرف / شارع الند ، غرب 24/2 | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 3 | [9 empty] | 298080 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 |  | 2026-10-10 | IDAS Review Phase | [5 empty] | AECOM | Yes
72 | Island | الدوار المؤدي الى نادي ضباط الشرطة. | 24.4054 | 54.4707 | 24.4054 | 54.4707 | 0 | 0 | الدوار المؤدي الى نادي ضباط الشرطة. | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-28 | Parsons Phase | [5 empty] | AECOM | Yes
73 | Island | المشرف / غرب52 / شارع احمد بن سعيد الرميثي | 24.4359 | 54.3954 | 24.4359 | 54.3954 | 0 | 0 | المشرف / غرب52 / شارع احمد بن سعيد الرميثي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-28 | IDAS Review Phase | [5 empty] | AECOM | Yes
74 | Island | تقاطع شارع الشيخ راشد بن سعيد مع تقاطع شارع الشيخة فاطمة بنت مبارك (مقابل مبنى دائرة الاشغال سابقا) | 24.4624 | 54.3763 | 24.4624 | 54.3763 | 0 | 0 | تقاطع شارع الشيخ راشد بن سعيد مع تقاطع شارع الشيخة فاطمة بنت مبارك (مقابل مبنى دائرة الاشغال سابقا) | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Hand over phase | N/A |  |  |  |  | AECOM | Yes
75 | Island | شارع اليزوة – الخالدية مقابل (سبينس- الكورنيش) | 24.4673 | 54.3343 | 24.4673 | 54.3343 | 0 | 0 | شارع اليزوة – الخالدية مقابل (سبينس- الكورنيش) | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 397440 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-05 | Contractor | [5 empty] | AECOM | Yes
76 | Island | شارع الكورنيش (مدخل بوابة قصر الامارات) | 24.4574 | 54.319 | 24.4574 | 54.319 | 0 | 0 | شارع الكورنيش (مدخل بوابة قصر الامارات) | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 5 |  |  | 248400 | 3 | [9 empty] | 596160 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-10 | Contractor | [5 empty] | AECOM | Yes
77 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4639 | 54.3766 | 24.4639 | 54.3766 | 0 | 0 | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 3 | [9 empty] | 364320 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Critical Infrastructure | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
78 | Island | مواقف سيارات مستشفي جلوبال كير | 24.4646 | 54.3658 | 24.4646 | 54.3658 | 0 | 0 | مواقف سيارات مستشفي جلوبال كير | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Implementation Phase | N/A |  |  |  |  | AECOM | Yes
79 | Island | شارع المطار مقابل قصر المنهل | 24.479 | 54.3624 | 24.479 | 54.3624 | 0 | 0 | شارع المطار مقابل قصر المنهل | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
80 | Island | مرسي البطين جوار مبني تبريد | 24.4544 | 54.3378 | 24.4544 | 54.3378 | 0 | 0 | مرسي البطين جوار مبني تبريد | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-19 | Contractor | [5 empty] | AECOM | Yes
81 | Island | بجوار مواقف سيارات المارينا مول | 24.4731 | 54.3201 | 24.4731 | 54.3201 | 0 | 0 | بجوار مواقف سيارات المارينا مول | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-27 | Contractor | [5 empty] | AECOM | Yes
82 | Island | مدارس التكنولوجيا التطبيقيه بمنطقه ال نهيان | 24.4672 | 54.3781 | 24.4672 | 54.3781 | 0 | 0 | مدارس التكنولوجيا التطبيقيه بمنطقه ال نهيان | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 397440 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-19 | Contractor | [5 empty] | AECOM | Yes
83 | Island | شارع الشيخة فاطمة بنت مبارك - مقابل مدرسة الامارات الوطنية | 24.4694 | 54.3851 | 24.4694 | 54.3851 | 0 | 0 | شارع الشيخة فاطمة بنت مبارك - مقابل مدرسة الامارات الوطنية | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | IDAS Review Phase | [5 empty] | Parsons | Yes
84 | Island | حوض E-25 - قريب من مبنى مبادلة | 24.4618 | 54.3936 | 24.4618 | 54.3936 | 0 | 0 | كامل حوض E-25 | FALSE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 12 |  |  | 397440 | 9 | [9 empty] | 1540080 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 |  | 2026-11-16 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
85 | Al Shahama | شارع الشيخ زايد بين مجمع جسور ياس و جسر المطار بالاتجاهين | 24.4749 | 54.6365 | 24.4743 | 54.6352 | Same location different coordinates |  | شارع الشيخ زايد بين مجمع جسور ياس و جسر المطار بالاتجاهين | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 8 |  |  | 397440 | 12 | [9 empty] | 1920960 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2026-12-31 | IDAS Review Phase | [5 empty] | Parsons | Yes
86 | Mussafah | نفق الصناعية الاول باتجاه الداخل | 24.3735 | 54.5219 | 24.3735 | 54.5219 | 0 | 0 | نفق الصناعية الاول باتجاه الداخل | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 4 | [9 empty] | 745200 |  |  | 0 | 0 | 525000 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
87 | Mussafah | نفق الصناعية الثاني باتجاه الداخل | 24.3465 | 54.5226 | 24.3465 | 54.5226 | 0 | 0 | نفق الصناعية الثاني باتجاه الداخل | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 414000 |  |  | 0 | 0 | 2100000 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
88 | Al Shahama | مخرج الجسر من الشامخة للفلاح باتجاه دبي | 24.4106 | 54.6815 | 24.4106 | 54.6815 | 0 | 0 | مخرج الجسر من الشامخة للفلاح باتجاه دبي | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 975000 | 60000 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-12-20 | Permitting Phase | Yes |  | 2026-08-19 |  |  | Parsons | Yes
89 | Al Shahama | مخرج جسر سويحان للقادم من جسر كرم الشام باتجاه الشامخة الفلاح | 24.4025 | 54.6703 | 24.4025 | 54.6703 | 0 | 0 | مخرج جسر سويحان للقادم من جسر كرم الشام باتجاه الشامخة الفلاح | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 840000 | 60000 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-12-23 | Permitting Phase | Yes |  | 2026-08-19 |  |  | Parsons | Yes
90 | Zayed | شارع الخليج العربي المخرج المؤدي لشارع العين | 24.3914 | 54.5291 | 24.3914 | 54.5291 | 0 | 0 | شارع الخليج العربي المخرج المؤدي لشارع العين | TRUE | Very High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 414000 |  |  | 0 | 0 | 0 | 33000 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
91 | Zayed | جسر تعليم القيادة بالاتجاهين | 24.347 | 54.5289 | 24.347 | 54.5289 | 0 | 0 | جسر تعليم القيادة بالاتجاهين | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Maintanence |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-30 |  | 2026-07-30 | Implementation Phase | N/A |  | 2026-06-30 |  |  | Parsons | Yes
92 | Zayed | جسر المفرق للقادم من مدينة شخبوط الطبية باتجاه ابوظبي | 24.313 | 54.6036 | 24.313 | 54.6036 | 0 | 0 | جسر المفرق للقادم من مدينة شخبوط الطبية باتجاه ابوظبي | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 |  | 2026-09-01 | IDAS Review Phase |  |  | 2026-07-30 |  |  | Parsons | Yes
93 | Al Shahama | شارع محمد بن راشد للقادم من دبي تم تحويل الحركة باتجاه الشامخة | 24.4242 | 54.7646 | 24.4242 | 54.7646 | 0 | 0 | شارع محمد بن راشد للقادم من دبي تم تحويل الحركة باتجاه الشامخة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-11-23 | Permitting Phase | Yes |  | 2026-08-19 |  |  | Parsons | Yes
94 | Zayed | شارع ابوظبي - العين مدخل شارع الخدمات قبل جسر مزيد مول باتجاه الخارج | 24.3886 | 54.5401 | 24.3886 | 54.5401 | 0 | 0 | شارع ابوظبي - العين مدخل شارع الخدمات قبل جسر مزيد مول باتجاه الخارج | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 300000 | 0 | 645000 | 60000 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
95 | Al Shahama | النفق المودي للشهامة للقادم من روضة الريف | 24.5429 | 54.6941 | 24.5429 | 54.6941 | 0 | 0 | النفق المودي للشهامة للقادم من روضة الريف | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 40000 | 0 | 645000 | 60000 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-28 | 2026-09-11 | 2026-12-11 | Contractor | [5 empty] | Parsons | Yes
96 | Al Wathbah | طريق سويحان بعد جسر الفلاح الشامخة باتجاه سويحان | 24.4188 | 54.7506 | 24.4188 | 54.7506 | 0 | 0 | طريق سويحان بعد جسر الفلاح الشامخة باتجاه سويحان | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 17 | [9 empty] | 3924720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2027-01-09 | Parsons Phase |  |  | 2026-08-19 |  |  | Parsons | Yes
97 | Zayed | على طول شارع ذياب بن عيسى في مدينة خليفة أ بالاتجاهين | 24.4025 | 54.5725 | 24.4025 | 54.5725 | 0 | 0 | على طول شارع ذياب بن عيسى في مدينة خليفة أ بالاتجاهين | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 |  | 2026-07-11 | Implementation Phase | yes |  | 2026-07-05 |  |  | Parsons | Yes
98 | Zayed | شارع الشيخ مكتوم بن راشد مقابل مستشفى شخبوط باتجاه الغربية | 24.3205 | 54.6125 | 24.3205 | 54.6125 | 0 | 0 | شارع الشيخ مكتوم بن راشد مقابل مستشفى شخبوط باتجاه الغربية | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 149040 | 10 | [9 empty] | 1391040 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-27 |  | 2026-09-08 | Implementation Phase | [5 empty] | Parsons | Yes
99 | Zayed | طريق ابوظبي العين قبل جسر محوي باتجاه الداخل | 24.3461 | 54.5731 | 24.3461 | 54.5731 | 0 | 0 | طريق ابوظبي العين قبل جسر محوي باتجاه الداخل | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 496800 |  |  |  | 600000 | 645000 | 60000 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2026-09-11 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
100 | Al Wathbah | شارع الشيخ مكتوم بن راشد عن حسر كرم الشام (الشوامخ) باتجاه دبي | 24.3726 | 54.6562 | 24.3726 | 54.6562 | 0 | 0 | شارع الشيخ مكتوم بن راشد عن حسر كرم الشام (الشوامخ) باتجاه دبي | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 331200 |  |  |  |  | 1140000 | 60000 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-17 | 2026-09-11 | 2026-11-27 | Permitting Phase | Yes |  | 2026-08-17 |  |  | Parsons | Yes
101 | Zayed | مدينة خليفة | 24.4406 | 54.6002 | 24.4406 | 54.6002 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-06 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-06 |  |  | Parsons | Yes
102 | Zayed | مدينة خليفة | 24.4149 | 54.502 | 24.4149 | 54.502 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
103 | Zayed | منطقة ربدان | 24.4112 | 54.5082 | 24.4112 | 54.5082 | 0 | 0 | منطقة ربدان | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-10-23 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
104 | Zayed | منطقة ربدان | 24.4028 | 54.5272 | 24.4028 | 54.5272 | 0 | 0 | منطقة ربدان | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
105 | Zayed | منطقة ربدان | 24.3493 | 54.6215 | 24.3493 | 54.6215 | 0 | 0 | منطقة ربدان | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-30 | IDAS Review Phase | [5 empty] | Parsons | Yes
106 | Zayed | مدينة شخبوط | 24.365 | 54.6482 | 24.365 | 54.6482 | 0 | 0 | مدينة شخبوط- شارع حدبة شخبوط | FALSE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 |  | 2026-09-22 | IDAS Review Phase |  |  | 2026-08-06 |  |  | Parsons | Yes
107 | Zayed | مدينة شخبوط | 24.405 | 54.5193 | 24.405 | 54.5193 | 0 | 0 | مدينة شخبوط | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 |  | 2026-10-27 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
108 | Zayed | منطقة ربدان | 24.3306 | 54.5368 | 24.3306 | 54.5368 | 0 | 0 | منطقة ربدان | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-20 | Contractor | [5 empty] | Parsons | Yes
109 | Zayed | مدينة محمد بن زايد | 24.4074 | 54.5026 | 24.4074 | 54.5026 | 0 | 0 | مدينة محمد بن زايد | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 |  | 2026-10-30 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
110 | Zayed | مدينة زايد | 24.3831 | 54.5948 | 24.3831 | 54.5948 | 0 | 0 | مدينة زايد- شارع الآصال | FALSE | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 |  | 2026-08-10 | Hand over phase | N/A |  | 2026-07-05 |  |  | Parsons | Yes
111 | Zayed | مدينة زايد | 24.3796 | 54.5576 | 24.3796 | 54.5576 | 0 | 0 | مدينة زايد- شارع سلطان بن محمد القبيسي | FALSE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-25 |  | 2026-09-16 | IDAS Review Phase |  |  | 2026-07-25 |  |  | Parsons | Yes
112 | Zayed | ساس النخل - مدينة زايد | 24.4187 | 54.4962 | 24.4187 | 54.4962 | 0 | 0 | ساس النخل - مدينة زايد | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-02 | Contractor | [5 empty] | Parsons | Yes
113 | Zayed | ربدان - ساس النخل | 24.3925 | 54.5033 | 24.3925 | 54.5033 | 0 | 0 | ربدان - ساس النخل | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
114 | Zayed | شارع جبر بن راشد الحلامي - طريق ساس النخل | 24.4237 | 54.5229 | 24.4237 | 54.5229 | 0 | 0 | شارع جبر بن راشد الحلامي - طريق ساس النخل | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 3 | [9 empty] | 298080 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 |  | 2026-12-10 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
115 | Zayed | مدينة محمد بن زايد | 24.308 | 54.5813 | 24.308 | 54.5813 | 0 | 0 | مدينة محمد بن زايد- شارع ياو العود | FALSE | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 |  | 2026-12-10 | Contractor | Yes |  |  |  |  | Parsons | Yes
116 | Zayed | مدينة زايد | 24.3846 | 54.633 | 24.3846 | 54.633 | 0 | 0 | مدينة زايد - شارع طوي القامة | FALSE | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-15 |  | 2026-08-17 | Hand over phase | N/A |  | 2026-07-15 |  |  | Parsons | Yes
117 | Zayed | مدينة زايد | 24.3542 | 54.6106 | 24.3542 | 54.6106 | 0 | 0 | مدينة زايد- شارع موشام تقاطع شارع النسيلة | FALSE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-21 |  | 2026-08-16 | Hand over phase | N/A |  | 2026-07-21 |  |  | Parsons | Yes
118 | Zayed | مدينة زايد | 24.3665 | 54.6067 | 24.3665 | 54.6067 | 0 | 0 | مدينة زايد- شارع ذياب بن عيسى | FALSE | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-12 |  | 2026-08-14 | Hand over phase | N/A |  | 2026-07-12 |  |  | Parsons | Yes
119 | Zayed | مدينة محمد بن زايد - شارع خليفة بن خميس الديهلي | 24.3403 | 54.5579 | 24.3403 | 54.5579 | 0 | 0 | مدينة محمد بن زايد - شارع خليفة بن خميس الديهلي | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-13 | [6 empty] | Parsons | Yes
120 | Zayed | مدينة محمد بن زايد | 24.2968 | 54.5634 | 24.2968 | 54.5634 | 0 | 0 | مدينة محمد بن زايد | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 |  | 2026-09-15 | Contractor | Yes |  |  |  |  | Parsons | Yes
121 | Zayed | Zayed City | 24.3686 | 54.6005 | 24.3686 | 54.6005 | 0 | 0 | مدينة زايد- دوار على تقاطع شارع ذياب بن عيسى وشارع زايد الخير | FALSE | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-22 |  | 2026-07-30 | Hand over phase | N/A |  | 2026-07-22 |  |  | Parsons | Yes
122 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.3994 | 54.5932 | 24.3994 | 54.5932 | 0 | 0 | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 |  | 2026-10-03 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
123 | Zayed | ربدان - شارع راشد بن جابر الهاملي | 24.4106 | 54.4965 | 24.4106 | 54.4965 | 0 | 0 | ربدان - شارع راشد بن جابر الهاملي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 |  | 2026-10-24 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
124 | Zayed | مدينة محمد بن زايد | 24.3176 | 54.5332 | 24.3176 | 54.5332 | 0 | 0 | مدينة محمد بن زايد | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-18 |  | 2026-09-17 | IDAS Review Phase |  |  | 2026-08-18 |  |  | Parsons | Yes
125 | Zayed | مدينة محمد بن زايد - MZ 17 | 24.3896 | 54.6092 | 24.3896 | 54.6092 | 0 | 0 | مدينة محمد بن زايد - MZ 17 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
126 | Zayed | مدينة زايد | 24.379 | 54.5851 | 24.379 | 54.5851 | 0 | 0 | مدينة زايد | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-25 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
127 | Zayed | ربدان | 24.4029 | 54.5038 | 24.4029 | 54.5038 | 0 | 0 | ربدان | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-25 | Permitting Phase | Yes |  | 2026-08-10 |  |  | Parsons | Yes
128 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4097 | 54.6368 | 24.4097 | 54.6368 | 0 | 0 | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | TRUE | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-11 | 2027-01-12 | Contractor | Yes |  |  |  |  | Parsons | Yes
129 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4102 | 54.6436 | 24.4102 | 54.6436 | 0 | 0 | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | TRUE | High | Yes | ADM Developer | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-11 | 2027-01-12 | Contractor | Yes |  |  |  |  | Parsons | Yes
130 | Zayed | مدينة زايد | 24.3704 | 54.6183 | 24.3704 | 54.6183 | 0 | 0 | مدينة زايد- MZ 4 | FALSE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-06 | Contractor | [5 empty] | Parsons | Yes
131 | Zayed | مدينة خليفة | 24.4334 | 54.5769 | 24.4334 | 54.5769 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 1 |  |  | 49680 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-04 |  |  | Parsons | Yes
132 | Al Shahama | مدينة الفلاح | 24.4283 | 54.7364 | 24.4283 | 54.7364 | 0 | 0 | مدينة الفلاح | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-10-23 | IDAS Review Phase | Yes |  |  |  |  | Parsons | Yes
133 | Al Shahama | الشهامة | 24.5196 | 54.6716 | 24.5196 | 54.6716 | 0 | 0 | الشهامة | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-26 | Contractor | Yes |  |  |  |  | Parsons | Yes
134 | Mussafah | مصفح صناعية | 24.326 | 54.5162 | 24.326 | 54.5162 | 0 | 0 | مصفح صناعية | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 10 | [9 empty] | 1788480 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
135 | Al Shahama | الباهية | 24.6264 | 54.7119 | 24.6264 | 54.7119 | 0 | 0 | الباهية | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-24 | Implementation Phase | Yes |  |  |  |  | AECOM | Yes
136 | Al Wathbah | طريق رزين | 24.1576 | 54.8458 | 24.1576 | 54.8458 | 0 | 0 | طريق رزين | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-17 | Contractor | [5 empty] | Parsons | Yes
137 | Al Shahama | شارع خليفة بن زايد - الريف | 24.4615 | 54.702 | 24.4615 | 54.702 | 0 | 0 | شارع خليفة بن زايد - الريف | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-09-09 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
138 | Al Wathbah | الوثبة جنوب | 24.2609 | 54.673 | 24.2609 | 54.673 | 0 | 0 | الوثبة جنوب | TRUE | Low | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-17 | Contractor | Yes |  |  |  |  | Parsons | Yes
139 | Al Shahama | مدينة الفلاح | 24.4258 | 54.7426 | 24.4258 | 54.7426 | 0 | 0 | مدينة الفلاح | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-02 |  | 2026-12-20 | IDAS Review Phase | Yes |  |  |  |  | Parsons | Yes
140 | Zayed | مدينة خليفة - دوار طيران الرئاسة | 24.436 | 54.6253 | 24.436 | 54.6253 | 0 | 0 | شارع الضيافة - دوار طيران الرئاسة | FALSE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 745200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 |  | 2026-07-25 | Hand over phase | N/A |  | 2026-07-18 |  |  | Parsons | Yes
141 | Mussafah | مصفح صناعية | 24.35 | 54.4939 | 24.35 | 54.4939 | 0 | 0 | مصفح صناعية | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 12 | [9 empty] | 2119680 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
142 | Al Wathbah | طريق الحفار | 24.3855 | 54.8443 | 24.3855 | 54.8443 | 0 | 0 | طريق الحفار | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-30 | Contractor | [5 empty] | Parsons | Yes
143 | Al Shahama | الرحبة | 24.5965 | 54.695 | 24.5965 | 54.695 | 0 | 0 | الرحبة | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-02 | Contractor | [5 empty] | AECOM | Yes
144 | Al Wathbah | شارع بني ياس بالقرب من محطة البترول | 24.2968 | 54.6285 | 24.2968 | 54.6285 | 0 | 0 | شارع بني ياس بالقرب من محطة البترول | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-12 | IDAS Review Phase | [5 empty] | Parsons | Yes
145 | Al Wathbah | مدينة الرياض | 24.3514 | 54.7125 | 24.3514 | 54.7125 | 0 | 0 | مدينة الرياض | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-09-11 | 2026-09-11 | IDAS Review Phase | [5 empty] | Parsons | Yes
146 | Al Wathbah | الوثبة جنوب | 24.2625 | 54.6587 | 24.2625 | 54.6587 | 0 | 0 | الوثبة جنوب | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-30 | Contractor | [5 empty] | Parsons | Yes
147 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.642 | 54.6575 | 24.642 | 54.6575 | 0 | 0 | الطريق المؤدي الى شاطى الشليلية | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 1 |  |  | 49680 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-10 | Implementation Phase | Yes |  |  |  |  | AECOM | Yes
148 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.6811 | 54.6692 | 24.6811 | 54.6692 | 0 | 0 | الطريق المؤدي الى شاطى الشليلية | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-18 | Contractor | [5 empty] | AECOM | Yes
149 | Al Shahama | شارع مكتوم بن راشد | 24.6959 | 54.7814 | 24.6959 | 54.7814 | 0 | 0 | شارع مكتوم بن راشد | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-26 | Contractor | [5 empty] | AECOM | Yes
150 | Al Shahama | شارع سلطان بن زايد - الريف | 24.4711 | 54.6709 | 24.4711 | 54.6709 | 0 | 0 | شارع سلطان بن زايد - الريف | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 |  | 2026-09-11 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
151 | Al Shahama | طريق الطف | 24.5973 | 54.9097 | 24.5973 | 54.9097 | 0 | 0 | طريق الطف | TRUE | Low | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Network New | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-08 | Contractor | [5 empty] | AECOM | Yes
152 | Al Shahama | الصدر- شارع عويد | 24.7557 | 54.7337 | 24.7557 | 54.7337 | 0 | 0 | الصدر- شارع عويد | TRUE | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-16 | Permitting Phase | Yes |  |  |  |  | AECOM | Yes
153 | Al Shahama | خليفة الصناعية - 6 | 24.7631 | 54.7003 | 24.7631 | 54.7003 | 0 | 0 | خليفة الصناعية - 6 | TRUE | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-24 | Permitting Phase | Yes |  |  |  |  | AECOM | Yes
154 | Al Shahama | مدينة الفلاح | 24.4322 | 54.7315 | 24.4322 | 54.7315 | 0 | 0 | مدينة الفلاح | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 347760 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-28 | Contractor | Yes |  |  |  |  | Parsons | Yes
155 | Al Shahama | مدينة الفلاح | 24.4395 | 54.7408 | 24.4395 | 54.7408 | 0 | 0 | مدينة الفلاح | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 248400 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-28 | Contractor | Yes |  |  |  |  | Parsons | Yes
156 | Al Wathbah | طريق أبو ظبي - العين | 24.3074 | 54.6051 | 24.3074 | 54.6051 | 0 | 0 | طريق أبو ظبي - العين | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-09 | 2026-09-09 | IDAS Review Phase | [5 empty] | Parsons | Yes
157 | Al Shahama | مدينة الفلاح | 24.4613 | 54.7361 | 24.4613 | 54.7361 | 0 | 0 | مدينة الفلاح | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-09-11 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
158 | Al Shahama | شارع مكتوم بن راشد باتجاه السمحة القديمة | 24.6864 | 54.7736 | 24.6864 | 54.7736 | 0 | 0 | شارع مكتوم بن راشد باتجاه السمحة القديمة | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-24 | Contractor | [5 empty] | AECOM | Yes
159 | Al Shahama | دوار على شارع مكتوم بن راشد | 24.7976 | 54.8637 | 24.7976 | 54.8637 | 0 | 0 | دوار على شارع مكتوم بن راشد | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-02 | Contractor | [5 empty] | AECOM | Yes
160 | Al Wathbah | طريق أبو ظبي - العين | 24.2812 | 54.6473 | 24.2812 | 54.6473 | 0 | 0 | طريق أبو ظبي - العين | TRUE | Medium | Yes | Developer | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Contractor | [5 empty] | Parsons | Yes
161 | Island | خلف مدرسه الامام الغزالي- شارع مطر المهيري - غرب 16 | 24.4583 | 54.3414 | 24.4583 | 54.3414 | 0 | 0 | خلف مدرسه الامام الغزالي- شارع مطر المهيري - غرب 16 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
162 | Island | شارع المطلع - شارع الخليج العربي - غرب 52 | 24.437 | 54.3736 | 24.437 | 54.3736 | 0 | 0 | شارع المطلع - شارع الخليج العربي - غرب 52 | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-27 | Contractor | [5 empty] | AECOM | Yes
163 | Island | مرسي البطين جوار مرسى اليخوت 1 | 24.4507 | 54.3348 | 24.4507 | 54.3348 | 0 | 0 | مرسي البطين جوار مرسى اليخوت 1 | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Contractor | [5 empty] | AECOM | Yes
164 | Island | شارع خليفة بن شخبوط - غرب 17-1- مواقف سيارات مدرسه هزاع بن زايد الاول | 24.4607 | 54.3575 | 24.4607 | 54.3575 | 0 | 0 | شارع خليفة بن شخبوط - غرب 17-1- مواقف سيارات مدرسه هزاع بن زايد الاول | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
165 | Island | تقاطع شارع الخليج العربي مع شارع الشيخ هزاع | 24.457 | 54.3552 | 24.457 | 54.3552 | 0 | 0 | تقاطع شارع الخليج العربي مع شارع الشيخ هزاع | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 5 | [9 empty] | 563040 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Contractor | [5 empty] | AECOM | Yes
166 | Island | شارع الشيخ زايد بن سلطان تقاطع شارع ظفير -النفق | 24.445 | 54.4379 | 24.445 | 54.4379 | 0 | 0 | شارع الشيخ زايد بن سلطان تقاطع شارع ظفير -النفق | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Contractor | [5 empty] | AECOM | Yes
167 | Island | مناره المقطع - جوار جسر المقطع | 24.4214 | 54.4818 | 24.4214 | 54.4818 | 0 | 0 | مناره المقطع - جوار جسر المقطع | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Contractor | [5 empty] | AECOM | Yes
168 | Island | جراند الامارات - شارع هزاع بن زايد تقاطع شارع الشيخ سلطلن بن زايد | 24.4741 | 54.3748 | 24.4741 | 54.3748 | 0 | 0 | جراند الامارات - شارع هزاع بن زايد تقاطع شارع الشيخ سلطلن بن زايد | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 397440 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-11 | Contractor | [5 empty] | AECOM | Yes
169 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع الفلاح | 24.4831 | 54.3758 | 24.4831 | 54.3758 | 0 | 0 | شارع سعيد بن احمد العتيبة تقاطع شارع الفلاح | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-11 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
170 | Island | مقابل فندق كرستال ابو ظبي- شرق 14 بالقرب من مركز مدينة زايد للتسوق | 24.4848 | 54.3636 | 24.4848 | 54.3636 | 0 | 0 | مقابل فندق كرستال ابو ظبي- شرق 14 بالقرب من مركز مدينة زايد للتسوق | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Contractor | [5 empty] | AECOM | Yes
171 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع زايد الأول | 24.4891 | 54.3699 | 24.4891 | 54.3699 | 0 | 0 | شارع سعيد بن احمد العتيبة تقاطع شارع زايد الأول | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
172 | Island | شارع الظفرة تقاطع شارع الخليج العربي- جوار دوار مجلس المشرف | 24.425 | 54.4108 | 24.425 | 54.4108 | 0 | 0 | شارع الظفرة تقاطع شارع الخليج العربي- جوار دوار مجلس المشرف | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Contractor | [5 empty] | AECOM | Yes
173 | Island | شارع زايد بن سلطان بين تقاطع شاع زايد الأول وشارع محمد بن بطي ال حامد - مقابل مطعم قصر الهند | 24.4928 | 54.3766 | 24.4928 | 54.3766 | 0 | 0 | شارع زايد بن سلطان بين تقاطع شاع زايد الأول وشارع محمد بن بطي ال حامد - مقابل مطعم قصر الهند | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
174 | Island | منطقه المزون | 24.4145 | 54.4314 | 24.4145 | 54.4314 | 0 | 0 | منطقه المزون | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-27 | Contractor | [5 empty] | AECOM | Yes
175 | Island | شارع الظفرة بين شارع راشد بن زايد وشارع الخليج العربي | 24.4279 | 54.4108 | 24.4279 | 54.4108 | 0 | 0 | شارع الظفرة بين شارع راشد بن زايد وشارع الخليج العربي | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
176 | Island | شارع سلامة بن بطي بين شارع راشد بن زايد وشارع الخليج العربي | 24.4339 | 54.4033 | 24.4339 | 54.4033 | 0 | 0 | شارع سلامة بن بطي بين شارع راشد بن زايد وشارع الخليج العربي | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
177 | Island | مدخل منطقة روضة ابوظبي من شارع الشيخ راشد بن سعيد- قرب مطار البطين | 24.417 | 54.47 | 24.417 | 54.47 | 0 | 0 | مدخل منطقة روضة ابوظبي من شارع الشيخ راشد بن سعيد- قرب مطار البطين | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
178 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع هزاع | 24.4704 | 54.3701 | 24.4704 | 54.3701 | 0 | 0 | شارع الشيخ راشد بن سعيد - تقاطع شارع هزاع | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
179 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع الشيخ محمد بن خليفة- مقابل محمصه الامراء | 24.459 | 54.3814 | 24.459 | 54.3814 | 0 | 0 | شارع الشيخ راشد بن سعيد - تقاطع شارع الشيخ محمد بن خليفة- مقابل محمصه الامراء | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
180 | Island | منطقة المعمورة - بجانب مبنى دائرة البلديات والنقل | 24.4617 | 54.3936 | 24.4638 | 54.3869 | 0.002098 | -0.006711 | منطقة المعمورة - بجانب مبنى دائرة البلديات والنقل | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 8 | [9 empty] | 1159200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 |  | 2026-11-14 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
181 | Island | جزيره الجبيل - شارع خليفه بن زايد | 24.5406 | 54.4836 | 24.5406 | 54.4836 | 0 | 0 | جزيره الجبيل - شارع خليفه بن زايد | TRUE | Low | Yes | مطور | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
182 | Island | دوار شارع الحريه - جزيره الريم | 24.482 | 54.4047 | 24.482 | 54.4047 | 0 | 0 | دوار شارع الحريه - جزيره الريم | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Contractor | [5 empty] | AECOM | Yes
183 | Island | جزيره السعديات - جوار مسجد الحمد | 24.5385 | 54.4396 | 24.5385 | 54.4396 | 0 | 0 | جزيره السعديات - شارع السعديات خلف مسجد الحمد | FALSE | Medium | Yes | مطور | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Contractor | [5 empty] | AECOM | Yes
184 | Island | شارع الشيخ راشد بن سعيد - جسر الجوازات | 24.4444 | 54.3952 | 24.4444 | 54.3952 | 0 | 0 | شارع الشيخ راشد بن سعيد - جسر الجوازات | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 6 |  |  | 298080 | 6 | [9 empty] | 596160 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
185 | Island | شارع سلطان بن زايد من تقاطغ شارع سلامة بن بطي الى شارع الظفرة- مقابل مطعم اليمن السعيد شارع المرور | 24.4397 | 54.4118 | 24.4397 | 54.4118 | 0 | 0 | شارع سلطان بن زايد من تقاطغ شارع سلامة بن بطي الى شارع الظفرة- مقابل مطعم اليمن السعيد شارع المرور | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Contractor | [5 empty] | AECOM | Yes
186 | Island | مدخل قصر البحر | 24.4724 | 54.3927 | 24.4724 | 54.3927 | 0 | 0 | مدخل قصر البحر | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 3 | [9 empty] | 447120 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-29 |  | 2026-12-23 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
187 | Island | مينا زايد تابع للمطور | 24.5171 | 54.3729 | 24.5171 | 54.3729 | 0 | 0 | مينا زايد - شارع الدوم | FALSE | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
188 | Island | الشارع من أرض المعارض لدوار الجوية- شارع السفارات | 24.4235 | 54.4444 | 24.4235 | 54.4444 | 0 | 0 | الشارع من أرض المعارض لدوار الجوية- شارع السفارات | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-25 | Contractor | [5 empty] | AECOM | Yes
189 | Mussafah | نفق المصفح الثاني باتجاه الخارج | 24.3473 | 54.5254 | 24.3473 | 54.5254 | 0 | 0 | نفق المصفح الثاني باتجاه الخارج | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Critical Infrastructure |  | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | TBC | [5 empty] | AECOM | Yes
190 | Al Shahama | الشهامة الجديدة | 24.5431 | 54.6917 | 24.5431 | 54.6917 | 0 | 0 | الشهامة الجديدة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-27 | 2026-09-11 | 2026-12-11 | Contractor | Yes |  |  |  |  | Parsons | Yes
191 | Al Shahama | نفق ياس | 24.461 | 54.6111 | 24.461 | 54.6111 | 0 | 0 | نفق ياس | TRUE | High | Yes | Developer (ICT) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-27 | 2026-09-11 | 2027-01-12 | Contractor | [5 empty] | Parsons | Yes
192 | Zayed | طريق الخليج العربي مقابل ملعب الكريكت | 24.3924 | 54.5486 | 24.3924 | 54.5486 | 0 | 0 | طريق الخليج العربي مقابل ملعب الكريكت | TRUE | Very High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 550000 | 0 | 60000 | [6 empty] | Yes | Fast- tracked | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
193 | Zayed | قبل الجسر المؤدي لمحمد بن زايد | 24.3772 | 54.551 | 24.3772 | 54.551 | 0 | 0 | قبل الجسر المؤدي لمحمد بن زايد | TRUE | High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-20 | Contractor | [5 empty] | Parsons | Yes
194 | Al Wathbah | بحيرة بني ياس | 24.3032 | 54.6275 | 24.3032 | 54.6275 | 0 | 0 | بحيرة بني ياس | TRUE | Very High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 |  | 2026-12-28 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
195 | Al Wathbah | شارع الزود - بني ياس | 24.3094 | 54.6156 | 24.3094 | 54.6156 | 0 | 0 | شارع الزود - بني ياس | TRUE | High | Yes | Private | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 15 | [9 empty] | 2848320 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 |  | 2026-12-30 | Permitting Phase | Yes |  | 2026-08-16 |  |  | Parsons | Yes
196 | Zayed | قبل الجسر المؤدي للمفرق الصناعية | 24.2921 | 54.5592 | 24.2921 | 54.5592 | 0 | 0 | قبل الجسر المؤدي للمفرق الصناعية | TRUE | Very High | Yes | Private | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  | 1340000 | 0 | 60000 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
197 | Zayed | شارع النصيلة- مدينة محمد بن زايد | 24.3244 | 54.5305 | 24.3244 | 54.5305 | 0 | 0 | شارع النصيلة- مدينة محمد بن زايد | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-09-07 | 2026-09-11 | Contractor | [5 empty] | Parsons | Yes
198 | Zayed | شارع النصيلة- مدينة محمد بن زايد - قبل الجسر | 24.3263 | 54.5841 | 24.3263 | 54.5841 | 0 | 0 | شارع النصيلة- مدينة محمد بن زايد - قبل الجسر | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 6 | [9 empty] | 1490400 |  |  | 0 | 0 | 1000000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-11 | 2026-10-01 | Contractor | Yes |  |  |  |  | Parsons | Yes
199 | Zayed | الجسر المؤدي الى المصفح - طريق أبو ظبي - العين | 24.3278 | 54.5859 | 24.3278 | 54.5859 | 0 | 0 | الجسر المؤدي الى المصفح - طريق أبو ظبي - العين | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 5 |  |  | 248400 | 4 | [9 empty] | 993600 |  |  | 0 | 0 | 2100000 | 0 | [6 empty] | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | 2026-10-08 | Contractor | Yes |  | 2026-08-10 |  |  | Parsons | Yes
200 | Al Wathbah | الشوامخ - تقاطع شارع طوي القامة مع شارع المورد | 24.3598 | 54.6677 | 24.3598 | 54.6677 | 0 | 0 | الشوامخ - تقاطع شارع طوي القامة مع شارع المورد | TRUE | High | Yes | Mainland | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-26 |  | 2026-11-11 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
201 | Zayed | مدينة خليفة | 24.4244 | 54.5449 | 24.4244 | 54.5449 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 |  | 2026-07-10 | Hand over phase | N/A |  | 2026-07-03 |  |  | Parsons | Yes
202 | Zayed | مدينة خليفة | 24.3958 | 54.555 | 24.3958 | 54.555 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-04 |  |  | Parsons | Yes
203 | Zayed | مدينة خليفة | 24.4297 | 54.5634 | 24.4297 | 54.5634 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 |  | 2026-07-10 | Hand over phase | N/A |  | 2026-07-03 |  |  | Parsons | Yes
204 | Zayed | مدينة خليفة | 24.4264 | 54.535 | 24.4264 | 54.535 | 0 | 0 | مدينة خليفة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 1 |  |  | 49680 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 |  | 2026-10-05 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
205 | Zayed | مدينة خليفة - طريق المطار | 24.4482 | 54.6131 | 24.4482 | 54.6131 | 0 | 0 | مدينة خليفة - طريق المطار | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 5 |  |  | 248400 | 2 | [9 empty] | 198720 | [5 empty] | 33000 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
206 | Zayed | مدينة خليفة | 24.4467 | 54.6181 | 24.4467 | 54.6181 | 0 | 0 | مدينة خليفة- شارع المريف | FALSE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-13 | 2026-09-11 | 2027-01-12 | Hand over phase | N/A |  | 2026-07-13 |  |  | Parsons | Yes
207 | Island | جسر دلما | 24.4668 | 54.3829 | 24.4668 | 54.3829 | 0 | 0 | جسر دلما | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 3 | [9 empty] | 745200 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 |  | 2026-12-15 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
208 | Mussafah | مدخل قاعدة الظفرة الجوية | 24.2821 | 54.5414 | 24.2821 | 54.5414 | 0 | 0 | مدخل قاعدة الظفرة الجوية | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 5 |  |  | 248400 | 6 | [9 empty] | 993600 |  |  |  | 1600000 | 2602500 | 100000 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | T.B.C |  | T.B.C | Contractor | Yes |  |  |  |  | Parsons | Yes
209 | Mussafah | مصفح صناعية - قطاع 3 | 24.3826 | 54.5106 | 24.3826 | 54.5106 | 0 | 0 | مصفح صناعية - قطاع 3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 180576 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
210 | Mussafah | مصفح صناعية - قطاع M19 | 24.3674 | 54.4811 | 24.3674 | 54.4811 | 0 | 0 | مصفح صناعية - قطاع M19 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 180576 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
211 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3578 | 54.4721 | 24.3578 | 54.4721 | 0 | 0 | مصفح صناعية - قطاع MW3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
212 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3567 | 54.4724 | 24.3567 | 54.4724 | 0 | 0 | مصفح صناعية - قطاع MW3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
213 | Mussafah | مصفح صناعية - قطاع M34 | 24.3463 | 54.5125 | 24.3463 | 54.5125 | 0 | 0 | مصفح صناعية - قطاع M34 | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 4 | 20736 | 77760 | 98496 | 5 | 1 | 3 | 1 | 2160 | 4320 | 864 | 7344 | 88128 | 330480 | 418608 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
214 | Mussafah | مصفح صناعية | 24.3284 | 54.5262 | 24.3284 | 54.5262 | 0 | 0 | مصفح صناعية | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 6 | [9 empty] | 1092960 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Critical Infrastructure | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Permitting Phase | Yes |  |  |  |  | AECOM | Yes
215 | Mussafah | مصفح صناعية - ICAD I | 24.3218 | 54.5048 | 24.3218 | 54.5048 | 0 | 0 | مصفح صناعية - ICAD I | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
216 | Mussafah | مصفح صناعية - ICAD I | 24.3268 | 54.4839 | 24.3268 | 54.4839 | 0 | 0 | مصفح صناعية - ICAD I | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
217 | Mussafah | مصفح صناعية - قطاع M42 | 24.3362 | 54.4781 | 24.3362 | 54.4781 | 0 | 0 | مصفح صناعية - قطاع M42 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
218 | Mussafah | مصفح صناعية - قطاع M43 | 24.3438 | 54.4807 | 24.3438 | 54.4807 | 0 | 0 | مصفح صناعية - قطاع M43 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
219 | Mussafah | مصفح صناعية - قطاع M32_02 | 24.3575 | 54.5142 | 24.3575 | 54.5142 | 0 | 0 | مصفح صناعية - قطاع M32_02 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’
220 | Mussafah | مصفح صناعية - قطاع M24 | 24.3607 | 54.5204 | 24.3607 | 54.5204 | 0 | 0 | مصفح صناعية - قطاع M24 | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
221 | Zayed | مدينة محمد بن زايد - Z9_01 | 24.3741 | 54.5364 | 24.3741 | 54.5364 | 0 | 0 | مدينة محمد بن زايد - Z9_01 | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
222 | Zayed | مدينة محمد بن زايد - Z1 | 24.3733 | 54.5395 | 24.3733 | 54.5395 | 0 | 0 | مدينة محمد بن زايد - Z1 | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | Contractor | [5 empty] | Parsons | Yes
223 | Zayed | مدينة محمد بن زايد - Z9 | 24.36 | 54.5372 | 24.36 | 54.5372 | 0 | 0 | مدينة محمد بن زايد - Z9 | TRUE | High | Yes | Private area | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
224 | Zayed | مدينة محمد بن زايد - Z5 | 24.353 | 54.5554 | 24.353 | 54.5554 | 0 | 0 | مدينة محمد بن زايد - Z5 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-06 | Contractor | [5 empty] | Parsons | Yes
225 | Zayed | مدينة محمد بن زايد - Z8 | 24.3514 | 54.5527 | 24.3514 | 54.5527 | 0 | 0 | مدينة محمد بن زايد - Z8 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
226 | Zayed | مدينة محمد بن زايد - Z9 | 24.3474 | 54.538 | 24.3474 | 54.538 | 0 | 0 | مدينة محمد بن زايد - Z9 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-30 | Contractor | [5 empty] | Parsons | Yes
227 | Zayed | مدينة محمد بن زايد - ME9 | 24.3451 | 54.5352 | 24.3451 | 54.5352 | 0 | 0 | مدينة محمد بن زايد - ME9 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
228 | Zayed | مدينة محمد بن زايد - ME9 | 24.3385 | 54.5324 | 24.3385 | 54.5324 | 0 | 0 | مدينة محمد بن زايد - ME9 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
229 | Zayed | مدينة محمد بن زايد - ME10 | 24.3359 | 54.5357 | 24.3359 | 54.5357 | 0 | 0 | مدينة محمد بن زايد - ME10 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
230 | Zayed | مدينة محمد بن زايد - ME11 | 24.3291 | 54.5384 | 24.3291 | 54.5384 | 0 | 0 | مدينة محمد بن زايد - ME11 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
231 | Zayed | مدينة محمد بن زايد - ME11 | 24.3268 | 54.5389 | 24.3268 | 54.5389 | 0 | 0 | مدينة محمد بن زايد - ME11 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
232 | Zayed | مدينة محمد بن زايد - Z20 | 24.3157 | 54.5398 | 24.3157 | 54.5398 | 0 | 0 | مدينة محمد بن زايد - Z20 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
233 | Zayed | مدينة محمد بن زايد - Z24 | 24.3153 | 54.5508 | 24.3153 | 54.5508 | 0 | 0 | مدينة محمد بن زايد - Z24 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
234 | Zayed | مدينة محمد بن زايد - Z23 | 24.3168 | 54.5556 | 24.3168 | 54.5556 | 0 | 0 | مدينة محمد بن زايد - Z23 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
235 | Zayed | مدينة محمد بن زايد - Z30 | 24.2966 | 54.5551 | 24.2966 | 54.5551 | 0 | 0 | مدينة محمد بن زايد - Z30 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
236 | Zayed | مدينة محمد بن زايد - Z30 | 24.2997 | 54.5587 | 24.2997 | 54.5587 | 0 | 0 | مدينة محمد بن زايد - Z30 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
237 | Zayed | مدينة محمد بن زايد - Z30 | 24.3017 | 54.5645 | 24.3017 | 54.5645 | 0 | 0 | مدينة محمد بن زايد - Z30 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
238 | Zayed | مدينة محمد بن زايد - Z30 | 24.295 | 54.5672 | 24.295 | 54.5672 | 0 | 0 | مدينة محمد بن زايد - Z30 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network
239 | Zayed | مدينة محمد بن زايد - Z31 | 24.3018 | 54.5744 | 24.3018 | 54.5744 | 0 | 0 | مدينة محمد بن زايد - Z31 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
240 | Zayed | مدينة محمد بن زايد - Z34 | 24.3017 | 54.5839 | 24.3017 | 54.5839 | 0 | 0 | مدينة محمد بن زايد - Z34 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
241 | Zayed | مدينة محمد بن زايد - Z34 | 24.3021 | 54.5813 | 24.3021 | 54.5813 | 0 | 0 | مدينة محمد بن زايد - Z34 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
242 | Zayed | مدينة محمد بن زايد - Z34 | 24.304 | 54.5828 | 24.304 | 54.5828 | 0 | 0 | مدينة محمد بن زايد - Z34 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
243 | Zayed | مدينة محمد بن زايد - Z34 | 24.3022 | 54.5775 | 24.3022 | 54.5775 | 0 | 0 | مدينة محمد بن زايد - Z34 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
244 | Zayed | مدينة محمد بن زايد - Z34 | 24.3047 | 54.5775 | 24.3047 | 54.5775 | 0 | 0 | مدينة محمد بن زايد - Z34 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
245 | Zayed | مدينة محمد بن زايد - Z35 | 24.3076 | 54.5916 | 24.3076 | 54.5916 | 0 | 0 | مدينة محمد بن زايد - Z35 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
246 | Zayed | مدينة محمد بن زايد - Z35 | 24.3161 | 54.5864 | 24.3161 | 54.5864 | 0 | 0 | مدينة محمد بن زايد - Z35 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
247 | Zayed | مدينة محمد بن زايد - Z33 | 24.3227 | 54.577 | 24.3227 | 54.577 | 0 | 0 | مدينة محمد بن زايد - Z33 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
248 | Zayed | مدينة محمد بن زايد - Z33 | 24.3192 | 54.5782 | 24.3192 | 54.5782 | 0 | 0 | مدينة محمد بن زايد - Z33 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
249 | Zayed | مدينة محمد بن زايد - Z33 | 24.323 | 54.5754 | 24.323 | 54.5754 | 0 | 0 | مدينة محمد بن زايد - Z33 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
250 | Zayed | مدينة محمد بن زايد - Z22 | 24.3223 | 54.5688 | 24.3223 | 54.5688 | 0 | 0 | مدينة محمد بن زايد - Z22 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
251 | Zayed | مدينة محمد بن زايد - Z22 | 24.3222 | 54.5645 | 24.3222 | 54.5645 | 0 | 0 | مدينة محمد بن زايد - Z22 | TRUE | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network
252 | Zayed | مدينة محمد بن زايد - Z22 | 24.3241 | 54.5623 | 24.3241 | 54.5623 | 0 | 0 | مدينة محمد بن زايد - Z22 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
253 | Zayed | مدينة محمد بن زايد - Z21 | 24.3232 | 54.5577 | 24.3232 | 54.5577 | 0 | 0 | مدينة محمد بن زايد - Z21 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
254 | Zayed | مدينة محمد بن زايد - Z15 | 24.3334 | 54.5579 | 24.3334 | 54.5579 | 0 | 0 | مدينة محمد بن زايد - Z15 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
255 | Zayed | مدينة محمد بن زايد - Z13 | 24.3437 | 54.5546 | 24.3437 | 54.5546 | 0 | 0 | مدينة محمد بن زايد - Z13 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’
256 | Zayed | مدينة محمد بن زايد - Z13_01 | 24.3422 | 54.5636 | 24.3422 | 54.5636 | 0 | 0 | مدينة محمد بن زايد - Z13_01 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
257 | Zayed | مدينة محمد بن زايد - Z36 | 24.3356 | 54.5782 | 24.3356 | 54.5782 | 0 | 0 | مدينة محمد بن زايد - Z36 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
258 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2868 | 54.5897 | 24.2868 | 54.5897 | 0 | 0 | مصفح - جرن يافور - المفرق الصناعية | TRUE | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
259 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2818 | 54.5849 | 24.2818 | 54.5849 | 0 | 0 | مصفح - جرن يافور - المفرق الصناعية | TRUE | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
260 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.256 | 54.6342 | 24.256 | 54.6342 | 0 | 0 | مصفح - جرن يافور - المفرق الصناعية | TRUE | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
261 | Zayed | ربدان - RB1 | 24.4179 | 54.4945 | 24.4179 | 54.4945 | 0 | 0 | ربدان - RB1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
262 | Zayed | ربدان - RB2 | 24.4149 | 54.4926 | 24.4149 | 54.4926 | 0 | 0 | ربدان - RB2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
263 | Zayed | ربدان - RB7 | 24.407 | 54.515 | 24.407 | 54.515 | 0 | 0 | ربدان - RB7 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
264 | Zayed | ربدان - RB14 | 24.4024 | 54.4879 | 24.4024 | 54.4879 | 0 | 0 | ربدان - RB14 | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
265 | Zayed | ربدان - RB28 | 24.3984 | 54.5024 | 24.3984 | 54.5024 | 0 | 0 | ربدان - RB28 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | [6 empty] | AECOM | Yes
266 | Zayed | ربدان - RB28 | 24.3947 | 54.5009 | 24.3947 | 54.5009 | 0 | 0 | ربدان - RB28 | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
267 | Zayed | المخرج الى طريق دبي - من طريق أبو ظبي العين | 24.4142 | 54.5066 | 24.4142 | 54.5066 | 0 | 0 | المخرج الى طريق دبي - من طريق أبو ظبي العين | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-25 | IDAS Review Phase | [5 empty] | Parsons | Yes
268 | Zayed | المخرج الى شارع الشيخ زايد - ساس النخل | 24.4193 | 54.5136 | 24.4193 | 54.5136 | 0 | 0 | المخرج الى شارع الشيخ زايد - ساس النخل | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-03 | Contractor | [5 empty] | Parsons | Yes
269 | Zayed | SW17_مدينة خليفة - 01 | 24.4116 | 54.5139 | 24.4116 | 54.5139 | 0 | 0 | SW17_مدينة خليفة - 01 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
270 | Zayed | مدينة خليفة - SW17 - وطني | 24.4163 | 54.5465 | 24.4163 | 54.5465 | 0 | 0 | مدينة خليفة - SW17 - وطني | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
271 | Zayed | مدينة خليفة - SW17 - وطني | 24.4148 | 54.5432 | 24.4148 | 54.5432 | 0 | 0 | مدينة خليفة - SW17 - وطني | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
272 | Zayed | مدينة خليفة - SW17 - وطني | 24.4144 | 54.5405 | 24.4144 | 54.5405 | 0 | 0 | مدينة خليفة - SW17 - وطني | TRUE | High | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
273 | Zayed | مدينة خليفة | 24.4145 | 54.5393 | 24.4145 | 54.5393 | 0 | 0 | مدينة خليفة | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-13 | Contractor | [5 empty] | Parsons | Yes
274 | Zayed | مدينة خليفة | 24.4144 | 54.5411 | 24.4144 | 54.5411 | 0 | 0 | مدينة خليفة | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0
275 | Zayed | مدينة خليفة - SW13 | 24.4132 | 54.5576 | 24.4132 | 54.5576 | 0 | 0 | مدينة خليفة - SW13 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
276 | Zayed | مدينة خليفة - SW2 | 24.4197 | 54.5586 | 24.4197 | 54.5586 | 0 | 0 | مدينة خليفة - SW2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
277 | Zayed | مدينة خليفة - SW3 | 24.4147 | 54.5641 | 24.4147 | 54.5641 | 0 | 0 | مدينة خليفة - SW3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
278 | Zayed | مدينة خليفة - SW4 | 24.41 | 54.5645 | 24.41 | 54.5645 | 0 | 0 | مدينة خليفة - SW4 | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
279 | Zayed | مدينة خليفة - شارع المطار بالاتجاه لأبو ظبي | 24.3978 | 54.5738 | 24.3978 | 54.5738 | 0 | 0 | مدينة خليفة - شارع المطار بالاتجاه لأبو ظبي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-10-17 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
280 | Zayed | مدينة خليفة - SE3 | 24.4195 | 54.5683 | 24.4195 | 54.5683 | 0 | 0 | مدينة خليفة - SE3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
281 | Zayed | مدينة خليفة - SE13 | 24.4184 | 54.5832 | 24.4184 | 54.5832 | 0 | 0 | مدينة خليفة - SE13 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
282 | Zayed | مدينة خليفة - SE24 | 24.414 | 54.5885 | 24.414 | 54.5885 | 0 | 0 | مدينة خليفة - SE24 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
283 | Zayed | مدينة خليفة - SE26 | 24.4092 | 54.5924 | 24.4092 | 54.5924 | 0 | 0 | مدينة خليفة - SE26 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
284 | Zayed | مدينة خليفة - SE6 | 24.4016 | 54.5785 | 24.4016 | 54.5785 | 0 | 0 | مدينة خليفة - SE6 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
285 | Zayed | مدينة خليفة - SE16 | 24.4027 | 54.5843 | 24.4027 | 54.5843 | 0 | 0 | مدينة خليفة - SE16 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
286 | Zayed | مدينة خليفة - SE26 | 24.4045 | 54.592 | 24.4045 | 54.5924 | Same location different coordinates |  | مدينة خليفة - SE26 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
287 | Zayed | مدينة خليفة - SE36 | 24.407 | 54.6048 | 24.407 | 54.6048 | 0 | 0 | مدينة خليفة - SE36 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
288 | Zayed | مدينة خليفة - SE38 | 24.4124 | 54.6033 | 24.4124 | 54.6033 | 0 | 0 | مدينة خليفة - SE38 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
289 | Zayed | مدينة خليفة - SE35 | 24.4158 | 54.6016 | 24.4158 | 54.6016 | 0 | 0 | مدينة خليفة - SE35 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
290 | Zayed | مدينة خليفة - SE44 | 24.43 | 54.5817 | 24.43 | 54.5817 | 0 | 0 | مدينة خليفة - SE44 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
291 | Zayed | مدينة خليفة - SE47 | 24.4365 | 54.5869 | 24.4365 | 54.5869 | 0 | 0 | مدينة خليفة - SE47 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
292 | Zayed | مدينة خليفة - SE47 | 24.44 | 54.5905 | 24.44 | 54.5905 | 0 | 0 | مدينة خليفة - SE47 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
293 | Zayed | مدينة خليفة - SE40 | 24.4264 | 54.6002 | 24.4264 | 54.6002 | 0 | 0 | مدينة خليفة - SE40 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
294 | Zayed | مدينة خليفة - الراحة - RBW13 | 24.4343 | 54.5597 | 24.4343 | 54.5597 | 0 | 0 | مدينة خليفة - الراحة - RBW13 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
295 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4384 | 54.5776 | 24.4384 | 54.5776 | 0 | 0 | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-14 |  | 2026-10-26 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
296 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4427 | 54.5933 | 24.4427 | 54.5933 | 0 | 0 | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-21 |  | 2026-10-31 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
297 | Zayed | مدينة شخبوط - طريق سويحان باتجاه الى طريق المفرق | 24.4094 | 54.6638 | 24.4094 | 54.6638 | 0 | 0 | مدينة شخبوط - طريق سويحان باتجاه الى طريق المفرق | TRUE | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 0 | 940000 | 0 | 60000 | [6 empty] | Yes | D |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-13 | Contractor | [5 empty] | Parsons | Yes
298 | Zayed | مدينة زايد - MZ6 | 24.3781 | 54.5951 | 24.3781 | 54.5951 | 0 | 0 | مدينة زايد - MZ6 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
299 | Zayed | مدينة زايد - MZ6 | 24.3826 | 54.6024 | 24.3826 | 54.6024 | 0 | 0 | مدينة زايد - MZ6 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
300 | Zayed | مدينة زايد - MZ7 | 24.3867 | 54.6059 | 24.3867 | 54.6059 | 0 | 0 | مدينة زايد - MZ7 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
301 | Zayed | مدينة زايد - MZ7 | 24.3819 | 54.6087 | 24.3819 | 54.6087 | 0 | 0 | مدينة زايد - MZ7 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
302 | Zayed | مدينة زايد - MZ10 | 24.3691 | 54.6046 | 24.3691 | 54.6046 | 0 | 0 | مدينة زايد - MZ10 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
303 | Zayed | مدينة زايد - MZ1 | 24.3657 | 54.6032 | 24.3657 | 54.6032 | 0 | 0 | مدينة زايد - MZ1 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
304 | Zayed | مدينة زايد - MZ1 | 24.3604 | 54.6 | 24.3604 | 54.6 | 0 | 0 | مدينة زايد - MZ1 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
305 | Zayed | مدينة زايد - MZ8 | 24.3892 | 54.6189 | 24.3892 | 54.6189 | 0 | 0 | مدينة زايد - MZ8 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
306 | Zayed | مدينة زايد - MZ9 | 24.3922 | 54.6221 | 24.3922 | 54.6221 | 0 | 0 | مدينة زايد - MZ9 | TRUE | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
307 | Zayed | مدينة شخبوط - MSH7 | 24.349 | 54.6085 | 24.349 | 54.6085 | 0 | 0 | مدينة شخبوط - MSH7 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
308 | Zayed | مدينة شخبوط - MSH7 | 24.3519 | 54.611 | 24.3519 | 54.611 | 0 | 0 | مدينة شخبوط - MSH7 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
309 | Zayed | مدينة شخبوط - MSH7 | 24.348 | 54.6131 | 24.348 | 54.6131 | 0 | 0 | مدينة شخبوط - MSH7 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
310 | Zayed | مدينة شخبوط - MSH5 | 24.35 | 54.6163 | 24.35 | 54.6163 | 0 | 0 | مدينة شخبوط - MSH5 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
311 | Zayed | مدينة شخبوط - MSH5 | 24.3503 | 54.6186 | 24.3503 | 54.6186 | 0 | 0 | مدينة شخبوط - MSH5 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
312 | Zayed | مدينة شخبوط - MSH5 | 24.3443 | 54.6165 | 24.3443 | 54.6165 | 0 | 0 | مدينة شخبوط - MSH5 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
313 | Zayed | مدينة شخبوط - MSH3 | 24.3453 | 54.6214 | 24.3453 | 54.6214 | 0 | 0 | مدينة شخبوط - MSH3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
314 | Zayed | مدينة شخبوط - MSH1 | 24.3373 | 54.6237 | 24.3373 | 54.6237 | 0 | 0 | مدينة شخبوط - MSH1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
315 | Zayed | مدينة شخبوط - MSH2 | 24.3423 | 54.6272 | 24.3423 | 54.6272 | 0 | 0 | مدينة شخبوط - MSH2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
316 | Zayed | مدينة شخبوط - MSH1 | 24.3436 | 54.6316 | 24.3436 | 54.6316 | 0 | 0 | مدينة شخبوط - MSH1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
317 | Zayed | مدينة شخبوط - MSH15 | 24.3583 | 54.637 | 24.3583 | 54.637 | 0 | 0 | مدينة شخبوط - MSH15 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
318 | Zayed | مدينة شخبوط - MSH14 | 24.3643 | 54.6345 | 24.3643 | 54.6345 | 0 | 0 | مدينة شخبوط - MSH14 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
319 | Zayed | مدينة شخبوط - MSH17 | 24.3697 | 54.6488 | 24.3697 | 54.6488 | 0 | 0 | مدينة شخبوط - MSH17 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
320 | Zayed | مدينة شخبوط - MSH19 | 24.3727 | 54.6467 | 24.3727 | 54.6467 | 0 | 0 | مدينة شخبوط - MSH19 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
321 | Zayed | مدينة شخبوط - MSH19 | 24.3721 | 54.6428 | 24.3721 | 54.6428 | 0 | 0 | مدينة شخبوط - MSH19 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
322 | Zayed | مدينة شخبوط - MSH23 | 24.3774 | 54.6306 | 24.3774 | 54.6306 | 0 | 0 | مدينة شخبوط - MSH23 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
323 | Zayed | مدينة شخبوط - MSH20 | 24.3756 | 54.6454 | 24.3756 | 54.6454 | 0 | 0 | مدينة شخبوط - MSH20 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
324 | Zayed | مدينة شخبوط - MSH24 | 24.388 | 54.6396 | 24.388 | 54.6396 | 0 | 0 | مدينة شخبوط - MSH24 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
325 | Al Wathbah | بني ياس - EB1_03 | 24.3174 | 54.6355 | 24.3174 | 54.6355 | 0 | 0 | بني ياس - EB1_03 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
326 | Al Wathbah | بني ياس - EB6_01 | 24.3068 | 54.6446 | 24.3068 | 54.6446 | 0 | 0 | بني ياس - EB6_01 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
327 | Al Wathbah | بني ياس - EB7_B | 24.2999 | 54.6381 | 24.2999 | 54.6381 | 0 | 0 | بني ياس - EB7_B | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
328 | Al Wathbah | بني ياس -EB10_A | 24.293 | 54.6517 | 24.293 | 54.6517 | 0 | 0 | بني ياس -EB10_A | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
329 | Al Wathbah | بني ياس -WB3_A | 24.2888 | 54.6342 | 24.2888 | 54.6342 | 0 | 0 | بني ياس -WB3_A | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
330 | Al Wathbah | بني ياس -EB11_01 | 24.3089 | 54.6456 | 24.3089 | 54.6456 | 0 | 0 | بني ياس -EB11_01 | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
331 | Al Wathbah | بني ياس -EB1_04 | 24.3256 | 54.6376 | 24.3256 | 54.6376 | 0 | 0 | بني ياس -EB1_04 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
332 | Al Wathbah | الشوامخ - SHM10 | 24.3431 | 54.6493 | 24.3431 | 54.6493 | 0 | 0 | الشوامخ - SHM10 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
333 | Al Wathbah | الشوامخ - SHM9 | 24.3498 | 54.6551 | 24.3498 | 54.6551 | 0 | 0 | الشوامخ - SHM9 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
334 | Al Wathbah | الشوامخ - SHM9 | 24.3535 | 54.6619 | 24.3535 | 54.6619 | 0 | 0 | الشوامخ - SHM9 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
335 | Al Wathbah | الشوامخ - SHM3 | 24.362 | 54.6552 | 24.362 | 54.6552 | 0 | 0 | الشوامخ - SHM3 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
336 | Al Wathbah | الشوامخ - SHM2 | 24.3681 | 54.6603 | 24.3681 | 54.6603 | 0 | 0 | الشوامخ - SHM2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
337 | Al Wathbah | الشوامخ - SHM1 | 24.3771 | 54.6636 | 24.3771 | 54.6636 | 0 | 0 | الشوامخ - SHM1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
338 | Al Wathbah | الشامخة - SH10 | 24.3969 | 54.704 | 24.3969 | 54.704 | 0 | 0 | الشامخة - SH10 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
339 | Al Wathbah | الشامخة - SH11 | 24.3834 | 54.7167 | 24.3834 | 54.7167 | 0 | 0 | الشامخة - SH11 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
340 | Al Wathbah | الشامخة - SH14 | 24.3692 | 54.7154 | 24.3692 | 54.7154 | 0 | 0 | الشامخة - SH14 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
341 | Al Wathbah | مدينة الرياض - RD26 | 24.3287 | 54.7804 | 24.3287 | 54.7804 | 0 | 0 | مدينة الرياض - RD26 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 3 | 0 | 0 | 6480 | 0 | 0 | 6480 | 77760 | 291600 | 369360 | 0 | 0 | 0 | 0 | 750000 | 0
342 | Al Wathbah | مدينة الرياض - RD32 | 24.3325 | 54.7441 | 24.3325 | 54.7441 | 0 | 0 | مدينة الرياض - RD32 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
343 | Al Wathbah | مدينة الرياض - RD11 | 24.3562 | 54.7382 | 24.3562 | 54.7382 | 0 | 0 | مدينة الرياض - RD11 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
344 | Al Wathbah | مدينة الرياض - RD7 | 24.3769 | 54.7572 | 24.3769 | 54.7572 | 0 | 0 | مدينة الرياض - RD7 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
345 | Al Shahama | الفلاح - 1E | 24.433 | 54.7399 | 24.433 | 54.7399 | 0 | 0 | الفلاح - 1E | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0
346 | Al Shahama | الفلاح - 1E | 24.431 | 54.7432 | 24.431 | 54.7432 | 0 | 0 | الفلاح - 1E | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0
347 | Al Shahama | الفلاح - 1E | 24.4412 | 54.7333 | 24.4412 | 54.7333 | 0 | 0 | الفلاح - 1E | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0
348 | Al Shahama | الفلاح - 1D | 24.4464 | 54.7381 | 24.4464 | 54.7381 | 0 | 0 | الفلاح - 1D | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0
349 | Al Shahama | الفلاح - 1C | 24.4577 | 54.7377 | 24.4577 | 54.7377 | 0 | 0 | الفلاح - 1C | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0
350 | Al Shahama | الفلاح - 1B | 24.4563 | 54.7178 | 24.4563 | 54.7178 | 0 | 0 | الفلاح - 1B | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0
351 | Al Shahama | جزيرة ياس - YN3 | 24.5108 | 54.6005 | 24.5108 | 54.6005 | 0 | 0 | جزيرة ياس - YN3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0
352 | Al Shahama | جزيرة ياس - YN3 | 24.504 | 54.596 | 24.504 | 54.596 | 0 | 0 | جزيرة ياس - YN3 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0
353 | Al Shahama | جزيرة ياس - YN7 | 24.4977 | 54.6225 | 24.4977 | 54.6225 | 0 | 0 | جزيرة ياس - YN7 | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
354 | Al Shahama | الباهية - Al Shahamah Old | 24.5421 | 54.6796 | 24.5421 | 54.6796 | 0 | 0 | الباهية - Al Shahamah Old | TRUE | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
355 | Al Shahama | الباهية - Al Bahyah New | 24.546 | 54.6293 | 24.546 | 54.6293 | 0 | 0 | الباهية - Al Bahyah New | TRUE | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
356 | Al Shahama | الباهية - Al Bahyah New | 24.5467 | 54.6367 | 24.5467 | 54.6367 | 0 | 0 | الباهية - Al Bahyah New | TRUE | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
357 | Al Shahama | الباهية - Al Shahamah Old | 24.5584 | 54.6798 | 24.5584 | 54.6798 | 0 | 0 | الباهية - Al Shahamah Old | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
358 | Al Shahama | الرحبة - Rahbah_A | 24.5655 | 54.6872 | 24.5655 | 54.6872 | 0 | 0 | الرحبة - Rahbah_A | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
359 | Al Shahama | الرحبة - Rahbah_A | 24.5663 | 54.6859 | 24.5663 | 54.6859 | 0 | 0 | الرحبة - Rahbah_A | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
360 | Al Shahama | الرحبة - Rahbah_A | 24.5695 | 54.6862 | 24.5695 | 54.6862 | 0 | 0 | الرحبة - Rahbah_A | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
361 | Al Shahama | الرحبة - Rahbah_C | 24.5769 | 54.6871 | 24.5769 | 54.6871 | 0 | 0 | الرحبة - Rahbah_C | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
362 | Al Shahama | الرحبة - Rahbah_G | 24.6021 | 54.6998 | 24.6021 | 54.6998 | 0 | 0 | الرحبة - Rahbah_G | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
363 | Al Shahama | الرحبة - السمحة | 24.6241 | 54.7104 | 24.6241 | 54.7104 | 0 | 0 | الرحبة - السمحة | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0
364 | Al Shahama | السمحة - Al Samhah East | 24.6542 | 54.7605 | 24.6542 | 54.7605 | 0 | 0 | السمحة - Al Samhah East | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
365 | Al Shahama | السمحة - Al Samhah East | 24.661 | 54.7647 | 24.661 | 54.7647 | 0 | 0 | السمحة - Al Samhah East | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
366 | Al Shahama | السمحة -Al Samhah East Old | 24.6718 | 54.7741 | 24.6718 | 54.7741 | 0 | 0 | السمحة -Al Samhah East Old | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
367 | Al Shahama | السمحة -Al Samhah East Old | 24.6781 | 54.7753 | 24.6781 | 54.7753 | 0 | 0 | السمحة -Al Samhah East Old | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
368 | Al Shahama | السمحة -Samhah_V | 24.6712 | 54.7479 | 24.6712 | 54.7479 | 0 | 0 | السمحة -Samhah_V | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
369 | Al Shahama | السمحة -Samhah_T | 24.6716 | 54.7581 | 24.6716 | 54.7581 | 0 | 0 | السمحة -Samhah_T | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
370 | Al Shahama | السمحة -Al Samhah West Old_ | 24.6859 | 54.7676 | 24.6859 | 54.7676 | 0 | 0 | السمحة -Al Samhah West Old_ | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
371 | Al Wathbah | Qasr Al Wathbah South | 24.1767 | 54.7566 | 24.1767 | 54.7566 | 0 | 0 | Qasr Al Wathbah South | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
372 | Al Wathbah | Al Dhafrah East | 24.2383 | 54.6337 | 24.2383 | 54.6337 | 0 | 0 | Al Dhafrah East | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
373 | Al Wathbah | Al Nahdah Al Askariah | 24.2607 | 54.7083 | 24.2607 | 54.7083 | 0 | 0 | Al Nahdah Al Askariah | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
374 | Al Wathbah | Al Nahdah Al Askariah | 24.2634 | 54.7013 | 24.2634 | 54.7013 | 0 | 0 | Al Nahdah Al Askariah | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
375 | Al Wathbah | Al Nahdah Al Askariah | 24.2677 | 54.6937 | 24.2677 | 54.6937 | 0 | 0 | Al Nahdah Al Askariah | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
376 | Island | جوار نيشن تاور | 24.4633 | 54.3288 | 24.4633 | 54.3288 | 0 | 0 | جوار نيشن تاور | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
377 | Island | شارع الاواصر | 24.4656 | 54.3357 | 24.4656 | 54.3357 | 0 | 0 | شارع الاواصر | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
378 | Island | شارع الاواصر | 24.4661 | 54.3366 | 24.4661 | 54.3366 | 0 | 0 | شارع الاواصر | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
379 | Island | ابراج الساحل | 24.4664 | 54.335 | 24.4664 | 54.335 | 0 | 0 | ابراج الساحل | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
380 | Island | اسبنس الكورنيش | 24.4659 | 54.3345 | 24.4659 | 54.3345 | 0 | 0 | اسبنس الكورنيش | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
381 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4696 | 54.3373 | 24.4696 | 54.3373 | 0 | 0 | مواقف مجمع سلامه السكني الكورنيش | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
382 | Island | خلف مدرسه سابس العالميه | 24.4628 | 54.3411 | 24.4628 | 54.3411 | 0 | 0 | خلف مدرسه سابس العالميه | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
383 | Island | خلف مدرسه سابس العالميه | 24.4626 | 54.3407 | 24.4626 | 54.3407 | 0 | 0 | خلف مدرسه سابس العالميه | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
384 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4695 | 54.3377 | 24.4695 | 54.3377 | 0 | 0 | مواقف مجمع سلامه السكني الكورنيش | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
385 | Island | كليه ابو ظبي للاداره | 24.4848 | 54.3536 | 24.4848 | 54.3536 | 0 | 0 | كليه ابو ظبي للاداره | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
386 | Island | شارع المطار مدخل قصر الحصن | 24.4835 | 54.358 | 24.4835 | 54.358 | 0 | 0 | شارع المطار مدخل قصر الحصن | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
387 | Island | صيدليه الملا منطقه الخالديه | 24.4792 | 54.3579 | 24.4792 | 54.3579 | 0 | 0 | صيدليه الملا منطقه الخالديه | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
388 | Island | مدينه خليفه الطبيه | 24.4705 | 54.364 | 24.4705 | 54.364 | 0 | 0 | مدينه خليفه الطبيه | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 0 | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 147744 | 0 | 0 | 0 | 0 | 0 | 0
389 | Island | مجلس المنهل | 24.4691 | 54.3587 | 24.4691 | 54.3587 | 0 | 0 | مجلس المنهل | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
390 | Island | مجمع الكرامه | 24.4641 | 54.3728 | 24.4641 | 54.3728 | 0 | 0 | مجمع الكرامه | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | IDAS Review Phase | [5 empty] | AECOM | Yes
391 | Island | خلف فندق فلايجيو شارع المطار | 24.4653 | 54.3744 | 24.4653 | 54.3744 | 0 | 0 | خلف فندق فلايجيو شارع المطار | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
392 | Island | خلف فندق فلايجيو شارع المطار | 24.4645 | 54.3745 | 24.4645 | 54.3745 | 0 | 0 | خلف فندق فلايجيو شارع المطار | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
393 | Island | شارع الشيخه فاطمه اتجاه البطين تقاطع شارع المطار | 24.4636 | 54.3777 | 24.4636 | 54.3777 | 0 | 0 | شارع الشيخه فاطمه اتجاه البطين تقاطع شارع المطار | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 298080 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
394 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4646 | 54.3757 | 24.4646 | 54.3757 | 0 | 0 | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
395 | Island | تقاطع الشيخه فاطمه مع شارع الكرامه | 24.4597 | 54.3733 | 24.4597 | 54.3733 | 0 | 0 | تقاطع الشيخه فاطمه مع شارع الكرامه | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
396 | Island | صيدليه المركز الامريكي جوار مجمع ليوا | 24.4575 | 54.371 | 24.4575 | 54.371 | 0 | 0 | صيدليه المركز الامريكي جوار مجمع ليوا | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
397 | Island | خلف المركز الامريكي | 24.4551 | 54.3725 | 24.4551 | 54.3725 | 0 | 0 | خلف المركز الامريكي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
398 | Island | خلف مركز القاضي الطبي | 24.4421 | 54.3678 | 24.4421 | 54.3678 | 0 | 0 | خلف مركز القاضي الطبي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
399 | Island | دوار الفروسيه 1 | 24.4425 | 54.3744 | 24.4425 | 54.3744 | 0 | 0 | دوار الفروسيه 1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
400 | Island | جوار مجمع حدائق المشرف | 24.4431 | 54.3734 | 24.4431 | 54.3734 | 0 | 0 | جوار مجمع حدائق المشرف | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
401 | Island | دوار الفروسيه 2 | 24.4465 | 54.3757 | 24.4465 | 54.3757 | 0 | 0 | دوار الفروسيه 2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
402 | Island | اسفل جسر شارع الخليج العربي | 24.4351 | 54.3768 | 24.4351 | 54.3768 | 0 | 0 | اسفل جسر شارع الخليج العربي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
403 | Island | جوار مبني الهويه والجنسيه 1 | 24.4473 | 54.3897 | 24.4473 | 54.3897 | 0 | 0 | جوار مبني الهويه والجنسيه 1 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
404 | Island | جوار مبني الهويه والجنسيه 2 | 24.4477 | 54.3886 | 24.4477 | 54.3886 | 0 | 0 | جوار مبني الهويه والجنسيه 2 | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
405 | Island | مسجد خالد بن الوليد منطقه البطين | 24.4514 | 54.3551 | 24.4514 | 54.3551 | 0 | 0 | مسجد خالد بن الوليد منطقه البطين | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
406 | Island | مرسي البطين جوار مرسى اليخوت 2 | 24.4514 | 54.3368 | 24.4514 | 54.3368 | 0 | 0 | مرسي البطين جوار مرسى اليخوت 2 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
407 | Island | حديقه ام الامارات 2 | 24.4544 | 54.3818 | 24.4544 | 54.3818 | 0 | 0 | حديقه ام الامارات 2 | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
408 | Island | جسر شارع الشيخ خليفه بن زايد اتجاه السعديات | 24.5151 | 54.3925 | 24.5151 | 54.3925 | 0 | 0 | جسر شارع الشيخ خليفه بن زايد اتجاه السعديات | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
409 | Island | مينا زايد تابع للمطور | 24.5322 | 54.3661 | 24.5322 | 54.3661 | 0 | 0 | مينا زايد | FALSE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
410 | Island | مينا زايد تابع للمطور | 24.5221 | 54.3682 | 24.5221 | 54.3682 | 0 | 0 | مينا زايد | FALSE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
411 | Island | مينا زايد تابع للمطور | 24.5136 | 54.3685 | 24.5136 | 54.3685 | 0 | 0 | مينا زايد | FALSE | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
412 | Island | فندق هلا ارجان- الزاهية | 24.502 | 54.377 | 24.502 | 54.377 | 0 | 0 | فندق هلا ارجان- الزاهية | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
413 | Island | مواقف سيارات خلف فندق نهال | 24.4982 | 54.3727 | 24.4982 | 54.3727 | 0 | 0 | مواقف سيارات خلف فندق نهال | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
414 | Island | مستشفي الكورنيش | 24.5013 | 54.3696 | 24.5013 | 54.3693 | Same location different coordinates |  | مستشفي الكورنيش | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
415 | Island | خلف المركز الاجتماعي الهندي | 24.5088 | 54.3794 | 24.5088 | 54.3794 | 0 | 0 | خلف المركز الاجتماعي الهندي | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
416 | Island | مواقف سيارات سوق السجاد | 24.5116 | 54.3834 | 24.5116 | 54.3834 | 0 | 0 | مواقف سيارات سوق السجاد | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Hand over phase | N/A |  |  |  |  | AECOM | Yes
417 | Island | مواقف سيارات سوق السجاد | 24.5121 | 54.3825 | 24.5121 | 54.3825 | 0 | 0 | مواقف سيارات سوق السجاد | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
418 | Island | شارع خليفه بن زايد تقاطع شارع المينا | 24.5091 | 54.3824 | 24.5091 | 54.3824 | 0 | 0 | شارع خليفه بن زايد تقاطع شارع المينا | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
419 | Island | جسر الماريا شارع حمدان بن محمد | 24.5021 | 54.3813 | 24.5021 | 54.3813 | 0 | 0 | جسر الماريا شارع حمدان بن محمد | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
420 | Island | شارع السلام قبل تقاطع شارع حمدان | 24.4956 | 54.374 | 24.4956 | 54.374 | 0 | 0 | شارع السلام قبل تقاطع شارع حمدان | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
421 | Island | جوار بنك ابو ظبي الاول - شارع السلام | 24.4919 | 54.378 | 24.4919 | 54.378 | 0 | 0 | جوار بنك ابو ظبي الاول - شارع السلام | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
422 | Island | شارع الريم جوار مطعم جاد | 24.4902 | 54.3807 | 24.4902 | 54.3807 | 0 | 0 | شارع الريم جوار مطعم جاد | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
423 | Island | جوار فندق جنه شارع الفلاح | 24.489 | 54.3831 | 24.489 | 54.3831 | 0 | 0 | جوار فندق جنه شارع الفلاح | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
424 | Island | جوار مجمع طاقه 1 | 24.4846 | 54.3788 | 24.4846 | 54.3788 | 0 | 0 | جوار مجمع طاقه 1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
425 | Island | جوار مجمع طاقه 2 | 24.4835 | 54.3779 | 24.4835 | 54.3779 | 0 | 0 | جوار مجمع طاقه 2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
426 | Island | مواقف شارع السلام محال تاجير السيارات 1 | 24.486 | 54.3816 | 24.486 | 54.3816 | 0 | 0 | مواقف شارع السلام محال تاجير السيارات 1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
427 | Island | مواقف شارع السلام محال تاجير السيارات 2 | 24.485 | 54.3821 | 24.485 | 54.3821 | 0 | 0 | مواقف شارع السلام محال تاجير السيارات 2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
428 | Island | مواقف حافلات مدرسه الشيخه فاطمه 1 | 24.4818 | 54.3799 | 24.4818 | 54.3799 | 0 | 0 | مواقف حافلات مدرسه الشيخه فاطمه 1 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
429 | Island | مواقف حافلات مدرسه الشيخه فاطمه 2 | 24.4823 | 54.3796 | 24.4823 | 54.3796 | 0 | 0 | مواقف حافلات مدرسه الشيخه فاطمه 2 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
430 | Island | جوار السفاره السريلانكيه | 24.4815 | 54.3848 | 24.4815 | 54.3848 | 0 | 0 | جوار السفاره السريلانكيه | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
431 | Island | خلف مسجد حمد خليفه الخلفان | 24.4805 | 54.3823 | 24.4805 | 54.3823 | 0 | 0 | خلف مسجد حمد خليفه الخلفان | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
432 | Island | مواقف مستشفي برجيل شارع الدفاع | 24.4785 | 54.3816 | 24.4785 | 54.3816 | 0 | 0 | مواقف مستشفي برجيل شارع الدفاع | TRUE | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
433 | Island | جوار مدرسه الايمان الخاصه | 24.4892 | 54.3671 | 24.4892 | 54.3671 | 0 | 0 | جوار مدرسه الايمان الخاصه | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
434 | Island | جوار مسجد عبد الرحيم خوري | 24.4859 | 54.3712 | 24.4859 | 54.3712 | 0 | 0 | جوار مسجد عبد الرحيم خوري | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
435 | Island | شارع المرور مقابل سوق الذهب | 24.4847 | 54.3667 | 24.4847 | 54.3667 | 0 | 0 | شارع المرور مقابل سوق الذهب | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
436 | Island | شارع المرور مقابل سوق الذهب | 24.4859 | 54.366 | 24.4859 | 54.366 | 0 | 0 | شارع المرور مقابل سوق الذهب | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
437 | Island | مواقف سوق الذهب | 24.4843 | 54.3644 | 24.4843 | 54.3644 | 0 | 0 | مواقف سوق الذهب | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
438 | Island | تقاطع شارع المرور مع شارع الفلاح | 24.4787 | 54.3697 | 24.4787 | 54.3697 | 0 | 0 | تقاطع شارع المرور مع شارع الفلاح | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
439 | Island | فندق النخيل شارع المرور | 24.4775 | 54.3715 | 24.4775 | 54.3715 | 0 | 0 | فندق النخيل شارع المرور | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
440 | Island | خلف جراند الامارات شارع المرور | 24.4731 | 54.3725 | 24.4731 | 54.3725 | 0 | 0 | خلف جراند الامارات شارع المرور | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
441 | Island | جوار كنتاكي شارع المطار | 24.4733 | 54.3683 | 24.4733 | 54.3683 | 0 | 0 | جوار كنتاكي شارع المطار | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
442 | Island | فندق ماريوت شارع المطار | 24.4704 | 54.3701 | 24.4704 | 54.3701 | 0 | 0 | فندق ماريوت شارع المطار | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
443 | Island | منطقه ال نهيان " محلات الشوكلاته " | 24.4726 | 54.3803 | 24.4726 | 54.3803 | 0 | 0 | منطقه ال نهيان " محلات الشوكلاته " | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
444 | Island | مجمع الكرامه | 24.4634 | 54.372 | 24.4634 | 54.372 | 0 | 0 | مجمع الكرامه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
445 | Island | مبني تدوير " الاشغال سابقا " | 24.4613 | 54.3749 | 24.4613 | 54.3749 | 0 | 0 | مبني تدوير " الاشغال سابقا " | TRUE | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
446 | Island | شارع ماء سلوان مقابل صحه مستشفي خليفه | 24.4674 | 54.3689 | 24.4674 | 54.3689 | 0 | 0 | شارع ماء سلوان مقابل صحه مستشفي خليفه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
447 | Island | مجمع الكرامه | 24.4625 | 54.3709 | 24.4625 | 54.3709 | 0 | 0 | مجمع الكرامه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
448 | Island | شارع الكرامه | 24.4613 | 54.3699 | 24.4613 | 54.3699 | 0 | 0 | شارع الكرامه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
449 | Island | روضه ابو ظبي للاطفال | 24.4634 | 54.3673 | 24.4634 | 54.3673 | 0 | 0 | روضه ابو ظبي للاطفال | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
450 | Island | مطعم المزراب الشعبي | 24.4543 | 54.3863 | 24.4543 | 54.3863 | 0 | 0 | مطعم المزراب الشعبي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
451 | Island | نادي الجزيره | 24.4513 | 54.3925 | 24.4513 | 54.3925 | 0 | 0 | نادي الجزيره | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 0 | 0
452 | Island | خلف جامعه خليفه | 24.4449 | 54.3989 | 24.4449 | 54.3989 | 0 | 0 | خلف جامعه خليفه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
453 | Island | مسجد حمزه بن عبد المطلب | 24.4437 | 54.4062 | 24.4437 | 54.4062 | 0 | 0 | مسجد حمزه بن عبد المطلب | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
454 | Island | حديقه قاف " حديقه الملك حمد " | 24.4357 | 54.4114 | 24.4357 | 54.4114 | 0 | 0 | حديقه قاف " حديقه الملك حمد " | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
455 | Island | خياط البيت السعيد - شارع المرور | 24.4379 | 54.4136 | 24.4379 | 54.4136 | 0 | 0 | خياط البيت السعيد - شارع المرور | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
456 | Island | مركز فحص المركبات - ادنوك شارع المرور | 24.4355 | 54.4168 | 24.4355 | 54.4168 | 0 | 0 | مركز فحص المركبات - ادنوك شارع المرور | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
457 | Island | كليه الشرطه | 24.4378 | 54.4193 | 24.4378 | 54.4193 | 0 | 0 | كليه الشرطه | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
458 | Island | خلف مسجد سيف بن حارب المنصوري | 24.4389 | 54.4185 | 24.4389 | 54.4185 | 0 | 0 | خلف مسجد سيف بن حارب المنصوري | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
459 | Island | الدفاع المدني - القبيسات | 24.425 | 54.4186 | 24.425 | 54.4186 | 0 | 0 | الدفاع المدني - القبيسات | TRUE | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
460 | Island | مسجد السيد يوسف الهاشمي | 24.4245 | 54.4151 | 24.4245 | 54.4151 | 0 | 0 | مسجد السيد يوسف الهاشمي | TRUE | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Quick Wins | Maintenance | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Hand over phase | N/A |  |  |  |  | AECOM | Yes
461 | Island | شارع سلامه بنت بطيء | 24.4333 | 54.4034 | 24.4333 | 54.4034 | 0 | 0 | شارع سلامه بنت بطيء | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
462 | Island | شارع المدرسه | 24.4315 | 54.4094 | 24.4315 | 54.4094 | 0 | 0 | شارع المدرسه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
463 | Island | مقابل اكادميه ابو ظبي للسباحه | 24.4267 | 54.4132 | 24.4267 | 54.4132 | 0 | 0 | مقابل اكادميه ابو ظبي للسباحه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
464 | Island | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | 24.4251 | 54.4099 | 24.4251 | 54.4099 | 0 | 0 | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
465 | Island | شرق 43 | 24.4397 | 54.4297 | 24.4397 | 54.4297 | 0 | 0 | شرق 43 | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
466 | Island | جوار مسجد جبريل | 24.4254 | 54.4254 | 24.4254 | 54.4254 | 0 | 0 | جوار مسجد جبريل | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
467 | Island | شارع الخرطوم - مدرسه الريم | 24.4346 | 54.4317 | 24.4346 | 54.4317 | 0 | 0 | شارع الخرطوم - مدرسه الريم | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
468 | Island | منطقه السعاده 1 | 24.4361 | 54.4371 | 24.4361 | 54.4371 | 0 | 0 | منطقه السعاده 1 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
469 | Island | منطقه السعاده 2 | 24.4413 | 54.4351 | 24.4413 | 54.4351 | 0 | 0 | منطقه السعاده 2 | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 0 | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
470 | Island | مجمع اوريكس | 24.4402 | 54.4476 | 24.4402 | 54.4476 | 0 | 0 | مجمع اوريكس | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0
471 | Island | محطه ادنوك - جوار مجمع الظبي | 24.4402 | 54.4518 | 24.4402 | 54.4518 | 0 | 0 | محطه ادنوك - جوار مجمع الظبي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 0 | 0
472 | Island | مدخل قصر المينا مع شارع المروج | 24.4378 | 54.4591 | 24.4378 | 54.4591 | 0 | 0 | مدخل قصر المينا مع شارع المروج | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
473 | Island | دوار مدينه زايد الرياضيه | 24.4192 | 54.4567 | 24.4192 | 54.4567 | 0 | 0 | دوار مدينه زايد الرياضيه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
474 | Island | ملاعب منطقه الروضه " غرب مطار البطين " | 24.4203 | 54.4617 | 24.4203 | 54.4617 | 0 | 0 | ملاعب منطقه الروضه " غرب مطار البطين " | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
475 | Island | منطقه الروضه " الابراج السكنيه " | 24.4178 | 54.4647 | 24.4178 | 54.4647 | 0 | 0 | منطقه الروضه " الابراج السكنيه " | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
476 | Island | حديقه نادي الضباط | 24.404 | 54.475 | 24.404 | 54.475 | 0 | 0 | الطريق الخارجي قرب حديقه نادي الضباط | FALSE | Medium | No | N/A | No | Absense of Drainage Network |  | 4 | 20736 | 77760 | 98496 | 5 | 0 | 0 | 5 | 0 | 0 | 4320 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
477 | Island | اكادميه الرياضه النسائيه | 24.4018 | 54.4696 | 24.4018 | 54.4696 | 0 | 0 | اكادميه الرياضه النسائيه | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
478 | Island | مجمع هيلز ابو ظبي | 24.4034 | 54.4648 | 24.4034 | 54.4648 | 0 | 0 | مجمع هيلز ابو ظبي | TRUE | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0
479 | Island | حديقه نادي الضباط | 24.4036 | 54.4817 | 24.4036 | 54.4817 | 0 | 0 | طريق فرعي قرب حديقه نادي الضباط | FALSE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
480 | Island | مواقف واحه الكرامه | 24.4089 | 54.4797 | 24.4089 | 54.4797 | 0 | 0 | مواقف واحه الكرامه | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
481 | Island | مقابل دائره القضاء - شارع النوفل | 24.4186 | 54.4467 | 24.4186 | 54.4467 | 0 | 0 | مقابل دائره القضاء - شارع النوفل | TRUE | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | AECOM
482 | Mussafah | طريق E-11 باتجاه الغويفات | 24.2512 | 54.4773 | 24.2512 | 54.4773 | 0 | 0 | طريق E-11 باتجاه الغويفات | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | [6 empty] | Parsons | Yes
483 | Al Wathbah | طريق E30 باتجاه العزب | 24.2094 | 54.8215 | 24.2094 | 54.8215 | 0 | 0 | طريق E30 باتجاه العزب | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [7 empty] | Contractor Design
484 | Al Shahama | طريق E16 | 24.5742 | 55.176 | 24.5742 | 55.176 | 0 | 0 | طريق E16 | TRUE | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
485 | Al Wathbah | شارع الخير | 24.2982 | 54.7121 | 24.2982 | 54.7121 | 0 | 0 | شارع الخير | TRUE | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
486 | Zayed | شارع E30- جسر المصفح - الفلتر باتجاه خليفة | 24.3875 | 54.5247 | 24.3875 | 54.5247 | 0 | 0 | شارع E30- جسر المصفح - الفلتر باتجاه خليفة | TRUE | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 |  |  | 0 | 0 | 750000 | 0 | [6 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-09-11 | 2027-01-12 | Hand over phase | N/A |  | 2026-07-18 |  |  | Parsons | Yes
487 | Zayed | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | 24.3916 | 54.5423 | 24.3916 | 54.5423 | 0 | 0 | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | TRUE | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 60000 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
488 | Zayed | دوار كرم الشام - مدينة شخبوط | 24.3716 | 54.6513 | 24.3716 | 54.6513 | 0 | 0 | دوار كرم الشام - مدينة شخبوط | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [7 empty] | Contractor Design
489 | Zayed | شارع مطر بن خادم المهيري- مدينة شخبوط | 24.3715 | 54.6481 | 24.3715 | 54.6481 | 0 | 0 | شارع مطر بن خادم المهيري- مدينة شخبوط | TRUE | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C |  | Absense of Drainage Network |  |  |  |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
490 | Al Shahama | شارع E12- من مجمع ياس باتجاه دبي | 24.4871 | 54.6344 | 24.4871 | 54.6344 | 0 | 0 | شارع E12- من مجمع ياس باتجاه دبي | TRUE | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 33000 | 0 | 0 | 0 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-26 |  | 2026-12-14 | Contractor | Yes |  |  |  |  | Parsons | Yes
491 | Mussafah | منطقة الأريام | 24.1659 | 54.3382 | 24.1659 | 54.3382 | 0 | 0 | منطقة الأريام | TRUE | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
492 | Mussafah | ايكاد 2 | 24.303228 | 54.4499 | 24.3021 | 54.4498 | #VALUE! | -0.000113 | ايكاد 2 | TRUE | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design |  | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons
493 | Al Wathbah | مدينة الرياض - شارع الخير | 24.2994 | 54.677 | 24.2994 | 54.677 | 0 | 0 | مدينة الرياض - شارع الخير | TRUE | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 4 | [9 empty] | 993600 |  |  | 0 | 0 | 0 | 0 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 |  | 2026-12-30 | 2D modelling |  |  | 2026-08-16 |  |  | Parsons | Yes
494 | Mussafah | منطقة النوف | 24.2478 | 54.1654 | 24.2478 | 54.1654 | 0 | 0 | منطقة النوف | TRUE | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
495 | Al Wathbah | ظهارة الطيب - أبو ظبي | 24.2105 | 54.8397 | 24.2105 | 54.8397 | 0 | 0 | ظهارة الطيب - أبو ظبي | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
496 | Al Wathbah | مدينة الرياض - حوض 144 | 24.2881 | 54.6911 | 24.2881 | 54.6911 | 0 | 0 | مدينة الرياض - حوض 144 | TRUE | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0
497 | Mussafah | منطقة الأريام | 24.2167 | 54.4065 | 24.2167 | 54.4065 | 0 | 0 | منطقة الأريام | TRUE | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
498 | Al Wathbah | عزب دهان - الوافية | 24.209 | 54.9138 | 24.209 | 54.9138 | 0 | 0 | عزب دهان - الوافية | TRUE | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
499 | Al Shahama | منطقة العجبان | 24.5997 | 54.8401 | 24.5997 | 54.8401 | 0 | 0 | منطقة العجبان | TRUE | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
500 | Mussafah | ايكاد 3 | 24.3108 | 54.5006 | 24.3108 | 54.5006 | 0 | 0 | ايكاد 3 | TRUE | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0
501 | Al Wathbah | عزب دهان | 24.195870 | 54.9685 | 24.195870 | 54.9685 | #VALUE! | 0 | عزب دهان | TRUE | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
502 | Al Shahama | مزارع عجبان - شارع عويد | 24.676 | 54.8319 | 24.676 | 54.8319 | 0 | 0 | مزارع عجبان - شارع عويد | TRUE | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network
503 | Mussafah | ايكاد 3 | 24.2996 | 54.4905 | 24.2996 | 54.4905 | 0 | 0 | ايكاد 3 | TRUE | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0
504 | Al Wathbah | منطقة طريق الحفار | 24.254018 | 54.8251 | 24.254018 | 54.8251 | #VALUE! | 0 | منطقة طريق الحفار | TRUE | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network
505 | Mussafah | ايكاد 3 | 24.299677 | 54.4849 | 24.299677 | 54.4849 | #VALUE! | 0 | ايكاد 3 | TRUE | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0
506 | Al Wathbah | أكادمية الدفاع المدني - طريق الحفار | 24.284 | 54.8305 | 24.3855 | 54.8443 | 0.10149 | 0.013839 | أكادمية الدفاع المدني - طريق الحفار | TRUE | Low | Yes | Private Area | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Under Assessment | T.B.C | T.B.C | T.B.C | T.B.C | T.B.C | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | T.B.C |  | T.B.C | Contractor Design | [5 empty] | Parsons

## 251 (hidden)
[11 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [20 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan
[38 empty] | Select Yes or No | Select one: Critical Infrastructure, Detailed Design, Fast-Track, or Quick Win | Provide the primary solution such as inlet, pipe, Upgrade to Catchment , Pond / Spillway, etc | Select one: Permanent, Interim, or Temporary | Please specify if additional budget is required for this hotspot (Yes/No) | Provide the requested budget for each applicable hotspot. If a single project spans multiple hotspots, list the budget only once under the primary hotspot. For all other covered hotspot entries, replace the budget with: "Included in Hotspot #X budget." | Provide the current rainfall design event, including the return period | Provide the existing network’s technical or hydraulic capacit | Provide the future or target rainfall design event, including the return period | Provide the future or target network capacity after the planned intervention | Provide the estimated floodwater volume managed by network after intervention | Provide the expected number of hours required for floodwater to recede after intervention | Revise the planned mobilization date | Revise the planned completion date | Select one: Contractor Design phase, Parsons Verification Phase, IDAS Review Phase, Municipality Permitting Phase, Implementation phase, Hand Over Phase | Select Yes or No. Enter Yes only after formal approval has been issued. | Provide the actual mobilization date (only after actual mobilization) | Provide the actual completion date (only after actual completion) | Select one: Not Started, On Track, Delayed, or Completed | Provide the full name of the accountable IDD owner.
Hotspot_ID | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD Interventoin Planned | IDD_Design_Category | Design Solution | Type of Intervention | Additional Budget Requirment | Additional Budget Requested | Hotspot Network Rain Design Event (Current) | Hotspot Network Design Technical Capacity (Current) | Hotspot Network Rain Design Event (Future) | Hotspot Network Design Technical Capacity (Future) | Flood Volume Capacity after Intervention | Associated recovery time after intervention | Planned_IDD_Mobilization_Date | Planned_IDD_Completion_Date | Project Stage | Approval from IDAS secured (Yes/No) | Actual_Mobilization_Date | Actual_Completion_Date | Intervention status | IDD_Owner_Name | Is_Private_Developer | Root_Cause_Category | IDD_Covered | IDD_Completion_Date2 | IDD_Timeline_Status
1 | Al Shahama | نفق الشهامة | 24.546 | 54.691 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-21 | #REF!
2 | Al Shahama | شارع الشيخ زايد بن سلطان | 24.4927 | 54.6493 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 | 2026-12-09 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-09 | #REF!
3 | Al Shahama | مجمع الجسور ياس | 24.4858 | 54.6449 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
4 | Al Shahama | نفق الشهامة الجديدة المؤدي الى ديرفيلدز مول | 24.5378 | 54.6848 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-09 | 2027-01-26 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-26 | #REF!
5 | Al Shahama | جسر الشهامة نادي الوحدة | 24.5611 | 54.6953 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-21 | #REF!
6 | Al Shahama | نفق كيزاد | 24.7287 | 54.8168 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Lowering Project | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 | 2026-12-31 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
7 | Al Shahama | روضة الريف – شارع الشهد | 24.4622 | 54.68 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
8 | Al Shahama | خليفة الصناعية - شارع غناضة | 24.7304 | 54.7793 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-10-08 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-08 | #REF!
9 | Al Shahama | منطقة الفلاح 4 | 24.4185 | 54.7241 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-11-30 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-30 | #REF!
10 | Al Shahama | منطقة الفلاح 1 | 24.4213 | 54.7472 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-25 | #REF!
11 | Al Shahama | ياس الحي الاماراتي | 24.4989 | 54.6024 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-08 | 2027-01-26 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-26 | #REF!
12 | Al Shahama | الباهية - شارع عجيج – الباهية مدرسة أميتي | 24.5313 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 | 2026-12-11 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-11 | #REF!
13 | Al Shahama | شارع عجيج - الصدر | 24.5934 | 54.6515 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-29 | 2027-02-16 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2027-02-16 | #REF!
14 | Mussafah | شارع سلطان بن محمد القبيسي - بعد الجسر المؤدي الى المصفح- الأول | 24.3736 | 54.5229 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
15 | Mussafah | مدينة الامارات الانسانية | 24.3789 | 54.5129 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
16 | Mussafah | Sector 17 | 24.3656 | 54.4832 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
17 | Mussafah | Sector 2 | 24.3779 | 54.5221 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
18 | Mussafah | Sector 15 | 24.3736 | 54.4826 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
19 | Mussafah | Sector 1 | 24.3792 | 54.5178 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
20 | Mussafah | Sector 1 | 24.3825 | 54.5234 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
21 | Zayed | مدخل مصفح القادم من شارع الخليج العربي | 24.3941 | 54.5186 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-12 | 2026-09-05 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-05 | #REF!
22 | Mussafah | Sector 9 | 24.3686 | 54.4914 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
23 | Mussafah | دوار دينا تريد | 24.2884 | 54.5646 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-12-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-25 | #REF!
24 | Mussafah | مستودعات البلدية | 24.2934 | 54.581 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-12-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-11 | #REF!
25 | Mussafah | طريق حميم | 24.1494 | 54.4205 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 | 2026-12-26 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-26 | #REF!
26 | Al Wathbah | مدينة الرياض - شارع طوي القايمة | 24.3314 | 54.7084 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-12-13 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-13 | #REF!
27 | Al Wathbah | مدينة الرياض - شارع الخير | 24.3432 | 54.7578 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-12-15 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
28 | Al Wathbah | مدينة الرياض - شارع العصري بن حمودة الظاهري | 24.3257 | 54.7446 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 | 2026-12-15 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
29 | Al Wathbah | مدينة الرياض -شارع الرياض | 24.333 | 54.7652 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-12-16 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-16 | #REF!
30 | Al Wathbah | مدينة الرياض -شارع النهضة | 24.3273 | 54.7042 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 | 2026-12-13 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-13 | #REF!
31 | Al Wathbah | مدينة الرياض -شارع الميثاق | 24.3307 | 54.7001 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-12-06 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-06 | #REF!
32 | Al Wathbah | مدينة الرياض - شارع سيح القطع | 24.3364 | 54.7356 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 | 2026-12-21 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-21 | #REF!
33 | Al Wathbah | مدينة الرياض - شارع الصنوبر | 24.3415 | 54.7524 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 | 2026-12-13 | 2D modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-13 | #REF!
34 | Al Wathbah | شارع الشيخ محمد بن راشد | 24.3732 | 54.729 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-09-14 | 2D modelling |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-14 | #REF!
35 | Al Wathbah | خلف مسلخ بني ياس | 24.3037 | 54.6711 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 | 2026-10-02 | 2D modelling |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
36 | Al Wathbah | الشوامخ - شارع خضيرمان | 24.3535 | 54.649 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 | 2027-02-03 | Parsons Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-02-03 | #REF!
37 | Al Wathbah | الشوامخ - مدخل ومخرج المزن | 24.3505 | 54.6802 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 | 2026-12-15 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
38 | Al Wathbah | شارع الشوامخ | 24.3855 | 54.6702 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 | 2026-09-07 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-07 | #REF!
39 | Al Wathbah | دوار - الشوامخ 12 | 24.3843 | 54.6745 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 | 2026-09-08 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-08 | #REF!
40 | Al Wathbah | مدينة الرياض -شارع الخير | 24.3221 | 54.749 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-12-17 | 2D Modelling |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-17 | #REF!
41 | Al Wathbah | الشوامخ 7 - شارع بدع بوحصية | 24.3721 | 54.6705 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-12-21 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-21 | #REF!
42 | Al Wathbah | مسجد الشيخة عفراء بنت زايد ال نهيان | 24.1836 | 54.9937 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-30 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-30 | #REF!
43 | Al Wathbah | الختم القديمة - بجوار حديقة الختم | 24.1881 | 54.9966 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-11-26 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-26 | #REF!
44 | Al Wathbah | بني ياس - شارع اليال | 24.3293 | 54.6331 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 | 2026-11-30 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-30 | #REF!
45 | Al Wathbah | بني ياس -شارع اليال | 24.3218 | 54.6427 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 | 2026-11-12 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
46 | Al Wathbah | بني ياس -شارع اليال | 24.3144 | 54.6534 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 | 2026-08-10 | Permitting Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-08-10 | #REF!
47 | Al Wathbah | بني ياس - شارع اليال | 24.3069 | 54.6633 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 | 2026-08-10 | Permitting Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-08-10 | #REF!
48 | Al Wathbah | بني ياس - شارع الشيخ محمد بن راشد | 24.2888 | 54.6549 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-15 | 2026-09-14 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-14 | #REF!
49 | Al Wathbah | بني ياس - شارع الخويرة | 24.3044 | 54.6281 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 | 2026-12-27 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-27 | #REF!
50 | Al Wathbah | نفق الوثبة | 24.2693 | 54.6681 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2027-01-24 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-24 | #REF!
51 | Al Wathbah | نفق النهضة | 24.2417 | 54.7368 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-20 | 2027-01-01 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-01 | #REF!
52 | Al Wathbah | الوثبة - شارع الحفظة | 24.2681 | 54.673 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2026-12-20 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-20 | #REF!
53 | Al Wathbah | الوثبة جنوب | 24.2663 | 54.6578 | Medium | Yes | Developer (Al Dar) | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-12 | IDAS Review Phase |  |  |  |  | Parsons | TRUE | Absence of Drainage Network | #REF! | 2026-11-12 | #REF!
54 | Al Wathbah | بني ياس - شارع الجزائر | 24.2758 | 54.6451 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-03-12 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-03-12 | #REF!
55 | Al Wathbah | الوثبة - شارع الرسوخ - بجانب منتزة الوثبة | 24.2458 | 54.7097 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 | 2026-11-18 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-18 | #REF!
56 | Al Wathbah | الوثبة - شارع النهضة | 24.269 | 54.684 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 | 2026-12-07 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-07 | #REF!
57 | Al Wathbah | بني ياس - شارع السهل | 24.2701 | 54.6498 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 | 2026-12-18 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-18 | #REF!
58 | Al Wathbah | الشامخة - بالقرب من الشامخة مول | 24.3999 | 54.7328 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2026-12-19 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-19 | #REF!
59 | Al Wathbah | الشامخة - شارع احمد بن شملان الفلاحي | 24.3937 | 54.7044 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-12-17 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
60 | Al Wathbah | الشامخة - تقاطع شارع الترشيد مع شارع ام الثعالب | 24.411 | 54.747 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-12-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-23 | #REF!
61 | Al Wathbah | الشامخة -شارع محمد بن شبيب المهيري | 24.3954 | 54.6943 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-12-24 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-24 | #REF!
62 | Al Wathbah | الشامخة -شارع الرضى | 24.3759 | 54.6992 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 | 2026-12-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-25 | #REF!
63 | Al Wathbah | الشامخة -شارع العايد | 24.3507 | 54.6832 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-11-22 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-22 | #REF!
64 | Al Wathbah | الشامخة - تقاطع شارع دمية طحنون مع شارع الخزنه | 24.4078 | 54.7358 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-11-16 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-16 | #REF!
65 | Al Wathbah | العدلة - شارع طوي بو صلف | 24.4182 | 54.8663 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 | 2026-03-12 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-03-12 | #REF!
66 | Al Wathbah | العدلة - شارع طوي اشعب | 24.4114 | 54.8677 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-09-17 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-17 | #REF!
67 | Al Wathbah | عزب العدلة | 24.3853 | 54.9003 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 | 2026-10-02 | N/A | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
68 | Al Wathbah | مدخل المحاجر في العدلة | 24.3869 | 54.9001 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 | 2026-10-02 | N/A | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
69 | Al Wathbah | مزارع العدلة | 24.3831 | 54.895 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 | 2026-10-02 | N/A | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-02 | #REF!
70 | Al Wathbah | الفاية الصناعية | 24.3082 | 54.8788 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
71 | Island | مواقف سيارات حديقه ام الامارات- المشرف / شارع الند ، غرب 24/2 | 24.4523 | 54.3841 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-10-10 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-10-10 | #REF!
72 | Island | الدوار المؤدي الى نادي ضباط الشرطة. | 24.4054 | 54.4707 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 | 2026-11-28 | Parsons Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-28 | #REF!
73 | Island | المشرف / غرب52 / شارع احمد بن سعيد الرميثي | 24.4359 | 54.3954 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 | 2026-11-28 | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-28 | #REF!
74 | Island | تقاطع شارع الشيخ راشد بن سعيد مع تقاطع شارع الشيخة فاطمة بنت مبارك (مقابل مبنى دائرة الاشغال سابقا) | 24.4624 | 54.3763 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Hand over phase | N/A |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
75 | Island | شارع اليزوة – الخالدية مقابل (سبينس- الكورنيش) | 24.4673 | 54.3343 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-05 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-05 | #REF!
76 | Island | شارع الكورنيش (مدخل بوابة قصر الامارات) | 24.4574 | 54.319 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-10 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-10 | #REF!
77 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4639 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Critical Infrastructure | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
78 | Island | مواقف سيارات مستشفي جلوبال كير | 24.4646 | 54.3658 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Implementation Phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
79 | Island | شارع المطار مقابل قصر المنهل | 24.479 | 54.3624 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
80 | Island | مرسي البطين جوار مبني تبريد | 24.4544 | 54.3378 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-19 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-19 | #REF!
81 | Island | بجوار مواقف سيارات المارينا مول | 24.4731 | 54.3201 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-27 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-27 | #REF!
82 | Island | مدارس التكنولوجيا التطبيقيه بمنطقه ال نهيان | 24.4672 | 54.3781 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-19 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-19 | #REF!
83 | Island | شارع الشيخة فاطمة بنت مبارك - مقابل مدرسة الامارات الوطنية | 24.4694 | 54.3851 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
84 | Island | حوض E-25 - قريب من مبنى مبادلة | 24.4618 | 54.3936 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 | 2026-11-16 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-16 | #REF!
85 | Al Shahama | شارع الشيخ زايد بين مجمع جسور ياس و جسر المطار بالاتجاهين | 24.4749 | 54.6365 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 | 2026-09-11 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
86 | Mussafah | نفق الصناعية الاول باتجاه الداخل | 24.3735 | 54.5219 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
87 | Mussafah | نفق الصناعية الثاني باتجاه الداخل | 24.3465 | 54.5226 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
88 | Al Shahama | مخرج الجسر من الشامخة للفلاح باتجاه دبي | 24.4106 | 54.6815 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-14 | 2026-12-20 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-20 | #REF!
89 | Al Shahama | مخرج جسر سويحان للقادم من جسر كرم الشام باتجاه الشامخة الفلاح | 24.4025 | 54.6703 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-15 | 2026-12-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-23 | #REF!
90 | Zayed | شارع الخليج العربي المخرج المؤدي لشارع العين | 24.3914 | 54.5291 | Very High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-16 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
91 | Zayed | جسر تعليم القيادة بالاتجاهين | 24.347 | 54.5289 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-30 | 2026-07-30 | Implementation Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-30 | #REF!
92 | Zayed | جسر المفرق للقادم من مدينة شخبوط الطبية باتجاه ابوظبي | 24.313 | 54.6036 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 | 2026-09-01 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-01 | #REF!
93 | Al Shahama | شارع محمد بن راشد للقادم من دبي تم تحويل الحركة باتجاه الشامخة | 24.4242 | 54.7646 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-15 | 2026-11-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-23 | #REF!
94 | Zayed | شارع ابوظبي - العين مدخل شارع الخدمات قبل جسر مزيد مول باتجاه الخارج | 24.3886 | 54.5401 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-01 | 2026-12-28 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-28 | #REF!
95 | Al Shahama | النفق المودي للشهامة للقادم من روضة الريف | 24.5429 | 54.6941 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-21 | #REF!
96 | Al Wathbah | طريق سويحان بعد جسر الفلاح الشامخة باتجاه سويحان | 24.4188 | 54.7506 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | Parsons Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
97 | Zayed | على طول شارع ذياب بن عيسى في مدينة خليفة أ بالاتجاهين | 24.4025 | 54.5725 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 | 2026-07-11 | Implementation Phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-11 | #REF!
98 | Zayed | شارع الشيخ مكتوم بن راشد مقابل مستشفى شخبوط باتجاه الغربية | 24.3205 | 54.6125 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-02 | 2026-09-08 | Implementation Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-08 | #REF!
99 | Zayed | طريق ابوظبي العين قبل جسر محوي باتجاه الداخل | 24.3461 | 54.5731 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-10 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-10 | #REF!
100 | Al Wathbah | شارع الشيخ مكتوم بن راشد عن حسر كرم الشام (الشوامخ) باتجاه دبي | 24.3726 | 54.6562 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-27 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-27 | #REF!
101 | Zayed | مدينة خليفة | 24.4406 | 54.6002 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-06 | 2026-07-11 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-11 | #REF!
102 | Zayed | مدينة خليفة | 24.4149 | 54.502 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-11 | #REF!
103 | Zayed | منطقة ربدان | 24.4112 | 54.5082 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 | 2026-10-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-23 | #REF!
104 | Zayed | منطقة ربدان | 24.4028 | 54.5272 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-10 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-10 | #REF!
105 | Zayed | منطقة ربدان | 24.3493 | 54.6215 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-15 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-15 | #REF!
106 | Zayed | مدينة شخبوط | 24.365 | 54.6482 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 | 2026-09-22 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-22 | #REF!
107 | Zayed | مدينة شخبوط | 24.405 | 54.5193 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 | 2026-10-27 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-27 | #REF!
108 | Zayed | منطقة ربدان | 24.3306 | 54.5368 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-20 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-20 | #REF!
109 | Zayed | مدينة محمد بن زايد | 24.4074 | 54.5026 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 | 2026-10-30 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-30 | #REF!
110 | Zayed | مدينة زايد | 24.3831 | 54.5948 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 | 2026-08-10 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-08-10 | #REF!
111 | Zayed | مدينة زايد | 24.3796 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-25 | 2026-09-16 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
112 | Zayed | ساس النخل - مدينة زايد | 24.4187 | 54.4962 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-02 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-02 | #REF!
113 | Zayed | ربدان - ساس النخل | 24.3925 | 54.5033 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
114 | Zayed | شارع جبر بن راشد الحلامي - طريق ساس النخل | 24.4237 | 54.5229 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-10 | #REF!
115 | Zayed | مدينة محمد بن زايد | 24.308 | 54.5813 | High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
116 | Zayed | مدينة زايد | 24.3846 | 54.633 | High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
117 | Zayed | مدينة زايد | 24.3542 | 54.6106 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
118 | Zayed | مدينة زايد | 24.3665 | 54.6067 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 | 2026-12-10 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-10 | #REF!
119 | Zayed | مدينة محمد بن زايد - شارع خليفة بن خميس الديهلي | 24.3403 | 54.5579 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-13 | [5 empty] | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-13 | #REF!
120 | Zayed | مدينة محمد بن زايد | 24.2968 | 54.5634 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-15 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-15 | #REF!
121 | Zayed | Zayed City | 24.3686 | 54.6005 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-22 | 2026-07-30 | Hand over phase | N/A |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-07-30 | #REF!
122 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.3994 | 54.5932 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-10-03 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-03 | #REF!
123 | Zayed | ربدان - شارع راشد بن جابر الهاملي | 24.4106 | 54.4965 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 | 2026-10-24 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-24 | #REF!
124 | Zayed | مدينة محمد بن زايد | 24.3176 | 54.5332 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-17 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-17 | #REF!
125 | Zayed | مدينة محمد بن زايد - MZ 17 | 24.3896 | 54.6092 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-29 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-29 | #REF!
126 | Zayed | مدينة زايد | 24.379 | 54.5851 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-08-15 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-08-15 | #REF!
127 | Zayed | ربدان | 24.4029 | 54.5038 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-25 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-25 | #REF!
128 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4097 | 54.6368 | High | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-08-15 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-08-15 | #REF!
129 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4102 | 54.6436 | High | Yes | ADM Developer | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-08-15 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-08-15 | #REF!
130 | Zayed | مدينة زايد | 24.3704 | 54.6183 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-06 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-06 | #REF!
131 | Zayed | مدينة خليفة | 24.4334 | 54.5769 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 | 2026-07-11 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-07-11 | #REF!
132 | Al Shahama | مدينة الفلاح | 24.4283 | 54.7364 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 | 2026-10-23 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-23 | #REF!
133 | Al Shahama | الشهامة | 24.5196 | 54.6716 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-26 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-26 | #REF!
134 | Mussafah | مصفح صناعية | 24.326 | 54.5162 | Medium | Yes | مطور | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
135 | Al Shahama | الباهية | 24.6264 | 54.7119 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-24 | Implementation Phase | Yes |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-10-24 | #REF!
136 | Al Wathbah | طريق رزين | 24.1576 | 54.8458 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
137 | Al Shahama | شارع خليفة بن زايد - الريف | 24.4615 | 54.702 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 | 2026-09-09 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-09 | #REF!
138 | Al Wathbah | الوثبة جنوب | 24.2609 | 54.673 | Low | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-17 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-17 | #REF!
139 | Al Shahama | مدينة الفلاح | 24.4258 | 54.7426 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-02 | 2026-12-20 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-20 | #REF!
140 | Zayed | مدينة خليفة - دوار طيران الرئاسة | 24.436 | 54.6253 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-07-25 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-25 | #REF!
141 | Mussafah | مصفح صناعية | 24.35 | 54.4939 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
142 | Al Wathbah | طريق الحفار | 24.3855 | 54.8443 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-30 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-11-30 | #REF!
143 | Al Shahama | الرحبة | 24.5965 | 54.695 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-02 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-02 | #REF!
144 | Al Wathbah | شارع بني ياس بالقرب من محطة البترول | 24.2968 | 54.6285 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 | 2026-11-12 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
145 | Al Wathbah | مدينة الرياض | 24.3514 | 54.7125 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-25 | 2026-12-21 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-21 | #REF!
146 | Al Wathbah | الوثبة جنوب | 24.2625 | 54.6587 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-30 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-30 | #REF!
147 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.642 | 54.6575 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-10 | Implementation Phase | Yes |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-10 | #REF!
148 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.6811 | 54.6692 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-18 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-18 | #REF!
149 | Al Shahama | شارع مكتوم بن راشد | 24.6959 | 54.7814 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-26 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-26 | #REF!
150 | Al Shahama | شارع سلطان بن زايد - الريف | 24.4711 | 54.6709 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
151 | Al Shahama | طريق الطف | 24.5973 | 54.9097 | Low | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Network New | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-08 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-12-08 | #REF!
152 | Al Shahama | الصدر- شارع عويد | 24.7557 | 54.7337 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-16 | Permitting Phase | Yes |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-12-16 | #REF!
153 | Al Shahama | خليفة الصناعية - 6 | 24.7631 | 54.7003 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-24 | Permitting Phase | Yes |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-12-24 | #REF!
154 | Al Shahama | مدينة الفلاح | 24.4322 | 54.7315 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-02-03 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-02-03 | #REF!
155 | Al Shahama | مدينة الفلاح | 24.4395 | 54.7408 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-02-03 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-02-03 | #REF!
156 | Al Wathbah | طريق أبو ظبي - العين | 24.3074 | 54.6051 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-18 | 2026-11-26 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-26 | #REF!
157 | Al Shahama | مدينة الفلاح | 24.4613 | 54.7361 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-11 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
158 | Al Shahama | شارع مكتوم بن راشد باتجاه السمحة القديمة | 24.6864 | 54.7736 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-24 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-24 | #REF!
159 | Al Shahama | دوار على شارع مكتوم بن راشد | 24.7976 | 54.8637 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-02 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2027-01-02 | #REF!
160 | Al Wathbah | طريق أبو ظبي - العين | 24.2812 | 54.6473 | Medium | Yes | Developer | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Contractor |  |  |  |  | Parsons | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
161 | Island | خلف مدرسه الامام الغزالي- شارع مطر المهيري - غرب 16 | 24.4583 | 54.3414 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
162 | Island | شارع المطلع - شارع الخليج العربي - غرب 52 | 24.437 | 54.3736 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-27 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-10-27 | #REF!
163 | Island | مرسي البطين جوار مرسى اليخوت 1 | 24.4507 | 54.3348 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-04 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-04 | #REF!
164 | Island | شارع خليفة بن شخبوط - غرب 17-1- مواقف سيارات مدرسه هزاع بن زايد الاول | 24.4607 | 54.3575 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-12-31 | #REF!
165 | Island | تقاطع شارع الخليج العربي مع شارع الشيخ هزاع | 24.457 | 54.3552 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-12 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
166 | Island | شارع الشيخ زايد بن سلطان تقاطع شارع ظفير -النفق | 24.445 | 54.4379 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-04 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-04 | #REF!
167 | Island | مناره المقطع - جوار جسر المقطع | 24.4214 | 54.4818 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-12 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
168 | Island | جراند الامارات - شارع هزاع بن زايد تقاطع شارع الشيخ سلطلن بن زايد | 24.4741 | 54.3748 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
169 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع الفلاح | 24.4831 | 54.3758 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-11 | #REF!
170 | Island | مقابل فندق كرستال ابو ظبي- شرق 14 بالقرب من مركز مدينة زايد للتسوق | 24.4848 | 54.3636 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-12 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-12 | #REF!
171 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع زايد الأول | 24.4891 | 54.3699 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
172 | Island | شارع الظفرة تقاطع شارع الخليج العربي- جوار دوار مجلس المشرف | 24.425 | 54.4108 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-04 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-04 | #REF!
173 | Island | شارع زايد بن سلطان بين تقاطع شاع زايد الأول وشارع محمد بن بطي ال حامد - مقابل مطعم قصر الهند | 24.4928 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
174 | Island | منطقه المزون | 24.4145 | 54.4314 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-27 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-27 | #REF!
175 | Island | شارع الظفرة بين شارع راشد بن زايد وشارع الخليج العربي | 24.4279 | 54.4108 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-09-16 | #REF!
176 | Island | شارع سلامة بن بطي بين شارع راشد بن زايد وشارع الخليج العربي | 24.4339 | 54.4033 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-20 | #REF!
177 | Island | مدخل منطقة روضة ابوظبي من شارع الشيخ راشد بن سعيد- قرب مطار البطين | 24.417 | 54.47 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-20 | #REF!
178 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع هزاع | 24.4704 | 54.3701 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
179 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع الشيخ محمد بن خليفة- مقابل محمصه الامراء | 24.459 | 54.3814 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-12-31 | #REF!
180 | Island | منطقة المعمورة - بجانب مبنى دائرة البلديات والنقل | 24.4617 | 54.3936 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 | 2026-11-14 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-11-14 | #REF!
181 | Island | جزيره الجبيل - شارع خليفه بن زايد | 24.5406 | 54.4836 | Low | Yes | مطور | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-11-20 | #REF!
182 | Island | دوار شارع الحريه - جزيره الريم | 24.482 | 54.4047 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-28 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-11-28 | #REF!
183 | Island | جزيره السعديات - جوار مسجد الحمد | 24.5385 | 54.4396 | Medium | Yes | مطور | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-12-31 | Contractor |  |  |  |  | AECOM | TRUE | Absence of Drainage Network | #REF! | 2026-12-31 | #REF!
184 | Island | شارع الشيخ راشد بن سعيد - جسر الجوازات | 24.4444 | 54.3952 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Contractor |  |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
185 | Island | شارع سلطان بن زايد من تقاطغ شارع سلامة بن بطي الى شارع الظفرة- مقابل مطعم اليمن السعيد شارع المرور | 24.4397 | 54.4118 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-28 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-28 | #REF!
186 | Island | مدخل قصر البحر | 24.4724 | 54.3927 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-29 | 2026-12-23 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-23 | #REF!
187 | Island | مينا زايد تابع للمطور | 24.5171 | 54.3729 | Medium | Yes | مطور | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-20 | Contractor |  |  |  |  | AECOM | TRUE | Topography & Road Engineering | #REF! | 2026-11-20 | #REF!
188 | Island | الشارع من أرض المعارض لدوار الجوية- شارع السفارات | 24.4235 | 54.4444 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-11-25 | Contractor |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | 2026-11-25 | #REF!
189 | Mussafah | نفق المصفح الثاني باتجاه الخارج | 24.3473 | 54.5254 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Critical Infrastructure |  | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | TBC |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
190 | Al Shahama | الشهامة الجديدة | 24.5431 | 54.6917 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-21 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-21 | #REF!
191 | Al Shahama | نفق ياس | 24.461 | 54.6111 | High | Yes | Developer (ICT) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-26 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2027-01-26 | #REF!
192 | Zayed | طريق الخليج العربي مقابل ملعب الكريكت | 24.3924 | 54.5486 | Very High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-16 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-16 | #REF!
193 | Zayed | قبل الجسر المؤدي لمحمد بن زايد | 24.3772 | 54.551 | High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-20 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-10-20 | #REF!
194 | Al Wathbah | بحيرة بني ياس | 24.3032 | 54.6275 | Very High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-12-28 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-28 | #REF!
195 | Al Wathbah | شارع الزود - بني ياس | 24.3094 | 54.6156 | High | Yes | Private | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 | 2026-12-30 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-30 | #REF!
196 | Zayed | قبل الجسر المؤدي للمفرق الصناعية | 24.2921 | 54.5592 | Very High | Yes | Private | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-01 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-01 | #REF!
197 | Zayed | شارع النصيلة- مدينة محمد بن زايد | 24.3244 | 54.5305 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-29 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-29 | #REF!
198 | Zayed | شارع النصيلة- مدينة محمد بن زايد - قبل الجسر | 24.3263 | 54.5841 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-01 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-01 | #REF!
199 | Zayed | الجسر المؤدي الى المصفح - طريق أبو ظبي - العين | 24.3278 | 54.5859 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-10-08 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-08 | #REF!
200 | Al Wathbah | الشوامخ - تقاطع شارع طوي القامة مع شارع المورد | 24.3598 | 54.6677 | High | Yes | Mainland | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-26 | 2026-11-11 | Permitting Phase | Yes |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-11-11 | #REF!
201 | Zayed | مدينة خليفة | 24.4244 | 54.5449 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 | 2026-07-10 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-10 | #REF!
202 | Zayed | مدينة خليفة | 24.3958 | 54.555 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 | 2026-07-11 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-07-11 | #REF!
203 | Zayed | مدينة خليفة | 24.4297 | 54.5634 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 | 2026-07-10 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-07-10 | #REF!
204 | Zayed | مدينة خليفة | 24.4264 | 54.535 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 | 2026-10-05 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-05 | #REF!
205 | Zayed | مدينة خليفة - طريق المطار | 24.4482 | 54.6131 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 | 2026-10-22 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-22 | #REF!
206 | Zayed | مدينة خليفة | 24.4467 | 54.6181 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-25 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-25 | #REF!
207 | Island | جسر دلما | 24.4668 | 54.3829 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 | 2026-12-15 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-12-15 | #REF!
208 | Mussafah | مدخل قاعدة الظفرة الجوية | 24.2821 | 54.5414 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
209 | Mussafah | مصفح صناعية - قطاع 3 | 24.3826 | 54.5106 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 180576 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
210 | Mussafah | مصفح صناعية - قطاع M19 | 24.3674 | 54.4811 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 1 | 2 | 0 | 1440 | 1728 | 3168 | 38016 | 142560 | 180576 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
211 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3578 | 54.4721 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
212 | Mussafah | مصفح صناعية - قطاع MW3 | 24.3567 | 54.4724 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
213 | Mussafah | مصفح صناعية - قطاع M34 | 24.3463 | 54.5125 | High | No | N/A | Yes | The network needs an upgrade |  | 4 | 20736 | 77760 | 98496 | 5 | 1 | 3 | 1 | 2160 | 4320 | 864 | 7344 | 88128 | 330480 | 418608 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
214 | Mussafah | مصفح صناعية | 24.3284 | 54.5262 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Critical Infrastructure | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-16 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-16 | #REF!
215 | Mussafah | مصفح صناعية - ICAD I | 24.3218 | 54.5048 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
216 | Mussafah | مصفح صناعية - ICAD I | 24.3268 | 54.4839 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
217 | Mussafah | مصفح صناعية - قطاع M42 | 24.3362 | 54.4781 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
218 | Mussafah | مصفح صناعية - قطاع M43 | 24.3438 | 54.4807 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
219 | Mussafah | مصفح صناعية - قطاع M32_02 | 24.3575 | 54.5142 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
220 | Mussafah | مصفح صناعية - قطاع M24 | 24.3607 | 54.5204 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
221 | Zayed | مدينة محمد بن زايد - Z9_01 | 24.3741 | 54.5364 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-29 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-29 | #REF!
222 | Zayed | مدينة محمد بن زايد - Z1 | 24.3733 | 54.5395 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
223 | Zayed | مدينة محمد بن زايد - Z9 | 24.36 | 54.5372 | High | Yes | Private area | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-10 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-09-10 | #REF!
224 | Zayed | مدينة محمد بن زايد - Z5 | 24.353 | 54.5554 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-06 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-10-06 | #REF!
225 | Zayed | مدينة محمد بن زايد - Z8 | 24.3514 | 54.5527 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [6 empty] | 2026-09-22 |  | Contractor | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
226 | Zayed | مدينة محمد بن زايد - Z9 | 24.3474 | 54.538 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-22 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-09-22 | #REF!
227 | Zayed | مدينة محمد بن زايد - ME9 | 24.3451 | 54.5352 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
228 | Zayed | مدينة محمد بن زايد - ME9 | 24.3385 | 54.5324 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
229 | Zayed | مدينة محمد بن زايد - ME10 | 24.3359 | 54.5357 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
230 | Zayed | مدينة محمد بن زايد - ME11 | 24.3291 | 54.5384 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
231 | Zayed | مدينة محمد بن زايد - ME11 | 24.3268 | 54.5389 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
232 | Zayed | مدينة محمد بن زايد - Z20 | 24.3157 | 54.5398 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
233 | Zayed | مدينة محمد بن زايد - Z24 | 24.3153 | 54.5508 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
234 | Zayed | مدينة محمد بن زايد - Z23 | 24.3168 | 54.5556 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
235 | Zayed | مدينة محمد بن زايد - Z30 | 24.2966 | 54.5551 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
236 | Zayed | مدينة محمد بن زايد - Z30 | 24.2997 | 54.5587 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
237 | Zayed | مدينة محمد بن زايد - Z30 | 24.3017 | 54.5645 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
238 | Zayed | مدينة محمد بن زايد - Z30 | 24.295 | 54.5672 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
239 | Zayed | مدينة محمد بن زايد - Z31 | 24.3018 | 54.5744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
240 | Zayed | مدينة محمد بن زايد - Z34 | 24.3017 | 54.5839 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
241 | Zayed | مدينة محمد بن زايد - Z34 | 24.3021 | 54.5813 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
242 | Zayed | مدينة محمد بن زايد - Z34 | 24.304 | 54.5828 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
243 | Zayed | مدينة محمد بن زايد - Z34 | 24.3022 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
244 | Zayed | مدينة محمد بن زايد - Z34 | 24.3047 | 54.5775 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
245 | Zayed | مدينة محمد بن زايد - Z35 | 24.3076 | 54.5916 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
246 | Zayed | مدينة محمد بن زايد - Z35 | 24.3161 | 54.5864 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
247 | Zayed | مدينة محمد بن زايد - Z33 | 24.3227 | 54.577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
248 | Zayed | مدينة محمد بن زايد - Z33 | 24.3192 | 54.5782 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
249 | Zayed | مدينة محمد بن زايد - Z33 | 24.323 | 54.5754 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
250 | Zayed | مدينة محمد بن زايد - Z22 | 24.3223 | 54.5688 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
251 | Zayed | مدينة محمد بن زايد - Z22 | 24.3222 | 54.5645 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ |  | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
252 | Zayed | مدينة محمد بن زايد - Z22 | 24.3241 | 54.5623 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
253 | Zayed | مدينة محمد بن زايد - Z21 | 24.3232 | 54.5577 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
254 | Zayed | مدينة محمد بن زايد - Z15 | 24.3334 | 54.5579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
255 | Zayed | مدينة محمد بن زايد - Z13 | 24.3437 | 54.5546 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [11 empty] | Ongoing assessment as design develop’ | [14 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
256 | Zayed | مدينة محمد بن زايد - Z13_01 | 24.3422 | 54.5636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
257 | Zayed | مدينة محمد بن زايد - Z36 | 24.3356 | 54.5782 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
258 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2868 | 54.5897 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
259 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.2818 | 54.5849 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
260 | Mussafah | مصفح - جرن يافور - المفرق الصناعية | 24.256 | 54.6342 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
261 | Zayed | ربدان - RB1 | 24.4179 | 54.4945 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
262 | Zayed | ربدان - RB2 | 24.4149 | 54.4926 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
263 | Zayed | ربدان - RB7 | 24.407 | 54.515 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
264 | Zayed | ربدان - RB14 | 24.4024 | 54.4879 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
265 | Zayed | ربدان - RB28 | 24.3984 | 54.5024 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2027-01-31 | [5 empty] | Parsons | FALSE | Topography & Road Engineering | #REF! | 2027-01-31 | #REF!
266 | Zayed | ربدان - RB28 | 24.3947 | 54.5009 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
267 | Zayed | المخرج الى طريق دبي - من طريق أبو ظبي العين | 24.4142 | 54.5066 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-09-25 | IDAS Review Phase |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-09-25 | #REF!
268 | Zayed | المخرج الى شارع الشيخ زايد - ساس النخل | 24.4193 | 54.5136 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-03 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-03 | #REF!
269 | Zayed | SW17_مدينة خليفة - 01 | 24.4116 | 54.5139 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
270 | Zayed | مدينة خليفة - SW17 - وطني | 24.4163 | 54.5465 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
271 | Zayed | مدينة خليفة - SW17 - وطني | 24.4148 | 54.5432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
272 | Zayed | مدينة خليفة - SW17 - وطني | 24.4144 | 54.5405 | High | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
273 | Zayed | مدينة خليفة | 24.4145 | 54.5393 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-13 | Contractor |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-10-13 | #REF!
274 | Zayed | مدينة خليفة | 24.4144 | 54.5411 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
275 | Zayed | مدينة خليفة - SW13 | 24.4132 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
276 | Zayed | مدينة خليفة - SW2 | 24.4197 | 54.5586 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
277 | Zayed | مدينة خليفة - SW3 | 24.4147 | 54.5641 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
278 | Zayed | مدينة خليفة - SW4 | 24.41 | 54.5645 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
279 | Zayed | مدينة خليفة - شارع المطار بالاتجاه لأبو ظبي | 24.3978 | 54.5738 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 | 2026-10-17 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-17 | #REF!
280 | Zayed | مدينة خليفة - SE3 | 24.4195 | 54.5683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
281 | Zayed | مدينة خليفة - SE13 | 24.4184 | 54.5832 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
282 | Zayed | مدينة خليفة - SE24 | 24.414 | 54.5885 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
283 | Zayed | مدينة خليفة - SE26 | 24.4092 | 54.5924 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
284 | Zayed | مدينة خليفة - SE6 | 24.4016 | 54.5785 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
285 | Zayed | مدينة خليفة - SE16 | 24.4027 | 54.5843 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
286 | Zayed | مدينة خليفة - SE26 | 24.4045 | 54.592 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
287 | Zayed | مدينة خليفة - SE36 | 24.407 | 54.6048 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
288 | Zayed | مدينة خليفة - SE38 | 24.4124 | 54.6033 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
289 | Zayed | مدينة خليفة - SE35 | 24.4158 | 54.6016 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
290 | Zayed | مدينة خليفة - SE44 | 24.43 | 54.5817 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
291 | Zayed | مدينة خليفة - SE47 | 24.4365 | 54.5869 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
292 | Zayed | مدينة خليفة - SE47 | 24.44 | 54.5905 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
293 | Zayed | مدينة خليفة - SE40 | 24.4264 | 54.6002 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
294 | Zayed | مدينة خليفة - الراحة - RBW13 | 24.4343 | 54.5597 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
295 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4384 | 54.5776 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-14 | 2026-10-26 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-26 | #REF!
296 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4427 | 54.5933 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-21 | 2026-10-31 | Permitting Phase | Yes |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-10-31 | #REF!
297 | Zayed | مدينة شخبوط - طريق سويحان باتجاه الى طريق المفرق | 24.4094 | 54.6638 | Very High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | D |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 | 2026-10-13 | Contractor |  |  |  |  | Parsons | FALSE | Topography & Road Engineering | #REF! | 2026-10-13 | #REF!
298 | Zayed | مدينة زايد - MZ6 | 24.3781 | 54.5951 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
299 | Zayed | مدينة زايد - MZ6 | 24.3826 | 54.6024 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
300 | Zayed | مدينة زايد - MZ7 | 24.3867 | 54.6059 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
301 | Zayed | مدينة زايد - MZ7 | 24.3819 | 54.6087 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
302 | Zayed | مدينة زايد - MZ10 | 24.3691 | 54.6046 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
303 | Zayed | مدينة زايد - MZ1 | 24.3657 | 54.6032 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
304 | Zayed | مدينة زايد - MZ1 | 24.3604 | 54.6 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
305 | Zayed | مدينة زايد - MZ8 | 24.3892 | 54.6189 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
306 | Zayed | مدينة زايد - MZ9 | 24.3922 | 54.6221 | Medium | Yes | Al Dar | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
307 | Zayed | مدينة شخبوط - MSH7 | 24.349 | 54.6085 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
308 | Zayed | مدينة شخبوط - MSH7 | 24.3519 | 54.611 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
309 | Zayed | مدينة شخبوط - MSH7 | 24.348 | 54.6131 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
310 | Zayed | مدينة شخبوط - MSH5 | 24.35 | 54.6163 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
311 | Zayed | مدينة شخبوط - MSH5 | 24.3503 | 54.6186 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
312 | Zayed | مدينة شخبوط - MSH5 | 24.3443 | 54.6165 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
313 | Zayed | مدينة شخبوط - MSH3 | 24.3453 | 54.6214 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
314 | Zayed | مدينة شخبوط - MSH1 | 24.3373 | 54.6237 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
315 | Zayed | مدينة شخبوط - MSH2 | 24.3423 | 54.6272 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
316 | Zayed | مدينة شخبوط - MSH1 | 24.3436 | 54.6316 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
317 | Zayed | مدينة شخبوط - MSH15 | 24.3583 | 54.637 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
318 | Zayed | مدينة شخبوط - MSH14 | 24.3643 | 54.6345 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
319 | Zayed | مدينة شخبوط - MSH17 | 24.3697 | 54.6488 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
320 | Zayed | مدينة شخبوط - MSH19 | 24.3727 | 54.6467 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
321 | Zayed | مدينة شخبوط - MSH19 | 24.3721 | 54.6428 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
322 | Zayed | مدينة شخبوط - MSH23 | 24.3774 | 54.6306 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
323 | Zayed | مدينة شخبوط - MSH20 | 24.3756 | 54.6454 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
324 | Zayed | مدينة شخبوط - MSH24 | 24.388 | 54.6396 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
325 | Al Wathbah | بني ياس - EB1_03 | 24.3174 | 54.6355 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
326 | Al Wathbah | بني ياس - EB6_01 | 24.3068 | 54.6446 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
327 | Al Wathbah | بني ياس - EB7_B | 24.2999 | 54.6381 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
328 | Al Wathbah | بني ياس -EB10_A | 24.293 | 54.6517 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
329 | Al Wathbah | بني ياس -WB3_A | 24.2888 | 54.6342 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
330 | Al Wathbah | بني ياس -EB11_01 | 24.3089 | 54.6456 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
331 | Al Wathbah | بني ياس -EB1_04 | 24.3256 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
332 | Al Wathbah | الشوامخ - SHM10 | 24.3431 | 54.6493 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
333 | Al Wathbah | الشوامخ - SHM9 | 24.3498 | 54.6551 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
334 | Al Wathbah | الشوامخ - SHM9 | 24.3535 | 54.6619 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
335 | Al Wathbah | الشوامخ - SHM3 | 24.362 | 54.6552 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
336 | Al Wathbah | الشوامخ - SHM2 | 24.3681 | 54.6603 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
337 | Al Wathbah | الشوامخ - SHM1 | 24.3771 | 54.6636 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
338 | Al Wathbah | الشامخة - SH10 | 24.3969 | 54.704 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
339 | Al Wathbah | الشامخة - SH11 | 24.3834 | 54.7167 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
340 | Al Wathbah | الشامخة - SH14 | 24.3692 | 54.7154 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
341 | Al Wathbah | مدينة الرياض - RD26 | 24.3287 | 54.7804 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 3 | 0 | 0 | 6480 | 0 | 0 | 6480 | 77760 | 291600 | 369360 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
342 | Al Wathbah | مدينة الرياض - RD32 | 24.3325 | 54.7441 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
343 | Al Wathbah | مدينة الرياض - RD11 | 24.3562 | 54.7382 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
344 | Al Wathbah | مدينة الرياض - RD7 | 24.3769 | 54.7572 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
345 | Al Shahama | الفلاح - 1E | 24.433 | 54.7399 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
346 | Al Shahama | الفلاح - 1E | 24.431 | 54.7432 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
347 | Al Shahama | الفلاح - 1E | 24.4412 | 54.7333 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
348 | Al Shahama | الفلاح - 1D | 24.4464 | 54.7381 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
349 | Al Shahama | الفلاح - 1C | 24.4577 | 54.7377 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
350 | Al Shahama | الفلاح - 1B | 24.4563 | 54.7178 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
351 | Al Shahama | جزيرة ياس - YN3 | 24.5108 | 54.6005 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
352 | Al Shahama | جزيرة ياس - YN3 | 24.504 | 54.596 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 2 | 0 | 0 | 4320 | 0 | 0 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
353 | Al Shahama | جزيرة ياس - YN7 | 24.4977 | 54.6225 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
354 | Al Shahama | الباهية - Al Shahamah Old | 24.5421 | 54.6796 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
355 | Al Shahama | الباهية - Al Bahyah New | 24.546 | 54.6293 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
356 | Al Shahama | الباهية - Al Bahyah New | 24.5467 | 54.6367 | Medium | Yes | Developer (Musanada) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
357 | Al Shahama | الباهية - Al Shahamah Old | 24.5584 | 54.6798 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
358 | Al Shahama | الرحبة - Rahbah_A | 24.5655 | 54.6872 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
359 | Al Shahama | الرحبة - Rahbah_A | 24.5663 | 54.6859 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
360 | Al Shahama | الرحبة - Rahbah_A | 24.5695 | 54.6862 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
361 | Al Shahama | الرحبة - Rahbah_C | 24.5769 | 54.6871 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
362 | Al Shahama | الرحبة - Rahbah_G | 24.6021 | 54.6998 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
363 | Al Shahama | الرحبة - السمحة | 24.6241 | 54.7104 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
364 | Al Shahama | السمحة - Al Samhah East | 24.6542 | 54.7605 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
365 | Al Shahama | السمحة - Al Samhah East | 24.661 | 54.7647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
366 | Al Shahama | السمحة -Al Samhah East Old | 24.6718 | 54.7741 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
367 | Al Shahama | السمحة -Al Samhah East Old | 24.6781 | 54.7753 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
368 | Al Shahama | السمحة -Samhah_V | 24.6712 | 54.7479 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
369 | Al Shahama | السمحة -Samhah_T | 24.6716 | 54.7581 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
370 | Al Shahama | السمحة -Al Samhah West Old_ | 24.6859 | 54.7676 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
371 | Al Wathbah | Qasr Al Wathbah South | 24.1767 | 54.7566 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
372 | Al Wathbah | Al Dhafrah East | 24.2383 | 54.6337 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
373 | Al Wathbah | Al Nahdah Al Askariah | 24.2607 | 54.7083 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
374 | Al Wathbah | Al Nahdah Al Askariah | 24.2634 | 54.7013 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
375 | Al Wathbah | Al Nahdah Al Askariah | 24.2677 | 54.6937 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
376 | Island | جوار نيشن تاور | 24.4633 | 54.3288 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
377 | Island | شارع الاواصر | 24.4656 | 54.3357 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
378 | Island | شارع الاواصر | 24.4661 | 54.3366 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
379 | Island | ابراج الساحل | 24.4664 | 54.335 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
380 | Island | اسبنس الكورنيش | 24.4659 | 54.3345 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
381 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4696 | 54.3373 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
382 | Island | خلف مدرسه سابس العالميه | 24.4628 | 54.3411 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
383 | Island | خلف مدرسه سابس العالميه | 24.4626 | 54.3407 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
384 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4695 | 54.3377 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
385 | Island | كليه ابو ظبي للاداره | 24.4848 | 54.3536 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
386 | Island | شارع المطار مدخل قصر الحصن | 24.4835 | 54.358 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
387 | Island | صيدليه الملا منطقه الخالديه | 24.4792 | 54.3579 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
388 | Island | مدينه خليفه الطبيه | 24.4705 | 54.364 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 0 | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
389 | Island | مجلس المنهل | 24.4691 | 54.3587 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
390 | Island | مجمع الكرامه | 24.4641 | 54.3728 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | IDAS Review Phase |  |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
391 | Island | خلف فندق فلايجيو شارع المطار | 24.4653 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
392 | Island | خلف فندق فلايجيو شارع المطار | 24.4645 | 54.3745 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
393 | Island | شارع الشيخه فاطمه اتجاه البطين تقاطع شارع المطار | 24.4636 | 54.3777 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
394 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4646 | 54.3757 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
395 | Island | تقاطع الشيخه فاطمه مع شارع الكرامه | 24.4597 | 54.3733 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
396 | Island | صيدليه المركز الامريكي جوار مجمع ليوا | 24.4575 | 54.371 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
397 | Island | خلف المركز الامريكي | 24.4551 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
398 | Island | خلف مركز القاضي الطبي | 24.4421 | 54.3678 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
399 | Island | دوار الفروسيه 1 | 24.4425 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
400 | Island | جوار مجمع حدائق المشرف | 24.4431 | 54.3734 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
401 | Island | دوار الفروسيه 2 | 24.4465 | 54.3757 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
402 | Island | اسفل جسر شارع الخليج العربي | 24.4351 | 54.3768 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
403 | Island | جوار مبني الهويه والجنسيه 1 | 24.4473 | 54.3897 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
404 | Island | جوار مبني الهويه والجنسيه 2 | 24.4477 | 54.3886 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
405 | Island | مسجد خالد بن الوليد منطقه البطين | 24.4514 | 54.3551 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
406 | Island | مرسي البطين جوار مرسى اليخوت 2 | 24.4514 | 54.3368 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
407 | Island | حديقه ام الامارات 2 | 24.4544 | 54.3818 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
408 | Island | جسر شارع الشيخ خليفه بن زايد اتجاه السعديات | 24.5151 | 54.3925 | Medium | Yes | مطور | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
409 | Island | مينا زايد تابع للمطور | 24.5322 | 54.3661 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
410 | Island | مينا زايد تابع للمطور | 24.5221 | 54.3682 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
411 | Island | مينا زايد تابع للمطور | 24.5136 | 54.3685 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
412 | Island | فندق هلا ارجان- الزاهية | 24.502 | 54.377 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
413 | Island | مواقف سيارات خلف فندق نهال | 24.4982 | 54.3727 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
414 | Island | مستشفي الكورنيش | 24.5013 | 54.3696 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
415 | Island | خلف المركز الاجتماعي الهندي | 24.5088 | 54.3794 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
416 | Island | مواقف سيارات سوق السجاد | 24.5116 | 54.3834 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Hand over phase | N/A |  |  |  | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
417 | Island | مواقف سيارات سوق السجاد | 24.5121 | 54.3825 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
418 | Island | شارع خليفه بن زايد تقاطع شارع المينا | 24.5091 | 54.3824 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
419 | Island | جسر الماريا شارع حمدان بن محمد | 24.5021 | 54.3813 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
420 | Island | شارع السلام قبل تقاطع شارع حمدان | 24.4956 | 54.374 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
421 | Island | جوار بنك ابو ظبي الاول - شارع السلام | 24.4919 | 54.378 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
422 | Island | شارع الريم جوار مطعم جاد | 24.4902 | 54.3807 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
423 | Island | جوار فندق جنه شارع الفلاح | 24.489 | 54.3831 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
424 | Island | جوار مجمع طاقه 1 | 24.4846 | 54.3788 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
425 | Island | جوار مجمع طاقه 2 | 24.4835 | 54.3779 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
426 | Island | مواقف شارع السلام محال تاجير السيارات 1 | 24.486 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
427 | Island | مواقف شارع السلام محال تاجير السيارات 2 | 24.485 | 54.3821 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
428 | Island | مواقف حافلات مدرسه الشيخه فاطمه 1 | 24.4818 | 54.3799 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
429 | Island | مواقف حافلات مدرسه الشيخه فاطمه 2 | 24.4823 | 54.3796 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
430 | Island | جوار السفاره السريلانكيه | 24.4815 | 54.3848 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
431 | Island | خلف مسجد حمد خليفه الخلفان | 24.4805 | 54.3823 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
432 | Island | مواقف مستشفي برجيل شارع الدفاع | 24.4785 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
433 | Island | جوار مدرسه الايمان الخاصه | 24.4892 | 54.3671 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
434 | Island | جوار مسجد عبد الرحيم خوري | 24.4859 | 54.3712 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
435 | Island | شارع المرور مقابل سوق الذهب | 24.4847 | 54.3667 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
436 | Island | شارع المرور مقابل سوق الذهب | 24.4859 | 54.366 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
437 | Island | مواقف سوق الذهب | 24.4843 | 54.3644 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
438 | Island | تقاطع شارع المرور مع شارع الفلاح | 24.4787 | 54.3697 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
439 | Island | فندق النخيل شارع المرور | 24.4775 | 54.3715 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
440 | Island | خلف جراند الامارات شارع المرور | 24.4731 | 54.3725 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
441 | Island | جوار كنتاكي شارع المطار | 24.4733 | 54.3683 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
442 | Island | فندق ماريوت شارع المطار | 24.4704 | 54.3701 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
443 | Island | منطقه ال نهيان " محلات الشوكلاته " | 24.4726 | 54.3803 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
444 | Island | مجمع الكرامه | 24.4634 | 54.372 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
445 | Island | مبني تدوير " الاشغال سابقا " | 24.4613 | 54.3749 | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
446 | Island | شارع ماء سلوان مقابل صحه مستشفي خليفه | 24.4674 | 54.3689 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
447 | Island | مجمع الكرامه | 24.4625 | 54.3709 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
448 | Island | شارع الكرامه | 24.4613 | 54.3699 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
449 | Island | روضه ابو ظبي للاطفال | 24.4634 | 54.3673 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
450 | Island | مطعم المزراب الشعبي | 24.4543 | 54.3863 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
451 | Island | نادي الجزيره | 24.4513 | 54.3925 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
452 | Island | خلف جامعه خليفه | 24.4449 | 54.3989 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
453 | Island | مسجد حمزه بن عبد المطلب | 24.4437 | 54.4062 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
454 | Island | حديقه قاف " حديقه الملك حمد " | 24.4357 | 54.4114 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
455 | Island | خياط البيت السعيد - شارع المرور | 24.4379 | 54.4136 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
456 | Island | مركز فحص المركبات - ادنوك شارع المرور | 24.4355 | 54.4168 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
457 | Island | كليه الشرطه | 24.4378 | 54.4193 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
458 | Island | خلف مسجد سيف بن حارب المنصوري | 24.4389 | 54.4185 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
459 | Island | الدفاع المدني - القبيسات | 24.425 | 54.4186 | High | No | N/A | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed |  | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | [5 empty] | AECOM | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
460 | Island | مسجد السيد يوسف الهاشمي | 24.4245 | 54.4151 | Medium | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintenance | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC | TBC | Hand over phase | N/A |  |  |  | AECOM | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
461 | Island | شارع سلامه بنت بطيء | 24.4333 | 54.4034 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
462 | Island | شارع المدرسه | 24.4315 | 54.4094 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
463 | Island | مقابل اكادميه ابو ظبي للسباحه | 24.4267 | 54.4132 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
464 | Island | شارع الظفرة تقاطع شارع الخليج العربي- دوار مجلس المشرف | 24.4251 | 54.4099 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
465 | Island | شرق 43 | 24.4397 | 54.4297 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
466 | Island | جوار مسجد جبريل | 24.4254 | 54.4254 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
467 | Island | شارع الخرطوم - مدرسه الريم | 24.4346 | 54.4317 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
468 | Island | منطقه السعاده 1 | 24.4361 | 54.4371 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
469 | Island | منطقه السعاده 2 | 24.4413 | 54.4351 | Medium | No | N/A | No | Absense of Drainage Network |  | 2 | 10368 | 38880 | 49248 | 3 | 0 | 0 | 3 | 0 | 0 | 2592 | 2592 | 31104 | 116640 | 147744 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
470 | Island | مجمع اوريكس | 24.4402 | 54.4476 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
471 | Island | محطه ادنوك - جوار مجمع الظبي | 24.4402 | 54.4518 | Medium | No | N/A | Yes | The network needs an upgrade |  | 2 | 10368 | 38880 | 49248 | 4 | 0 | 0 | 4 | 0 | 0 | 3456 | 3456 | 41472 | 155520 | 196992 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
472 | Island | مدخل قصر المينا مع شارع المروج | 24.4378 | 54.4591 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
473 | Island | دوار مدينه زايد الرياضيه | 24.4192 | 54.4567 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
474 | Island | ملاعب منطقه الروضه " غرب مطار البطين " | 24.4203 | 54.4617 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
475 | Island | منطقه الروضه " الابراج السكنيه " | 24.4178 | 54.4647 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
476 | Island | حديقه نادي الضباط | 24.404 | 54.475 | Medium | No | N/A | No | Absense of Drainage Network |  | 4 | 20736 | 77760 | 98496 | 5 | 0 | 0 | 5 | 0 | 0 | 4320 | 4320 | 51840 | 194400 | 246240 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
477 | Island | اكادميه الرياضه النسائيه | 24.4018 | 54.4696 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
478 | Island | مجمع هيلز ابو ظبي | 24.4034 | 54.4648 | Medium | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
479 | Island | حديقه نادي الضباط | 24.4036 | 54.4817 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
480 | Island | مواقف واحه الكرامه | 24.4089 | 54.4797 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
481 | Island | مقابل دائره القضاء - شارع النوفل | 24.4186 | 54.4467 | High | No | N/A | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | FALSE | Topography & Road Engineering | #REF! | #REF! | #REF!
482 | Mussafah | طريق E-11 باتجاه الغويفات | 24.2512 | 54.4773 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 | 2027-01-31 | [5 empty] | Parsons | FALSE | Absence of Drainage Network | #REF! | 2027-01-31 | #REF!
483 | Al Wathbah | طريق E30 باتجاه العزب | 24.2094 | 54.8215 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
484 | Al Shahama | طريق E16 | 24.5742 | 55.176 | Medium | Yes | Al Dar | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
485 | Al Wathbah | شارع الخير | 24.2982 | 54.7121 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
486 | Zayed | شارع E30- جسر المصفح - الفلتر باتجاه خليفة | 24.3875 | 54.5247 | High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-07-30 | Hand over phase | N/A |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-07-30 | #REF!
487 | Zayed | شارع الخليج العربي - مجمع الجسور باتجاه مدينة خليفة | 24.3916 | 54.5423 | Very High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 2 | 0 | 0 | 2880 | 0 | 2880 | 34560 | 129600 | 164160 | 0 | 0 | 0 | 0 | 750000 | 60000 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
488 | Zayed | دوار كرم الشام - مدينة شخبوط | 24.3716 | 54.6513 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
489 | Zayed | شارع مطر بن خادم المهيري- مدينة شخبوط | 24.3715 | 54.6481 | High | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 750000 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | [6 empty] | Contractor Design | [5 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
490 | Al Shahama | شارع E12- من مجمع ياس باتجاه دبي | 24.4871 | 54.6344 | Very High | No | N/A | No | Absense of Drainage Network | [28 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-26 | 2026-12-14 | Contractor |  |  |  |  | Parsons | FALSE | Absence of Drainage Network | #REF! | 2026-12-14 | #REF!
491 | Mussafah | منطقة الأريام | 24.1659 | 54.3382 | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
492 | Mussafah | ايكاد 2 | 24.303228 | 54.4499 | High | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Yes - Under Assessment | t.b.c. | t.b.c. | t.b.c. | No | AED450M 2026 cashflow required, email to SW Taskforce 28 July | [8 empty] | Contractor Design | [5 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
493 | Al Wathbah | مدينة الرياض - شارع الخير | 24.2994 | 54.677 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | [28 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 | 2026-12-30 | 2D modelling |  |  |  |  | Parsons | TRUE | Topography & Road Engineering | #REF! | 2026-12-30 | #REF!
494 | Mussafah | منطقة النوف | 24.2478 | 54.1654 | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
495 | Al Wathbah | ظهارة الطيب - أبو ظبي | 24.2105 | 54.8397 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
496 | Al Wathbah | مدينة الرياض - حوض 144 | 24.2881 | 54.6911 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
497 | Mussafah | منطقة الأريام | 24.2167 | 54.4065 | Low | Yes | مطور | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
498 | Al Wathbah | عزب دهان - الوافية | 24.209 | 54.9138 | Medium | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
499 | Al Shahama | منطقة العجبان | 24.5997 | 54.8401 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
500 | Mussafah | ايكاد 3 | 24.3108 | 54.5006 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
501 | Al Wathbah | عزب دهان | 24.195870 | 54.9685 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
502 | Al Shahama | مزارع عجبان - شارع عويد | 24.676 | 54.8319 | Low | Yes | Private | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
503 | Mussafah | ايكاد 3 | 24.2996 | 54.4905 | Medium | Yes | Private | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
504 | Al Wathbah | منطقة طريق الحفار | 24.254018 | 54.8251 | Low | No | N/A | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 0 | 1 | 0 | 0 | 864 | 864 | 10368 | 38880 | 49248 | 0 | 0 | 0 | 0 | 750000 | 0 | [13 empty] | Absense of Drainage Network | [12 empty] | FALSE | Absence of Drainage Network | #REF! | #REF! | #REF!
505 | Mussafah | ايكاد 3 | 24.299677 | 54.4849 | Medium | Yes | مطور | Yes | The network needs an upgrade |  | 1 | 5184 | 19440 | 24624 | 1 | 0 | 1 | 0 | 0 | 1440 | 0 | 1440 | 17280 | 64800 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | TRUE | Topography & Road Engineering | #REF! | #REF! | #REF!
506 | Al Wathbah | أكادمية الدفاع المدني - طريق الحفار | 24.284 | 54.8305 | Low | Yes | Private Area | No | Absense of Drainage Network |  | 1 | 5184 | 19440 | 24624 | 2 | 0 | 0 | 2 | 0 | 0 | 1728 | 1728 | 20736 | 77760 | 98496 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | Absense of Drainage Network | [6 empty] | Contractor | [5 empty] | TRUE | Absence of Drainage Network | #REF! | #REF! | #REF!
Formulas:
IDD_Completion_Date2 = IF([Hotspot_ID]="","",IF(ISNUMBER([Planned_IDD_Completion_Date]),[Planned_IDD_Completion_Date],IF(TRIM(#REF!&"")<>"",IF(ISNUMBER(IFERROR(INDEX(#REF!,MATCH(#REF!,#REF!,0)),"")),IFERROR(INDEX(#REF!,MATCH(#REF!,#REF!,0)),""),"CLIENT INPUT REQUIRED"),"CLIENT INPUT REQUIRED")))

## Sheet2 (hidden)
Hotspot_ID | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | IDD Interventoin Planned | IDD_Design_Category | Design Solution | Type of Intervention | Additional Budget Requirment | Additional Budget Requested | Hotspot Network Rain Design Event (Current) | Hotspot Network Design Technical Capacity (Current) | Hotspot Network Rain Design Event (Future) | Hotspot Network Design Technical Capacity (Future) | Flood Volume Capacity after Intervention | Associated recovery time after intervention | Planned_IDD_Mobilization_Date | Critical Infrastructure Area Phase1 Solution Completion Date | Planned_IDD_Completion_Date | Project Stage | Approval from IDAS secured (Yes/No) | Design Description | Actual_Mobilization_Date | Actual_Completion_Date | Intervention status | IDD_Owner_Name | Original 255 List
1 | Al Shahama | نفق الشهامة | 24.546 | 54.691 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 331200 |  |  | 250000 |  |  |  | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-28 | 2026-09-11 | 2026-12-11 | Contractor |  |  |  |  | 105 | Parsons | Yes
2 | Al Shahama | شارع الشيخ زايد بن سلطان | 24.4927 | 54.6493 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-20 |  | 2026-12-08 | Permitting Phase | Yes |  |  |  | 49 | Parsons | Yes
3 | Al Shahama | مجمع الجسور ياس | 24.4858 | 54.6449 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 6 | [9 empty] | 596160 |  |  |  | 1100000 |  | 60000 | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-09-11 | 2026-12-31 | Permitting Phase | Yes |  |  |  | 128 | Parsons | Yes
4 | Al Shahama | نفق الشهامة الجديدة المؤدي الى ديرفيلدز مول | 24.5378 | 54.6848 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 331200 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-09 |  | 2027-01-29 | Contractor |  |  |  |  | 51 | Parsons | Yes
5 | Al Shahama | جسر الشهامة نادي الوحدة | 24.5611 | 54.6953 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 3 | [9 empty] | 298080 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 |  | 2026-09-21 | Contractor | Yes |  |  |  | 31 | Parsons | Yes
6 | Al Shahama | نفق كيزاد | 24.7287 | 54.8168 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 298080 | [6 empty] | Yes | Detailed | Lowering Project | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 |  | 2026-12-31 | IDAS Review Phase |  |  |  |  | 154 | AECOM | Yes
7 | Al Shahama | روضة الريف – شارع الشهد | 24.4622 | 54.68 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 496800 |  |  |  | 575000 |  |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2026-12-11 | Contractor |  |  |  |  | 51 | Parsons | Yes
8 | Al Shahama | خليفة الصناعية - شارع غناضة | 24.7304 | 54.7793 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 4 | [9 empty] | 662400 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-10-08 | IDAS Review Phase |  |  |  |  | 49 | AECOM | Yes
9 | Al Shahama | منطقة الفلاح 4 | 24.4185 | 54.7241 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-11-30 | IDAS Review Phase | Yes |  |  |  | 90 | Parsons | Yes
10 | Al Shahama | منطقة الفلاح 1 | 24.4213 | 54.7472 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-25 | IDAS Review Phase | Yes |  |  |  | 82 | Parsons | Yes
11 | Al Shahama | ياس الحي الاماراتي | 24.4989 | 54.6024 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-12-08 |  | 2027-01-26 | Contractor |  |  |  |  | 49 | Parsons | Yes
12 | Al Shahama | الباهية - شارع عجيج – الباهية مدرسة أميتي | 24.5313 | 54.6376 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2026-12-11 | Contractor | Yes |  |  |  | 51 | Parsons | Yes
13 | Al Shahama | شارع عجيج - الصدر | 24.5934 | 54.6515 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-29 |  | 2027-02-16 | IDAS Review Phase |  |  |  |  | 171 | AECOM | Yes
14 | Mussafah | شارع سلطان بن محمد القبيسي - بعد الجسر المؤدي الى المصفح- الأول | 24.3736 | 54.5229 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
15 | Mussafah | مدينة الامارات الانسانية | 24.3789 | 54.5129 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 13 | [9 empty] | 2003760 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
16 | Mussafah | Sector 17 | 24.3656 | 54.4832 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 3 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
17 | Mussafah | Sector 2 | 24.3779 | 54.5221 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 3 | [9 empty] | 579600 |  |  |  |  | 750000 |  | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
18 | Mussafah | Sector 15 | 24.3736 | 54.4826 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 165600 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
19 | Mussafah | Sector 1 | 24.3792 | 54.5178 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
20 | Mussafah | Sector 1 | 24.3825 | 54.5234 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | TBC |  |  |  |  | 122 | AECOM | Yes
21 | Zayed | مدخل مصفح القادم من شارع الخليج العربي | 24.3941 | 54.5186 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 8 | [9 empty] | 1523520 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-09-11 | 2027-01-12 | Permitting Phase |  |  |  |  | 142 | Parsons | Yes
22 | Mussafah | Sector 9 | 24.3686 | 54.4914 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 10 | [9 empty] | 1854720 |  |  |  |  | 750000 |  | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | Contractor |  |  |  |  | 122 | AECOM | Yes
23 | Mussafah | دوار دينا تريد | 24.2884 | 54.5646 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 10 | [9 empty] | 1771920 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 |  | 2026-12-25 | IDAS Review Phase |  |  |  |  | 122 | Parsons | Yes
24 | Mussafah | مستودعات البلدية | 24.2934 | 54.581 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 10 | [9 empty] | 1771920 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 |  | 2026-12-11 | Permitting Phase | Yes |  |  |  | 107 | Parsons | Yes
25 | Mussafah | طريق حميم | 24.1494 | 54.4205 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 3 | [9 empty] | 430560 | [6 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-12-26 | Permitting Phase | Yes |  |  |  | 118 | Parsons | Yes
26 | Al Wathbah | مدينة الرياض - شارع طوي القايمة | 24.3314 | 54.7084 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-12-13 | 2D modelling |  |  | 2026-08-20 |  | 115 | Parsons | Yes
27 | Al Wathbah | مدينة الرياض - شارع الخير | 24.3432 | 54.7578 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 |  | 2026-12-15 | 2D modelling |  |  |  |  | 113 | Parsons | Yes
28 | Al Wathbah | مدينة الرياض - شارع العصري بن حمودة الظاهري | 24.3257 | 54.7446 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | 2026-12-15 | 2D modelling |  |  |  |  | 106 | Parsons | Yes
29 | Al Wathbah | مدينة الرياض -شارع الرياض | 24.333 | 54.7652 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 745200 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 |  | 2026-12-16 | 2D modelling |  |  |  |  | 113 | Parsons | Yes
30 | Al Wathbah | مدينة الرياض -شارع النهضة | 24.3273 | 54.7042 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | 2026-12-13 | 2D modelling |  |  |  |  | 104 | Parsons | Yes
31 | Al Wathbah | مدينة الرياض -شارع الميثاق | 24.3307 | 54.7001 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 |  | 2026-12-06 | 2D modelling |  |  |  |  | 104 | Parsons | Yes
32 | Al Wathbah | مدينة الرياض - شارع سيح القطع | 24.3364 | 54.7356 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 745200 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 |  | 2026-12-21 | 2D modelling |  |  |  |  | 121 | Parsons | Yes
33 | Al Wathbah | مدينة الرياض - شارع الصنوبر | 24.3415 | 54.7524 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-31 |  | 2026-12-13 | 2D modelling |  |  |  |  | 104 | Parsons | Yes
34 | Al Wathbah | شارع الشيخ محمد بن راشد | 24.3732 | 54.729 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 4 | [9 empty] | 993600 |  |  |  |  | 900000 | 130000 | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 | 2026-09-11 | 2026-09-11 | 2D modelling |  |  |  |  | 19 | Parsons | Yes
35 | Al Wathbah | خلف مسلخ بني ياس | 24.3037 | 54.6711 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-10-02 | 2D modelling |  |  |  |  | 33 | Parsons | Yes
36 | Al Wathbah | الشوامخ - شارع خضيرمان | 24.3535 | 54.649 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-21 |  | 2027-01-28 | Parsons Phase |  |  |  |  | 99 | Parsons | Yes
37 | Al Wathbah | الشوامخ - مدخل ومخرج المزن | 24.3505 | 54.6802 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 |  | 2026-12-15 | Permitting Phase | Yes |  |  |  | 100 | Parsons | Yes
38 | Al Wathbah | شارع الشوامخ | 24.3855 | 54.6702 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 |  | 2026-09-07 | IDAS Review Phase | Yes |  | 2026-06-13 |  | 86 | Parsons | Yes
39 | Al Wathbah | دوار - الشوامخ 12 | 24.3843 | 54.6745 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-13 |  | 2026-09-08 | IDAS Review Phase | Yes |  | 2026-06-13 |  | 87 | Parsons | Yes
40 | Al Wathbah | مدينة الرياض -شارع الخير | 24.3221 | 54.749 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-12-17 | 2D Modelling |  |  |  |  | 104 | Parsons | Yes
41 | Al Wathbah | الشوامخ 7 - شارع بدع بوحصية | 24.3721 | 54.6705 | Medium | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 | [6 empty] | Yes | Detailed | Upgrade Inlet | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-12-21 | IDAS Review Phase | yes |  |  |  | 111 | Parsons | Yes
42 | Al Wathbah | مسجد الشيخة عفراء بنت زايد ال نهيان | 24.1836 | 54.9937 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-30 | Permitting Phase | Yes |  |  |  | 87 | Parsons | Yes
43 | Al Wathbah | الختم القديمة - بجوار حديقة الختم | 24.1881 | 54.9966 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-11-26 | Permitting Phase | Yes |  |  |  | 86 | Parsons | Yes
44 | Al Wathbah | بني ياس - شارع اليال | 24.3293 | 54.6331 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-05 |  | 2026-11-30 | IDAS Review Phase |  |  |  |  | 86 | Parsons | Yes
45 | Al Wathbah | بني ياس -شارع اليال | 24.3218 | 54.6427 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-06 |  | 2026-11-12 | IDAS Review Phase |  |  |  |  | 67 | Parsons | Yes
46 | Al Wathbah | بني ياس -شارع اليال | 24.3144 | 54.6534 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 |  | 2026-08-25 | Permitting Phase | Yes |  | 2026-06-15 |  | 71 | Parsons | Yes
47 | Al Wathbah | بني ياس - شارع اليال | 24.3069 | 54.6633 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-15 |  | 2026-08-25 | Permitting Phase | Yes |  | 2026-06-15 |  | 71 | Parsons | Yes
48 | Al Wathbah | بني ياس - شارع الشيخ محمد بن راشد | 24.2888 | 54.6549 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 | [6 empty] | Yes | Fast- tracked | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-15 | 2026-09-11 | 2026-09-11 | IDAS Review Phase |  |  | 2026-08-15 |  | 27 | Parsons | Yes
49 | Al Wathbah | بني ياس - شارع الخويرة | 24.3044 | 54.6281 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-30 |  | 2026-12-27 | Permitting Phase | Yes |  |  |  | 119 | Parsons | Yes
50 | Al Wathbah | نفق الوثبة | 24.2693 | 54.6681 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 993600 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2027-01-24 | Contractor |  |  |  |  | 139 | Parsons | Yes
51 | Al Wathbah | نفق النهضة | 24.2417 | 54.7368 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-20 |  | 2027-01-01 | Contractor |  |  |  |  | 103 | Parsons | Yes
52 | Al Wathbah | الوثبة - شارع الحفظة | 24.2681 | 54.673 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-12-20 | Contractor |  |  |  |  | 104 | Parsons | Yes
53 | Al Wathbah | الوثبة جنوب | 24.2663 | 54.6578 | Medium | Yes | Developer (Al Dar) | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 165600 | [6 empty] | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-12 | IDAS Review Phase |  |  |  |  | 69 | Parsons | Yes
54 | Al Wathbah | بني ياس - شارع الجزائر | 24.2758 | 54.6451 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-07 | IDAS Review Phase | [5 empty] | Parsons | Yes
55 | Al Wathbah | الوثبة - شارع الرسوخ - بجانب منتزة الوثبة | 24.2458 | 54.7097 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 |  | 2026-11-18 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
56 | Al Wathbah | الوثبة - شارع النهضة | 24.269 | 54.684 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 |  | 2026-12-07 | Permitting Phase | Yes |  | 2026-08-06 |  |  | Parsons | Yes
57 | Al Wathbah | بني ياس - شارع السهل | 24.2701 | 54.6498 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-03 |  | 2026-12-18 | Permitting Phase | Yes |  | 2026-08-03 |  |  | Parsons | Yes
58 | Al Wathbah | الشامخة - بالقرب من الشامخة مول | 24.3999 | 54.7328 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  | 400000 |  | 33000 | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-12-19 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
59 | Al Wathbah | الشامخة - شارع احمد بن شملان الفلاحي | 24.3937 | 54.7044 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-17 | IDAS Review Phase | [5 empty] | Parsons | Yes
60 | Al Wathbah | الشامخة - تقاطع شارع الترشيد مع شارع ام الثعالب | 24.411 | 54.747 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-07 |  | 2026-12-23 | Permitting Phase | Yes |  | 2026-08-07 |  |  | Parsons | Yes
61 | Al Wathbah | الشامخة -شارع محمد بن شبيب المهيري | 24.3954 | 54.6943 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-24 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
62 | Al Wathbah | الشامخة -شارع الرضى | 24.3759 | 54.6992 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-12-25 | IDAS Review Phase | Yes |  |  |  |  | Parsons | Yes
63 | Al Wathbah | الشامخة -شارع العايد | 24.3507 | 54.6832 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-11-22 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
64 | Al Wathbah | الشامخة - تقاطع شارع دمية طحنون مع شارع الخزنه | 24.4078 | 54.7358 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-11-16 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
65 | Al Wathbah | العدلة - شارع طوي بو صلف | 24.4182 | 54.8663 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-08 |  | 2026-12-07 | Contractor | Yes |  |  |  |  | Parsons | Yes
66 | Al Wathbah | العدلة - شارع طوي اشعب | 24.4114 | 54.8677 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-20 |  | 2026-09-17 | Permitting Phase | Yes |  | 2026-08-20 |  |  | Parsons | Yes
67 | Al Wathbah | عزب العدلة | 24.3853 | 54.9003 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | N/A | N/A |  | 2026-07-26 |  |  | Parsons | Yes
68 | Al Wathbah | مدخل المحاجر في العدلة | 24.3869 | 54.9001 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | N/A | N/A |  | 2026-07-26 |  |  | Parsons | Yes
69 | Al Wathbah | مزارع العدلة | 24.3831 | 54.895 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | N/A |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-26 |  | 2026-10-02 | N/A | N/A |  | 2026-07-26 |  |  | Parsons | Yes
70 | Al Wathbah | الفاية الصناعية | 24.3082 | 54.8788 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-17 | Contractor | [5 empty] | Parsons | Yes
71 | Island | مواقف سيارات حديقه ام الامارات- المشرف / شارع الند ، غرب 24/2 | 24.4523 | 54.3841 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 3 | [9 empty] | 298080 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 |  | 2026-10-10 | IDAS Review Phase | [5 empty] | AECOM | Yes
72 | Island | الدوار المؤدي الى نادي ضباط الشرطة. | 24.4054 | 54.4707 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 331200 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-28 | Parsons Phase | [5 empty] | AECOM | Yes
73 | Island | المشرف / غرب52 / شارع احمد بن سعيد الرميثي | 24.4359 | 54.3954 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 331200 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-12 |  | 2026-11-28 | IDAS Review Phase | [5 empty] | AECOM | Yes
74 | Island | تقاطع شارع الشيخ راشد بن سعيد مع تقاطع شارع الشيخة فاطمة بنت مبارك (مقابل مبنى دائرة الاشغال سابقا) | 24.4624 | 54.3763 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Hand over phase | N/A |  |  |  |  | AECOM | Yes
75 | Island | شارع اليزوة – الخالدية مقابل (سبينس- الكورنيش) | 24.4673 | 54.3343 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 397440 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-05 | Contractor | [5 empty] | AECOM | Yes
76 | Island | شارع الكورنيش (مدخل بوابة قصر الامارات) | 24.4574 | 54.319 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 5 |  |  | 248400 | 3 | [9 empty] | 596160 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-10 | Contractor | [5 empty] | AECOM | Yes
77 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4639 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 3 | [9 empty] | 364320 | [6 empty] | Yes | Critical Infrastructure | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
78 | Island | مواقف سيارات مستشفي جلوبال كير | 24.4646 | 54.3658 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Implementation Phase | N/A |  |  |  |  | AECOM | Yes
79 | Island | شارع المطار مقابل قصر المنهل | 24.479 | 54.3624 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
80 | Island | مرسي البطين جوار مبني تبريد | 24.4544 | 54.3378 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-19 | Contractor | [5 empty] | AECOM | Yes
81 | Island | بجوار مواقف سيارات المارينا مول | 24.4731 | 54.3201 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-27 | Contractor | [5 empty] | AECOM | Yes
82 | Island | مدارس التكنولوجيا التطبيقيه بمنطقه ال نهيان | 24.4672 | 54.3781 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 397440 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-19 | Contractor | [5 empty] | AECOM | Yes
83 | Island | شارع الشيخة فاطمة بنت مبارك - مقابل مدرسة الامارات الوطنية | 24.4694 | 54.3851 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | IDAS Review Phase | [5 empty] | Parsons | Yes
84 | Island | حوض E-25 - قريب من مبنى مبادلة | 24.4618 | 54.3936 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 12 |  |  | 397440 | 9 | [9 empty] | 1540080 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 |  | 2026-11-16 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
85 | Al Shahama | شارع الشيخ زايد بين مجمع جسور ياس و جسر المطار بالاتجاهين | 24.4749 | 54.6365 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 8 |  |  | 397440 | 12 | [9 empty] | 1920960 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2026-12-31 | IDAS Review Phase | [5 empty] | Parsons | Yes
86 | Mussafah | نفق الصناعية الاول باتجاه الداخل | 24.3735 | 54.5219 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 4 | [9 empty] | 745200 |  |  |  |  | 525000 |  | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
87 | Mussafah | نفق الصناعية الثاني باتجاه الداخل | 24.3465 | 54.5226 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 2 | [9 empty] | 414000 |  |  |  |  | 2100000 |  | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
88 | Al Shahama | مخرج الجسر من الشامخة للفلاح باتجاه دبي | 24.4106 | 54.6815 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 975000 | 60000 | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-12-20 | Permitting Phase | Yes |  | 2026-08-19 |  |  | Parsons | Yes
89 | Al Shahama | مخرج جسر سويحان للقادم من جسر كرم الشام باتجاه الشامخة الفلاح | 24.4025 | 54.6703 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  |  | 840000 | 60000 | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-12-23 | Permitting Phase | Yes |  | 2026-08-19 |  |  | Parsons | Yes
90 | Zayed | شارع الخليج العربي المخرج المؤدي لشارع العين | 24.3914 | 54.5291 | Very High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 414000 | [5 empty] | 33000 | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
91 | Zayed | جسر تعليم القيادة بالاتجاهين | 24.347 | 54.5289 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | Quick Wins | Maintanence |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-06-30 |  | 2026-07-30 | Implementation Phase | N/A |  | 2026-06-30 |  |  | Parsons | Yes
92 | Zayed | جسر المفرق للقادم من مدينة شخبوط الطبية باتجاه ابوظبي | 24.313 | 54.6036 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-30 |  | 2026-09-01 | IDAS Review Phase |  |  | 2026-07-30 |  |  | Parsons | Yes
93 | Al Shahama | شارع محمد بن راشد للقادم من دبي تم تحويل الحركة باتجاه الشامخة | 24.4242 | 54.7646 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2026-11-23 | Permitting Phase | Yes |  | 2026-08-19 |  |  | Parsons | Yes
94 | Zayed | شارع ابوظبي - العين مدخل شارع الخدمات قبل جسر مزيد مول باتجاه الخارج | 24.3886 | 54.5401 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  | 300000 |  | 645000 | 60000 | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
95 | Al Shahama | النفق المودي للشهامة للقادم من روضة الريف | 24.5429 | 54.6941 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  | 40000 |  | 645000 | 60000 | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-28 | 2026-09-11 | 2026-12-11 | Contractor | [5 empty] | Parsons | Yes
96 | Al Wathbah | طريق سويحان بعد جسر الفلاح الشامخة باتجاه سويحان | 24.4188 | 54.7506 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 17 | [9 empty] | 3924720 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-19 | 2026-09-11 | 2027-01-09 | Parsons Phase |  |  | 2026-08-19 |  |  | Parsons | Yes
97 | Zayed | على طول شارع ذياب بن عيسى في مدينة خليفة أ بالاتجاهين | 24.4025 | 54.5725 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 |  | 2026-07-11 | Implementation Phase | yes |  | 2026-07-05 |  |  | Parsons | Yes
98 | Zayed | شارع الشيخ مكتوم بن راشد مقابل مستشفى شخبوط باتجاه الغربية | 24.3205 | 54.6125 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 149040 | 10 | [9 empty] | 1391040 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-27 |  | 2026-09-08 | Implementation Phase | [5 empty] | Parsons | Yes
99 | Zayed | طريق ابوظبي العين قبل جسر محوي باتجاه الداخل | 24.3461 | 54.5731 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 496800 |  |  |  | 600000 | 645000 | 60000 | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2026-09-11 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
100 | Al Wathbah | شارع الشيخ مكتوم بن راشد عن حسر كرم الشام (الشوامخ) باتجاه دبي | 24.3726 | 54.6562 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 331200 |  |  |  |  | 1140000 | 60000 | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-17 | 2026-09-11 | 2026-11-27 | Permitting Phase | Yes |  | 2026-08-17 |  |  | Parsons | Yes
101 | Zayed | مدينة خليفة | 24.4406 | 54.6002 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Quick Wins | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-06 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-06 |  |  | Parsons | Yes
102 | Zayed | مدينة خليفة | 24.4149 | 54.502 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
103 | Zayed | منطقة ربدان | 24.4112 | 54.5082 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-10 |  | 2026-10-23 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
104 | Zayed | منطقة ربدان | 24.4028 | 54.5272 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
105 | Zayed | منطقة ربدان | 24.3493 | 54.6215 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-30 | IDAS Review Phase | [5 empty] | Parsons | Yes
106 | Zayed | مدينة شخبوط | 24.365 | 54.6482 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-06 |  | 2026-09-22 | IDAS Review Phase |  |  | 2026-08-06 |  |  | Parsons | Yes
107 | Zayed | مدينة شخبوط | 24.405 | 54.5193 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 |  | 2026-10-27 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
108 | Zayed | منطقة ربدان | 24.3306 | 54.5368 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-20 | Contractor | [5 empty] | Parsons | Yes
109 | Zayed | مدينة محمد بن زايد | 24.4074 | 54.5026 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-03 |  | 2026-10-30 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
110 | Zayed | مدينة زايد | 24.3831 | 54.5948 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-05 |  | 2026-08-10 | Hand over phase | N/A |  | 2026-07-05 |  |  | Parsons | Yes
111 | Zayed | مدينة زايد | 24.3796 | 54.5576 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-25 |  | 2026-09-16 | IDAS Review Phase |  |  | 2026-07-25 |  |  | Parsons | Yes
112 | Zayed | ساس النخل - مدينة زايد | 24.4187 | 54.4962 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-02 | Contractor | [5 empty] | Parsons | Yes
113 | Zayed | ربدان - ساس النخل | 24.3925 | 54.5033 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
114 | Zayed | شارع جبر بن راشد الحلامي - طريق ساس النخل | 24.4237 | 54.5229 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 3 | [9 empty] | 298080 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 |  | 2026-12-10 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
115 | Zayed | مدينة محمد بن زايد | 24.308 | 54.5813 | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-23 |  | 2026-12-10 | Contractor | Yes |  |  |  |  | Parsons | Yes
116 | Zayed | مدينة زايد | 24.3846 | 54.633 | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-15 |  | 2026-08-17 | Hand over phase | N/A |  | 2026-07-15 |  |  | Parsons | Yes
117 | Zayed | مدينة زايد | 24.3542 | 54.6106 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-21 |  | 2026-08-16 | Hand over phase | N/A |  | 2026-07-21 |  |  | Parsons | Yes
118 | Zayed | مدينة زايد | 24.3665 | 54.6067 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-12 |  | 2026-08-14 | Hand over phase | N/A |  | 2026-07-12 |  |  | Parsons | Yes
119 | Zayed | مدينة محمد بن زايد - شارع خليفة بن خميس الديهلي | 24.3403 | 54.5579 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-13 | [6 empty] | Parsons | Yes
120 | Zayed | مدينة محمد بن زايد | 24.2968 | 54.5634 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 |  | 2026-09-15 | Contractor | Yes |  |  |  |  | Parsons | Yes
121 | Zayed | Zayed City | 24.3686 | 54.6005 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Quick Wins | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-22 |  | 2026-07-30 | Hand over phase | N/A |  | 2026-07-22 |  |  | Parsons | Yes
122 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.3994 | 54.5932 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 |  | 2026-10-03 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
123 | Zayed | ربدان - شارع راشد بن جابر الهاملي | 24.4106 | 54.4965 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-09 |  | 2026-10-24 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
124 | Zayed | مدينة محمد بن زايد | 24.3176 | 54.5332 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-18 |  | 2026-09-17 | IDAS Review Phase |  |  | 2026-08-18 |  |  | Parsons | Yes
125 | Zayed | مدينة محمد بن زايد - MZ 17 | 24.3896 | 54.6092 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
126 | Zayed | مدينة زايد | 24.379 | 54.5851 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Fast- tracked | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-25 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
127 | Zayed | ربدان | 24.4029 | 54.5038 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-25 | Permitting Phase | Yes |  | 2026-08-10 |  |  | Parsons | Yes
128 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4097 | 54.6368 | High | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-11 | 2027-01-12 | Contractor | Yes |  |  |  |  | Parsons | Yes
129 | Zayed | طريق الخليج العربي - من جسر الكريكت لجسر سويجان | 24.4102 | 54.6436 | High | Yes | ADM Developer | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-11 | 2027-01-12 | Contractor | Yes |  |  |  |  | Parsons | Yes
130 | Zayed | مدينة زايد | 24.3704 | 54.6183 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-06 | Contractor | [5 empty] | Parsons | Yes
131 | Zayed | مدينة خليفة | 24.4334 | 54.5769 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 1 |  |  | 49680 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-04 |  |  | Parsons | Yes
132 | Al Shahama | مدينة الفلاح | 24.4283 | 54.7364 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-01 |  | 2026-10-23 | IDAS Review Phase | Yes |  |  |  |  | Parsons | Yes
133 | Al Shahama | الشهامة | 24.5196 | 54.6716 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-26 | Contractor | Yes |  |  |  |  | Parsons | Yes
134 | Mussafah | مصفح صناعية | 24.326 | 54.5162 | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 10 | [9 empty] | 1788480 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
135 | Al Shahama | الباهية | 24.6264 | 54.7119 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-24 | Implementation Phase | Yes |  |  |  |  | AECOM | Yes
136 | Al Wathbah | طريق رزين | 24.1576 | 54.8458 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-17 | Contractor | [5 empty] | Parsons | Yes
137 | Al Shahama | شارع خليفة بن زايد - الريف | 24.4615 | 54.702 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-09-09 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
138 | Al Wathbah | الوثبة جنوب | 24.2609 | 54.673 | Low | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-17 | Contractor | Yes |  |  |  |  | Parsons | Yes
139 | Al Shahama | مدينة الفلاح | 24.4258 | 54.7426 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-02 |  | 2026-12-20 | IDAS Review Phase | Yes |  |  |  |  | Parsons | Yes
140 | Zayed | مدينة خليفة - دوار طيران الرئاسة | 24.436 | 54.6253 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 745200 | [6 empty] | Yes | Quick Wins | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 |  | 2026-07-25 | Hand over phase | N/A |  | 2026-07-18 |  |  | Parsons | Yes
141 | Mussafah | مصفح صناعية | 24.35 | 54.4939 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 12 | [9 empty] | 2119680 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | TBC | [5 empty] | AECOM | Yes
142 | Al Wathbah | طريق الحفار | 24.3855 | 54.8443 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-30 | Contractor | [5 empty] | Parsons | Yes
143 | Al Shahama | الرحبة | 24.5965 | 54.695 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-02 | Contractor | [5 empty] | AECOM | Yes
144 | Al Wathbah | شارع بني ياس بالقرب من محطة البترول | 24.2968 | 54.6285 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-04 |  | 2026-11-12 | IDAS Review Phase | [5 empty] | Parsons | Yes
145 | Al Wathbah | مدينة الرياض | 24.3514 | 54.7125 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-09-11 | 2026-09-11 | IDAS Review Phase | [5 empty] | Parsons | Yes
146 | Al Wathbah | الوثبة جنوب | 24.2625 | 54.6587 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-30 | Contractor | [5 empty] | Parsons | Yes
147 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.642 | 54.6575 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 1 |  |  | 49680 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-10 | Implementation Phase | Yes |  |  |  |  | AECOM | Yes
148 | Al Shahama | الطريق المؤدي الى شاطى الشليلية | 24.6811 | 54.6692 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-18 | Contractor | [5 empty] | AECOM | Yes
149 | Al Shahama | شارع مكتوم بن راشد | 24.6959 | 54.7814 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-26 | Contractor | [5 empty] | AECOM | Yes
150 | Al Shahama | شارع سلطان بن زايد - الريف | 24.4711 | 54.6709 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-21 |  | 2026-09-11 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
151 | Al Shahama | طريق الطف | 24.5973 | 54.9097 | Low | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Network New | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-08 | Contractor | [5 empty] | AECOM | Yes
152 | Al Shahama | الصدر- شارع عويد | 24.7557 | 54.7337 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 | [6 empty] | Yes | Detailed | Pond / Spillway | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-16 | Permitting Phase | Yes |  |  |  |  | AECOM | Yes
153 | Al Shahama | خليفة الصناعية - 6 | 24.7631 | 54.7003 | Low | Yes | Developer (AD ports) | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-24 | Permitting Phase | Yes |  |  |  |  | AECOM | Yes
154 | Al Shahama | مدينة الفلاح | 24.4322 | 54.7315 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 347760 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-28 | Contractor | Yes |  |  |  |  | Parsons | Yes
155 | Al Shahama | مدينة الفلاح | 24.4395 | 54.7408 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 248400 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-28 | Contractor | Yes |  |  |  |  | Parsons | Yes
156 | Al Wathbah | طريق أبو ظبي - العين | 24.3074 | 54.6051 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Fast- tracked | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-09 | 2026-09-09 | IDAS Review Phase | [5 empty] | Parsons | Yes
157 | Al Shahama | مدينة الفلاح | 24.4613 | 54.7361 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-01 |  | 2026-09-11 | Permitting Phase | Yes |  | 2026-08-01 |  |  | Parsons | Yes
158 | Al Shahama | شارع مكتوم بن راشد باتجاه السمحة القديمة | 24.6864 | 54.7736 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-24 | Contractor | [5 empty] | AECOM | Yes
159 | Al Shahama | دوار على شارع مكتوم بن راشد | 24.7976 | 54.8637 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-02 | Contractor | [5 empty] | AECOM | Yes
160 | Al Wathbah | طريق أبو ظبي - العين | 24.2812 | 54.6473 | Medium | Yes | Developer | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Contractor | [5 empty] | Parsons | Yes
161 | Island | خلف مدرسه الامام الغزالي- شارع مطر المهيري - غرب 16 | 24.4583 | 54.3414 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
162 | Island | شارع المطلع - شارع الخليج العربي - غرب 52 | 24.437 | 54.3736 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-27 | Contractor | [5 empty] | AECOM | Yes
163 | Island | مرسي البطين جوار مرسى اليخوت 1 | 24.4507 | 54.3348 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Contractor | [5 empty] | AECOM | Yes
164 | Island | شارع خليفة بن شخبوط - غرب 17-1- مواقف سيارات مدرسه هزاع بن زايد الاول | 24.4607 | 54.3575 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
165 | Island | تقاطع شارع الخليج العربي مع شارع الشيخ هزاع | 24.457 | 54.3552 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 5 | [9 empty] | 563040 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Contractor | [5 empty] | AECOM | Yes
166 | Island | شارع الشيخ زايد بن سلطان تقاطع شارع ظفير -النفق | 24.445 | 54.4379 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Contractor | [5 empty] | AECOM | Yes
167 | Island | مناره المقطع - جوار جسر المقطع | 24.4214 | 54.4818 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Contractor | [5 empty] | AECOM | Yes
168 | Island | جراند الامارات - شارع هزاع بن زايد تقاطع شارع الشيخ سلطلن بن زايد | 24.4741 | 54.3748 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 4 | [9 empty] | 397440 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-11 | Contractor | [5 empty] | AECOM | Yes
169 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع الفلاح | 24.4831 | 54.3758 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-11 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
170 | Island | مقابل فندق كرستال ابو ظبي- شرق 14 بالقرب من مركز مدينة زايد للتسوق | 24.4848 | 54.3636 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-12 | Contractor | [5 empty] | AECOM | Yes
171 | Island | شارع سعيد بن احمد العتيبة تقاطع شارع زايد الأول | 24.4891 | 54.3699 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
172 | Island | شارع الظفرة تقاطع شارع الخليج العربي- جوار دوار مجلس المشرف | 24.425 | 54.4108 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-04 | Contractor | [5 empty] | AECOM | Yes
173 | Island | شارع زايد بن سلطان بين تقاطع شاع زايد الأول وشارع محمد بن بطي ال حامد - مقابل مطعم قصر الهند | 24.4928 | 54.3766 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
174 | Island | منطقه المزون | 24.4145 | 54.4314 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-27 | Contractor | [5 empty] | AECOM | Yes
175 | Island | شارع الظفرة بين شارع راشد بن زايد وشارع الخليج العربي | 24.4279 | 54.4108 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
176 | Island | شارع سلامة بن بطي بين شارع راشد بن زايد وشارع الخليج العربي | 24.4339 | 54.4033 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
177 | Island | مدخل منطقة روضة ابوظبي من شارع الشيخ راشد بن سعيد- قرب مطار البطين | 24.417 | 54.47 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
178 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع هزاع | 24.4704 | 54.3701 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
179 | Island | شارع الشيخ راشد بن سعيد - تقاطع شارع الشيخ محمد بن خليفة- مقابل محمصه الامراء | 24.459 | 54.3814 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Hand over phase | N/A |  |  |  |  | AECOM | Yes
180 | Island | منطقة المعمورة - بجانب مبنى دائرة البلديات والنقل | 24.4617 | 54.3936 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 8 | [9 empty] | 1159200 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-12 |  | 2026-11-14 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
181 | Island | جزيره الجبيل - شارع خليفه بن زايد | 24.5406 | 54.4836 | Low | Yes | مطور | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
182 | Island | دوار شارع الحريه - جزيره الريم | 24.482 | 54.4047 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Contractor | [5 empty] | AECOM | Yes
183 | Island | جزيره السعديات - جوار مسجد الحمد | 24.5385 | 54.4396 | Medium | Yes | مطور | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-12-31 | Contractor | [5 empty] | AECOM | Yes
184 | Island | شارع الشيخ راشد بن سعيد - جسر الجوازات | 24.4444 | 54.3952 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 6 |  |  | 298080 | 6 | [9 empty] | 596160 | [6 empty] | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Contractor | [5 empty] | AECOM | Yes
185 | Island | شارع سلطان بن زايد من تقاطغ شارع سلامة بن بطي الى شارع الظفرة- مقابل مطعم اليمن السعيد شارع المرور | 24.4397 | 54.4118 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-28 | Contractor | [5 empty] | AECOM | Yes
186 | Island | مدخل قصر البحر | 24.4724 | 54.3927 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 3 | [9 empty] | 447120 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-29 |  | 2026-12-23 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
187 | Island | مينا زايد تابع للمطور | 24.5171 | 54.3729 | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-20 | Contractor | [5 empty] | AECOM | Yes
188 | Island | الشارع من أرض المعارض لدوار الجوية- شارع السفارات | 24.4235 | 54.4444 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-11-25 | Contractor | [5 empty] | AECOM | Yes
189 | Mussafah | نفق المصفح الثاني باتجاه الخارج | 24.3473 | 54.5254 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | Critical Infrastructure |  | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-50 yr + 20% climate change factor | 81.84mm (+16.37mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | TBC | [5 empty] | AECOM | Yes
190 | Al Shahama | الشهامة الجديدة | 24.5431 | 54.6917 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-27 | 2026-09-11 | 2026-12-11 | Contractor | Yes |  |  |  |  | Parsons | Yes
191 | Al Shahama | نفق ياس | 24.461 | 54.6111 | High | Yes | Developer (ICT) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-27 | 2026-09-11 | 2027-01-12 | Contractor | [5 empty] | Parsons | Yes
192 | Zayed | طريق الخليج العربي مقابل ملعب الكريكت | 24.3924 | 54.5486 | Very High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  | 550000 |  | 60000 | Yes | Fast- tracked | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
193 | Zayed | قبل الجسر المؤدي لمحمد بن زايد | 24.3772 | 54.551 | High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 165600 |  |  |  |  | 750000 |  | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-20 | Contractor | [5 empty] | Parsons | Yes
194 | Al Wathbah | بحيرة بني ياس | 24.3032 | 54.6275 | Very High | Yes | Developer (Musanada) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-23 |  | 2026-12-28 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
195 | Al Wathbah | شارع الزود - بني ياس | 24.3094 | 54.6156 | High | Yes | Private | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 15 | [9 empty] | 2848320 |  |  |  |  | 750000 |  | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 |  | 2026-12-30 | Permitting Phase | Yes |  | 2026-08-16 |  |  | Parsons | Yes
196 | Zayed | قبل الجسر المؤدي للمفرق الصناعية | 24.2921 | 54.5592 | Very High | Yes | Private | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  | 1340000 |  | 60000 | Yes | Detailed | Road Levels | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
197 | Zayed | شارع النصيلة- مدينة محمد بن زايد | 24.3244 | 54.5305 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-25 | 2026-09-07 | 2026-09-11 | Contractor | [5 empty] | Parsons | Yes
198 | Zayed | شارع النصيلة- مدينة محمد بن زايد - قبل الجسر | 24.3263 | 54.5841 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 6 | [9 empty] | 1490400 |  |  |  |  | 1000000 |  | Yes | Detailed | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-24 | 2026-09-11 | 2026-10-01 | Contractor | Yes |  |  |  |  | Parsons | Yes
199 | Zayed | الجسر المؤدي الى المصفح - طريق أبو ظبي - العين | 24.3278 | 54.5859 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 5 |  |  | 248400 | 4 | [9 empty] | 993600 |  |  |  |  | 2100000 |  | Yes | Detailed | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 | 2026-09-11 | 2026-10-08 | Contractor | Yes |  | 2026-08-10 |  |  | Parsons | Yes
200 | Al Wathbah | الشوامخ - تقاطع شارع طوي القامة مع شارع المورد | 24.3598 | 54.6677 | High | Yes | Mainland | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-26 |  | 2026-11-11 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
201 | Zayed | مدينة خليفة | 24.4244 | 54.5449 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 |  | 2026-07-10 | Hand over phase | N/A |  | 2026-07-03 |  |  | Parsons | Yes
202 | Zayed | مدينة خليفة | 24.3958 | 54.555 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Maintanence | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-04 |  | 2026-07-11 | Hand over phase | N/A |  | 2026-07-04 |  |  | Parsons | Yes
203 | Zayed | مدينة خليفة | 24.4297 | 54.5634 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Maintanence | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-03 |  | 2026-07-10 | Hand over phase | N/A |  | 2026-07-03 |  |  | Parsons | Yes
204 | Zayed | مدينة خليفة | 24.4264 | 54.535 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 1 |  |  | 49680 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-22 |  | 2026-10-05 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
205 | Zayed | مدينة خليفة - طريق المطار | 24.4482 | 54.6131 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 5 |  |  | 248400 | 2 | [9 empty] | 198720 | [5 empty] | 33000 | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-26 | 2026-09-11 | 2027-01-12 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
206 | Zayed | مدينة خليفة | 24.4467 | 54.6181 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-13 | 2026-09-11 | 2027-01-12 | Hand over phase | N/A |  | 2026-07-13 |  |  | Parsons | Yes
207 | Island | جسر دلما | 24.4668 | 54.3829 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 4 |  |  | 198720 | 3 | [9 empty] | 745200 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-11 |  | 2026-12-15 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
208 | Mussafah | مدخل قاعدة الظفرة الجوية | 24.2821 | 54.5414 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 5 |  |  | 248400 | 6 | [9 empty] | 993600 |  |  |  | 1600000 | 2602500 | 100000 | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | T.B.C |  | T.B.C | Contractor | Yes |  |  |  |  | Parsons | Yes
214 | Mussafah | مصفح صناعية | 24.3284 | 54.5262 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 4 |  |  | 198720 | 6 | [9 empty] | 1092960 |  |  |  |  | 750000 |  | Yes | Critical Infrastructure | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-10 |  | 2026-09-16 | Permitting Phase | Yes |  |  |  |  | AECOM | Yes
221 | Zayed | مدينة محمد بن زايد - Z9_01 | 24.3741 | 54.5364 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
222 | Zayed | مدينة محمد بن زايد - Z1 | 24.3733 | 54.5395 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | Contractor | [5 empty] | Parsons | Yes
223 | Zayed | مدينة محمد بن زايد - Z9 | 24.36 | 54.5372 | High | Yes | Private area | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  |  | 750000 |  | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-29 | Contractor | [5 empty] | Parsons | Yes
224 | Zayed | مدينة محمد بن زايد - Z5 | 24.353 | 54.5554 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-06 | Contractor | [5 empty] | Parsons | Yes
226 | Zayed | مدينة محمد بن زايد - Z9 | 24.3474 | 54.538 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 3 |  |  | 149040 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-30 | Contractor | [5 empty] | Parsons | Yes
265 | Zayed | ربدان - RB28 | 24.3984 | 54.5024 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2027-01-31 | [6 empty] | AECOM | Yes
267 | Zayed | المخرج الى طريق دبي - من طريق أبو ظبي العين | 24.4142 | 54.5066 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Intermediate | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-09-25 | IDAS Review Phase | [5 empty] | Parsons | Yes
268 | Zayed | المخرج الى شارع الشيخ زايد - ساس النخل | 24.4193 | 54.5136 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-03 | Contractor | [5 empty] | Parsons | Yes
273 | Zayed | مدينة خليفة | 24.4145 | 54.5393 | Medium | Yes | Al Dar | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 331200 |  |  |  |  | 750000 |  | Yes | Fast- tracked |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-13 | Contractor | [5 empty] | Parsons | Yes
279 | Zayed | مدينة خليفة - شارع المطار بالاتجاه لأبو ظبي | 24.3978 | 54.5738 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  |  |  | 750000 |  | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-07 |  | 2026-10-17 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
295 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4384 | 54.5776 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-14 |  | 2026-10-26 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
296 | Zayed | مدينة خليفة - الراحة - طريق أبو ظبي دبي - بالاتجاه الى دبي | 24.4427 | 54.5933 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Fast- tracked | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-21 |  | 2026-10-31 | Permitting Phase | Yes |  |  |  |  | Parsons | Yes
297 | Zayed | مدينة شخبوط - طريق سويحان باتجاه الى طريق المفرق | 24.4094 | 54.6638 | Very High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 496800 |  |  |  | 940000 |  | 60000 | Yes | D |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-09-22 |  | 2026-10-13 | Contractor | [5 empty] | Parsons | Yes
376 | Island | جوار نيشن تاور | 24.4633 | 54.3288 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
377 | Island | شارع الاواصر | 24.4656 | 54.3357 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
378 | Island | شارع الاواصر | 24.4661 | 54.3366 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
379 | Island | ابراج الساحل | 24.4664 | 54.335 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
380 | Island | اسبنس الكورنيش | 24.4659 | 54.3345 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
381 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4696 | 54.3373 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
382 | Island | خلف مدرسه سابس العالميه | 24.4628 | 54.3411 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
383 | Island | خلف مدرسه سابس العالميه | 24.4626 | 54.3407 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
384 | Island | مواقف مجمع سلامه السكني الكورنيش | 24.4695 | 54.3377 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
385 | Island | كليه ابو ظبي للاداره | 24.4848 | 54.3536 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
386 | Island | شارع المطار مدخل قصر الحصن | 24.4835 | 54.358 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
390 | Island | مجمع الكرامه | 24.4641 | 54.3728 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | New Inlet and Pipes |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | IDAS Review Phase | [5 empty] | AECOM | Yes
391 | Island | خلف فندق فلايجيو شارع المطار | 24.4653 | 54.3744 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
393 | Island | شارع الشيخه فاطمه اتجاه البطين تقاطع شارع المطار | 24.4636 | 54.3777 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 3 | [9 empty] | 298080 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
394 | Island | شارع المطار اتجاه الخارج قبل تقاطع الشيخه فاطمه | 24.4646 | 54.3757 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
395 | Island | تقاطع الشيخه فاطمه مع شارع الكرامه | 24.4597 | 54.3733 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
396 | Island | صيدليه المركز الامريكي جوار مجمع ليوا | 24.4575 | 54.371 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
405 | Island | مسجد خالد بن الوليد منطقه البطين | 24.4514 | 54.3551 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
408 | Island | جسر شارع الشيخ خليفه بن زايد اتجاه السعديات | 24.5151 | 54.3925 | Medium | Yes | مطور | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
412 | Island | فندق هلا ارجان- الزاهية | 24.502 | 54.377 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
415 | Island | خلف المركز الاجتماعي الهندي | 24.5088 | 54.3794 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
416 | Island | مواقف سيارات سوق السجاد | 24.5116 | 54.3834 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Hand over phase | N/A |  |  |  |  | AECOM | Yes
418 | Island | شارع خليفه بن زايد تقاطع شارع المينا | 24.5091 | 54.3824 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
419 | Island | جسر الماريا شارع حمدان بن محمد | 24.5021 | 54.3813 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 1 |  |  | 49680 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
420 | Island | شارع السلام قبل تقاطع شارع حمدان | 24.4956 | 54.374 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
431 | Island | خلف مسجد حمد خليفه الخلفان | 24.4805 | 54.3823 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
432 | Island | مواقف مستشفي برجيل شارع الدفاع | 24.4785 | 54.3816 | Medium | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 2 | [9 empty] | 198720 | [6 empty] | Yes | Detailed | Upgrade to Catchment | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
459 | Island | الدفاع المدني - القبيسات | 24.425 | 54.4186 | High | No | N/A | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Detailed |  | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | [6 empty] | AECOM | Yes
460 | Island | مسجد السيد يوسف الهاشمي | 24.4245 | 54.4151 | Medium | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 99360 | [6 empty] | Yes | Quick Wins | Maintenance | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | TBC |  | TBC | Hand over phase | N/A |  |  |  |  | AECOM | Yes
482 | Mussafah | طريق E-11 باتجاه الغويفات | 24.2512 | 54.4773 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 1 | [9 empty] | 165600 | [6 empty] | Yes | T.B.C |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-01 |  | 2027-01-31 | [6 empty] | Parsons | Yes
486 | Zayed | شارع E30- جسر المصفح - الفلتر باتجاه خليفة | 24.3875 | 54.5247 | High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 3 |  |  | 149040 | 1 | [9 empty] | 165600 |  |  |  |  | 750000 |  | Yes | Quick Wins | Maintenance |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-07-18 | 2026-09-11 | 2027-01-12 | Hand over phase | N/A |  | 2026-07-18 |  |  | Parsons | Yes
490 | Al Shahama | شارع E12- من مجمع ياس باتجاه دبي | 24.4871 | 54.6344 | Very High | No | N/A | No | Absense of Drainage Network | Absense of Drainage Network | 2 |  |  | 99360 | 2 | [9 empty] | 198720 |  |  | 33000 |  |  |  | Yes | Detailed |  |  | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July |  | Absense of Drainage Network | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-10-26 |  | 2026-12-14 | Contractor | Yes |  |  |  |  | Parsons | Yes
493 | Al Wathbah | مدينة الرياض - شارع الخير | 24.2994 | 54.677 | High | Yes | Developer (Al Dar) | Yes | The network needs an upgrade | The network needs an upgrade | 2 |  |  | 99360 | 4 | [9 empty] | 993600 | [6 empty] | Yes | Detailed | New Inlet and Pipes | Permanent | NO | AED450M 2026 cashflow required, email to SW Taskforce 28 July | Current ADQCC WA726-1 Apr. 2022: 1-in-5 yr (44.88 mm/24hr): All areas 1-in-10 yr (51.12mm/24hr): Major Roads, Palaces, Soakaways 1-in-25 yr (69.60mm/24hr): Culverts, Lagoons, Airports 1-in-50 yr (81.84mm/24hr): Underpasses, underground carpark | Estimated between 30-39mm | 1-in-10 yr + 20% climate change factor | 51.12mm (+10.22mm) over 24 hrs | POST detailed design | POST IDAS approval of Detailed Design | 2026-08-16 |  | 2026-12-30 | 2D modelling |  |  | 2026-08-16 |  |  | Parsons | Yes
[11 empty] | 631 |  |  |  | 612 | [12 empty] | 623000 | 7105000 | 89867500 | 929000

## Assumptions (hidden)
ADM Summary - Hotspots by Criticality and Root Cause
Criticality | # of Hotspots | Root Cause | Duty Only Pumps Qty (12") | Duty Only Pumps Qty (8") | Duty Only Pumps Qty (6") | Additional Pumps Qty (12") | Additional Pumps Qty (8") | Additional Pumps Qty (6") | Additional Pumps Total Price (12") AED | Additional Pumps Total Price (8") AED | Additional Pumps Total Price (6") AED | Additional Tankers | Additional Tankers Price | Additional Detention Ponds (100*50*2 cubic meters) Qty | Additional Detention Ponds (100*50*2 cubic meters) Price (AED) | Additional Manpower Qty | Additional Manpower Total Price (AED)
Very High | 1 | With Network |  |  |  | 0 | 2 | 0 | 0 | 164160 | 0 | 120 tanker standby | 41040000 |  | 0 | 1 | 24624
| 1 | Without Network |  |  |  | 0 | 0 | 2 | 0 | 0 | 98496 |  |  | 1 | 750000 | 1 | 24624
High | 5 | With Network |  |  |  | 1 | 6 | 17 | 123120 | 492480 | 837216 |  |  |  | 3750000 | 17 | 418608
| 17 | Without Network |  |  |  | 0 | 0 | 13 | 0 | 0 | 640224 |  |  | 8 | 1500000 | 7 | 172368
Medium | 46 | With Network |  |  |  | 35 | 13 | 199 | 4309200 | 1067040 | 9800352 |  |  |  | 58500000 | 171 | 4210704
| 170 | Without Network |  |  |  | 2 | 0 | 75 | 246240 | 0 | 3693600 |  |  | 89 | 8250000 | 56 | 1378944
Low | 6 | With Network |  |  |  | 0 | 1 | 0 | 0 | 82080 | 0 |  |  |  | 750000 | 1 | 24624
| 5 | Without Network |  |  |  | 0 | 6 | 8 | 0 | 492480 | 393984 |  |  | 4 | 3000000 | 11 | 270864
Subtotal Very High | 2 |  |  |  |  | 0 | 2 | 2 | 0 | 164160 | 98496 |  |  | 1 | 750000 | 2 | 49248
Subtotal High | 22 |  |  |  |  | 1 | 6 | 30 | 123120 | 492480 | 1477440 |  |  | 8 | 5250000 | 24 | 590976
Subtotal Medium | 216 |  |  |  |  | 37 | 13 | 274 | 4555440 | 1067040 | 13493952 |  |  | 89 | 66750000 | 227 | 5589648
Subtotal Low | 11 |  |  |  |  | 0 | 7 | 8 | 0 | 574560 | 393984 |  |  | 4 | 3750000 | 12 | 295488
Outfalls & Siphons |  |  | 69 | 20 |  |  |  |  | 1788480 | 345600 | 0 |  |  | 0 |  | 50 | 259200
GRAND TOTAL | 251 |  |  |  |  | 38 | 28 | 314 | 6467040 | 2643840 | 15463872 |  | 41040000 | 102 | 76560000 | 315 | 6784560 | incl. Collection Chambers via Exec Summary!D47
ASSUMPTIONS
Pump Rental Rates (per hour):
12" Pump Duty Rate |  | 90 | AED/hr
8" Pump Duty Rate |  | 60 | AED/hr | [13 empty] | 148959312
6" Pump Duty Rate |  | 36 | AED/hr
12" Pump Standby Rate |  | 45 | AED/hr
8" Pump Standby Rate |  | 30 | AED/hr
6" Pump Standby Rate |  | 18 | AED/hr
Labour Rate (per hour):
Duty Rate |  | 18 | AED/hr
Standby Rate |  | 9 | AED/hr
Tanker Rate (per hour):
Duty Rate |  | 250 | AED/hr
Standby Rate |  | 125 | AED/hr
Duration Assumptions:
Active Rainfall Days |  | 10 | days
Contingency Factor |  | 20%
Active Days with Contingency (10+2) |  | 12 | days
Standby Days (3 months) |  | 90 | days
Standby Cost Factor |  | 50%
Hours per Day |  | 24 | hours
Outfalls & Siphons Assumptions:
Manpower for Outfalls (50% of outfalls) |  | 50 | headcount
12" Pumps for Outfalls |  | 69 | qty
8" Pumps for Outfalls |  | 20 | qty
6" Pumps for Outfalls |  | 0 | qty
Note: Outfall prices calculated using same hourly rates and durations as above