## Exec Summary
DMT Stormwater Resilience - Exec Summary
Region | Al Ain
Configurable deadline
| Deadline_Date >> | 2027-02-14
SLIDE 1 - Region Overview
Overview & Criticality
Metric | Count | % of total
Total stormwater hotspots | 184
Very high | 89 | 48.37%
High | 60 | 32.61%
Medium | 32 | 17.39%
Low | 3 | 1.63%
Highly critical (Very High + High) | 149 | 80.98%
Critical (Medium + Low) | 35 | 19.02%
Coverage (who owns the hotspot area)
Coverage | Count | % of total
Covered by Municipality (developer blank/No) | 0 | 0%
Covered by Private Entities / Developers | 184 | 100%
Root cause
Root cause | Count | % of total
Topography & Road Engineering | 11 | 5.978%
Inadequate Design Capacity | 139 | 75.54%
Absence of Drainage Network | 34 | 18.48%
Unmapped / CHECK | 0 | 0%
Other Metrics
Metric | Count
On existing stormwater network (Yes) | 139
Not on network (No) | 45
Duplicate Hotspot IDs (should be 0) | 0
ADM/IDD pond-scope overlaps flagged | 0
SLIDE 2 - Municipality Emergency Response Plan
AAM Daily Rate
Metric | Highly Critical | Critical | Total
Hotspots covered | 149 | 35 | 184
Manpower (headcount) | 0 | 0 | 0
Pumps (qty) | 35 | 12 | 47 | 56
Tankers (qty) | 138 | 32 | 170 | 190
Additional pumps (qty) | 9 |  | 9
Additional tankers (qty) | 20 |  | 20
Manpower budget (AED) | 0 | 0 | 0
Pumps budget (AED) | 175000 | 60000 | 235000
Tankers budget (AED) | 690000 | 160000 | 850000
Additional pumps (AED) | 45000 |  | 45000 | For palaces
Additional tankers (AED) | 100000 |  | 100000 | For palaces
Total emergency budget (AED) | 865000 | 220000 | 1230000
Total Emergency Response Budget (10)
Metric |  |  | Total
Manpower budget (AED)
Pumps budget (AED) |  |  | 2800000
Tankers budget (AED) |  |  | 9500000
Total Emergency Response Budget (AED) |  |  | 12300000
Emergency budget - private-development subset
Metric | Highly Critical | Critical | Total
Hotspots (private dev) | 149 | 35 | 184
Emergency budget - private dev (AED) | 865000 | 220000 | 1085000
SLIDE 3 - IDD Intervention (CAPEX) Plan
IDD-covered hotspots & CAPEX (IDD owner + at least one IDD field populated)
Metric | Highly Critical | Critical | Total
IDD-covered hotspots | 0 | 0 | 0
IDD CAPEX budget (AED) | 0 | 0 | 0
IDD CAPEX - private-development subset
Metric | Highly Critical | Critical | Total
IDD hotspots (private dev) | 0 | 0 | 0
IDD CAPEX - private dev (AED) | 0 | 0 | 0
SLIDE 4 - Budget for the Region (reference matrix)
Region | IDD Intervention (CAPEX) |  | Municipality Emergency Response Plan |  | Grand Total
| Highly Critical | Critical | Highly Critical | Critical
Abu Dhabi | 0 hotspots AED 0.0 m (0 in private dev, AED 0.0 m) | 0 hotspots AED 0.0 m (0 in private dev, AED 0.0 m) | 149 hotspots AED 0.9 m (149 in private dev, AED 0.9 m) | 35 hotspots AED 0.2 m (35 in private dev, AED 0.2 m) | 184 hotspots AED 1.1 m (184 in private dev, AED 1.1 m)
Total | 0 hotspots AED 0.0 m (0 in private dev, AED 0.0 m) |  | 184 hotspots AED 1.1 m (184 in private dev, AED 1.1 m) |  | 184 hotspots AED 1.1 m (184 in private dev, AED 1.1 m)
TIMELINE - Resolution vs Deadline_Date
Hotspot counts by timeline status
Timeline status | Count | % of total
Resolved before Feb 2027 | 0 | 0%
Resolved after Feb 2027 | 0 | 0%
No specific plan | 184 | 100%
CLIENT INPUT REQUIRED | 0 | 0%
Filter-ready detail list
Hotspot ID | Area | Location | Criticality | Private Dev? | IDD Intervention | Project Stage | IDD Completion Date | Timeline Status
1 | Al Aamerah & Al Sad & Al Salamat | Al Rifaa, Al Aamerah | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
2 | Al Aamerah & Al Sad & Al Salamat | 34 Ramlat Al Khadar St, Al Aamerah - Al Samar | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
3 | Al Aamerah & Al Sad & Al Salamat | Al Samar, Al Aamerah | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
4 | Al Aamerah & Al Sad & Al Salamat | Wadi Al Fayah St, Al Sad - Ramlat Al Saad | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
5 | Al Aamerah & Al Sad & Al Salamat | 28 An Nasr St, Al Salamat - Al Salamat 1 | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
6 | Al Arad | Sayh Al ʹArad St, Al 'Arad - Al Arad 1 | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
7 | Al Bateen | Ghafat Al Shwaihi, Al Bateen | Medium | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
8 | Al Bateen | Yaw Sablah St, Al Bateen - Ghafat Al Shwaihi | Medium | TRUE | Based on Future Design | Design phase | 2027-12-01 | No specific plan
9 | Al Bateen | Ghiyout Al Hidayri St, Al Bateen - Ghafat Al Shwaihi | Medium | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
10 | Al Dhahir & Mezyad & Um Ghafah | Zayed Bin Sultan St, Al Dhahir - Dhaher 1 | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
11 | Al Dhahir & Mezyad & Um Ghafah | Al Barari Mall R/A, Dhaher 3, Al Dhahir | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
12 | Al Dhahir & Mezyad & Um Ghafah | Al Ain City Municipality – Customer Service Center, Mezyad | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
13 | Al Dhahir & Mezyad & Um Ghafah | Zayed Bin Sultan St, Mazyad - Mazyad 2 | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
14 | Al Dhahir & Mezyad & Um Ghafah | Al Muraikhat, Um Ghafah | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
15 | Al Faqaa | Al Ain - Dubai Rd, Al Faqaa | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
16 | Al Faqaa | Dulaymah 1, Al Fagaa | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
17 | Al Rawdah Al Sharqiyah - Al Ifaz & Al Ghireebah | 19-7 Al Sofouh St, Al Rawdah Al Sharqiyah - Al Ifaz | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
18 | Al Rawdah Al Sharqiyah - Al Ifaz & Al Ghireebah | Al Ifaz, Al Rawdah Al Sharqiyah | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
19 | Al Fou'ah | Al Ain - Dubai Rd, Al Nabbagh – Sibeitah Tahnoun Bin Mohammed Al Nhayan Rd. | Medium | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-01 | No specific plan
20 | Al Fou'ah | Al Fou'ah - Al Sajaa | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
21 | Al Fou'ah | Abu 'Ubaidah Bin Al Jarrah St. Al Sajaa, Al Fou'ah | High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
22 | Al Fou'ah | Al Fouʹah St, Al Fou'ah - Al Raqiyah | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
23 | Al Hiyar | Wadi Maad, Al Hiyar | High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
24 | Al Hiyar | Ramlat Al Hayer, Al Hiyar | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
25 | Al Hiyar | E20, Al Hiyar - Al Hayer 6 | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
26 | Al Hiyar | Um Al Dakhan, Al Hiyar | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
27 | Al Hiyar | Al Shansoobah, Al Hiyar | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
28 | Al Hiyar | Al Shansoobah, Al Hiyar | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
29 | Al Hiyar | 36 Wadi At Tabnah St, Al Hiyar - Ramlat Al Hayer | High | TRUE | New Network | Design phase | CLIENT INPUT REQUIRED | No specific plan
30 | Al Hiyar | Shaʹbiyat Al Hiyar St, Al Hiyar - Al Jabib - East | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
31 | Al Hiyar | Sweihan Rd, Al Hiyar - Al Ghashbah | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
32 | Al Jimi | 35 Al Jamal St, Al Jimi - Al Mraijeb | Very High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
33 | Al Jimi | 4-8 Al Tajer St. Al Jimi - Slemi | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
34 | Al Jimi | 5-1 Al Snono, Al Jimi - Slemi | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
35 | Al Jimi | 47-7 Al Bahaa St, Al Jimi - Al Mraijeb | Very High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
36 | Al Jimi | Hazza Bin Sultan Staduim Tunnel, Zayed The First St | Very High | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-01 | No specific plan
37 | Al Jimi | Mohammed Bin Khalifa St, Al Jimi | Very High | TRUE | Upgrade Network | Design phase | 2028-06-01 | No specific plan
38 | Al Jimi | Al Muwaijʹi St, Al Jimi - Civic Center | Very High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
39 | Al Jimi | Civic Center, Al Jimi | Very High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
40 | Al Jimi | Ugdat Al Ameriya, Al Jimi | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
41 | Al Khibeesi | 28-56 AI Lammah St, Al Khibeesi - Al Naseriyya | High | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
42 | Al Khibeesi | Al Zaafaran, Al Khibeesi | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
43 | Al Khibeesi (Emergency plan with Al Dar) | Al Meryal, Al Khibeesi Area | High | TRUE | New Network | Implementation phase | CLIENT INPUT REQUIRED | No specific plan
44 | Al Maqam & Asharej (to be rais to injazz) | Shabiyat Al Maqam, Al Maqam | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
45 | Al Maqam & Asharej | Al Maqam - Shabiyat Al Maqam | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
46 | Al Maqam & Asharej | Al Urjuwan St, Al Maqam - Shabiyat Al Maqam | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
47 | Al Maqam & Asharej (to be check or to removed) | Al Yasat St. Shabiyat Al Maqam, Al Maqam | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
48 | Al Maqam & Asharej | 151-149 Al Jawharah St, 'Asharij - Al Dafeinah | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
49 | Al Maqam & Asharej | Tawam Tunnel, Shabhanat Asharej, Al Muwaij'i | Very High | TRUE | Upgrade Network | Hand Over Phase | CLIENT INPUT REQUIRED | No specific plan
50 | Al Maqam & Asharej (to be added the tankers) | Asharej Tunnel, Khalifa Bin Zayed St, | Very High | TRUE | Upgrade Network | Hand Over Phase | 2020-12-01 | No specific plan
51 | Al Maqam & Asharej (confirmed to be add 1 no of Pump) | Bida Bin Ammar, Al Muwaij'i Area | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
52 | Al Maqam & Asharej | Maitha Bint Mohammed St 'Asharij - Shiebat Al Oud - Abu | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
53 | Al Mu'tarid | 75-45 AI Siray St, Al Mu'tarid - Hai Al Wadi | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
54 | Al Mu'tarid | Al Baladiyah St, Al Mu'tarid - Al Gellah | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
55 | Al Mu'tarid | Al Jabal R/A Khalifa Bin Zayed St, Al Mu'tarid | Very High | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-01 | No specific plan
56 | Al Mu'tarid | Mohammed Bin Khalifa St, Al Mu'tarid - Ramlat Aawad Shaheen | Very High | TRUE | Upgrade Network | Design phase | 2028-06-01 | No specific plan
57 | Al Mu'tarid (to be removed) | Shakhboot Bin Sultan St, Al Mu'tarid | Very High | TRUE | Upgrade Network | Design phase | 2028-06-01 | No specific plan
58 | Al Mu'tarid (to be added the tanker) | Al Radi St, Al Mu'tarid - Hai Al Jabal | Very High | TRUE | Upgrade Network | Hand Over Phase | CLIENT INPUT REQUIRED | No specific plan
59 | Al Mu'tarid | Teebi St, Al Mu'tarid Area | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
60 | Al Mu'tarid | Al Husoun St, Al Mu'tarid - Ugdat Al Muwaiji | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
61 | Al Mu'tarid | Khalifa Bin Zayed The First St, Al Mu'tarid - Al Jizza | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
62 | Al Jahili | Al Marayegh, Al Jahili Area | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
63 | Al Muwaiji | Saeed Bin Shakhbout The First St, Al Muwaij'i - Majlood | High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
64 | Al Muwaiji | Saeed Bin Shakhbout The First St, Al Muwaij'i - Al Ruwaikah | High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
65 | Al Muwaiji | Maitha Bint Mohammed St, Al Muwaij'i - Deer Park | High | TRUE | Upgrade Network | Hand Over Phase | CLIENT INPUT REQUIRED | No specific plan
66 | Al Nabbagh | Sibeitah, Al Nabbagh 66! | Medium | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-01 | No specific plan
67 | Al Nabbagh | Lane 821, Al Nabbagh - Sibeitah | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
68 | Al Qattarah | 96-124 Al Dameed St, Al Qattarah - Al Mragha | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
69 | Al Qattarah | 96-124 Al Dameed St, Al Qattarah - Al Mragha | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
70 | Al Qattarah | 96-124 Al Dameed St, Al Qattarah - Al Mragha | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
71 | Al Qattarah | Bani Yas St, Al Qattarah - Al Mergab | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
72 | Al Qattarah | alfurusia roundabout (Equestrianism)- Al Qattarah - Al Mergab | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
73 | Al Qattarah | Bani Yas St, Al Qattarah - Al Mergab | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
74 | Al Sarouj & Al Noud | Al Qanadeel St, Al Sarouj - Al Harmoozi | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
75 | Al Sarouj & Al Noud | Al Harmoozi, Al Sarouj | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
76 | Al Sarouj & Al Noud | Hai Al Wadi, Al Sarouj | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
77 | Al Sarouj & Al Noud | Al Mashall, Al Sarouj | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
78 | Al Sarouj & Al Noud | Al Harmoozi, Al Sarouj | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
79 | Al Sarouj & Al Noud | 29-23 Al Qutami St, Al Sarouj - Hai Al Wadi | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
80 | Al Sarouj & Al Noud | Al Mashall, Al Sarouj | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
81 | Al Sarouj & Al Noud | Zayed Bin Sultan St Hai Al Wadi, Al Sarouj | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
82 | Al Sarouj & Al Noud | Al Harmoozi, Al Sarouj | Very High | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-31 | No specific plan
83 | Al Sarouj & Al Noud | Truck R/A Wadi Al Ain 3, Al Noud | Very High | TRUE | New Network | Design phase | CLIENT INPUT REQUIRED | No specific plan
84 | Al Sarouj & Al Noud | ADNOC Station, Wadi Al Ain 2, Al Noud | Very High | TRUE | New Network | Implementation phase | CLIENT INPUT REQUIRED | No specific plan
85 | Al Shiwayb | AL SHWAIB FAMILY PARK | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
86 | Al Shiwayb | Ramlat Al Shuwaib, Al Shiwayb | High | TRUE | Pond/Side slope protection | Implementation phase | 2026-07-01 | No specific plan
87 | Al Shiwayb | Al Shiwayb Rd, Al Shiwayb | High | TRUE | Pond/Side slope protection | Implementation phase | 2026-07-01 | No specific plan
88 | Al Shiwayb | Shibak 2, Al Shiwayb Rd. | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
89 | Al Tiwayya | 6-8 Al Mu'attar St, Al Markhaniyyah - Muaifaa | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
90 | Al Tiwayya | Jafeer Obaid, Al Tiwayya | Medium | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
91 | Al Tiwayya | Ras Ash Sheikh St, Al Tiwayya - Eidan Al Ridda | Medium | TRUE | Upgrade Network | Implementation phase | 2026-12-01 | No specific plan
92 | Al Tiwayya | Eidan Al Jareh, Al Tiwayya Area | Medium | TRUE | Upgrade Network | Hand Over Phase | CLIENT INPUT REQUIRED | No specific plan
93 | Al Wiqan | Um Az Zumoul Rd, Al Wiqan - Saq Al Awir | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
94 | Al Wiqan | 26th St, Al Wiqan - Al Sayh | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
95 | Al Wiqan | Al Muhallab St, Al Wiqan - Ramlat Addimah | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
96 | Al Quo'a | 40th St, Al Qou' - Al Quo'a Town | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
97 | Central District | 25 Al Mandhour St, Central District - Hai Al Murabbaa | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
98 | Central District | AI Mut-haf St, Central District - Hai Al Hisn | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
99 | Central District | Al Ain Oasis, Central District | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
100 | Central District | 33-9 Al Hdaybah St, Central District - Al Talaa | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
101 | Central District | Al Wisal St, Central District - Al Nyadat | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
102 | Central District | 73-67 Al Masarrah St, Central District - Al Kuwaitat | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
103 | Central District | Al Ain Civil Defense | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
104 | Central District | 25 Al Sufouq St, Central District | Very High | TRUE | Upgrade Network | Design phase | 2028-06-01 | No specific plan
105 | Central District | 25 Al Sufouq St, Central District | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
106 | Central District | Hai Al Qasr, Central District | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
107 | Central District | 12-16 Seasons St, Central District - Nad Al Rusas | Very High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
108 | Central District | Malayim St, Central District - Nad Al Gorban | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
109 | Central District | Al Sufouq St, Central District - Shiebat Bin Anbar | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
110 | Central District | 97-87 Al Anhar St Central District - Nad Al Gorban - Abu | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
111 | Falaj Hazza | Falaj Hazza' - Jefeer Jedeed | Low | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
112 | Falaj Hazza | Falaj Hazza' - Jefeer Jedeed | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
113 | Falaj Hazza | 14 شارع السَاسْ, Falaj Hazza' - Jefeer Jedeed | Low | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
114 | Falaj Hazza | Zkhir Tunnel, Nahyan The First St, Falaj Hazza' - Ramlat Zakher | Low | TRUE | Upgrade Network | Hand Over Phase | CLIENT INPUT REQUIRED | No specific plan
115 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Ain Al Fayda, Ain Al Faydah | Medium | TRUE | Upgrade Network | Implementation phase | 2026-09-01 | No specific plan
116 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Al Bawarij St, Ain Al Faydah - Ain Al Fayda | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
117 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Ain Al Fayda, E40 E30 R/A | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
118 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Dihn Al ʹOud St, Mbazzarah Al Khadra - Green Mubazzarah 2 | Medium | TRUE | Upgrade Network | Implementation phase | 2026-09-01 | No specific plan
119 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | 6-16 Tawi Tay St, Al Dhahrah - Al Malaleeh | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
120 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Um Az Zumoul Rd, Al Dhahrah - Al Malaleeh | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
121 | Hili | 4 An Nayfah St, Hili - Al Reef | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
122 | Hili | 91-87 Muslim Bin Yasar St, Hili - Shareat Hili | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
123 | Hili | 6 Al Astorlab St - Hili - Eidan Al Mahaba | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
124 | Hili | 7-3 Irq As Simayh St Hili - Al Reef | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
125 | Hili | Al Misbah, Hili | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
126 | Hili (completed only monitoring) | Al Misbah, Al Athar St. Hili Area | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
127 | Hili | Hili Archaeological park Roundabout, 55 - Hili - Athar Hili | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
128 | Hili | 62-66 Al Hawwami St, Hili - Al Reef | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
129 | Hili | Khalfan Bin Matar Al Rumaithi St, Hili - Al Misbah | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
130 | Hili | Falaj Hili St, Hili - Ugdat Al Husoon | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
131 | Hili | Mohammed Bin Khalifa St, Hili | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
132 | Hili | Imran Bin Talhah St, Hili - Al Nayfa 1 | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
133 | Hili | Ramlat Al Ghabbah St, Hili - Al Nayfa 1 | Very High | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
134 | Hili | Abu ʹUbaidah Bin Al Jarrah St, Al Fou'ah | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
135 | Hili | Al Reef, Hili Area | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
136 | Industrial Area | Al Naglah, Industrial Area | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
137 | Industrial Area | Al Naglah, Industrial Area | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
138 | Industrial Area | Shiebat Al Salam, Industrial Area | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
139 | Industrial Area | As Siham 2 St, Industrial Area - Leetag | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
140 | Industrial Area | Sanaiyah Tunnel, Khalid Bin Sultan St, Al Mutaw'ah - Hai Al Musalla | Very High | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-01 | No specific plan
141 | Industrial Area | Al Aras, Industrial Area | Very High | TRUE | Upgrade Network | Design phase | 2027-12-01 | No specific plan
142 | Industrial Area | Cement Factory R/A Green Mubazzarah 1 | Very High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
143 | Masakin | 1024 Rd, Masakin - Ghshabah | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
144 | Masakin | Al Adhamiyah, Masakin | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
145 | Masakin | Al Adhamiyah, Masakin | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
146 | Nahil | Al Shaqq, Nahil | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
147 | Nahil | Masakkin | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
148 | Nahil | E95, Nahil - Nahil 5 | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
149 | Saih Al Gharbal | E30, Saih Al Gharbal | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
150 | Saih Al Gharbal | Saih Al Gharbal, Al Rawdah E30 | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
151 | Saih Al Gharbal | E30, Al Salamat - Sayh Al Daay, Ar Rawdah Rd | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
152 | Saih Al Gharbal | E30, Al Salamat - Sayh Al Daay - Ar Rawdh Rd | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
153 | Al Masoudi | 6-12 Al Mataf St, Al Mas'oudi - Al Gaseemah | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
154 | Al Masoudi | Al Mubtahil St, Al Mas'oudi - Al Gaseemah | Medium | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
155 | Al Masoudi | Tahnoun Bin Mohammed Al Nahyan Rd. Tunnel, Batha Bin Hilal, Al Tiwayya | Medium | TRUE | Upgrade Underpass drainage system | Design phase | 2028-01-01 | No specific plan
156 | Al Masoudi | Tahnoun Bin Mohammed Al Nahyan Rd. Tunnel, Batha Bin Hilal, Al Tiwayya | Medium | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
157 | Al Masoudi | Al Abtal St, Al Mas'oudi - Manazef | Medium | TRUE | Upgrade Network | Hand Over Phase | 2026-03-01 | No specific plan
158 | Bad Bint Saud | Al Sharf, Bad' Bint Sa'oud | Medium | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
159 | Bad Bint Saud | E95, Bad' Bint Sa'oud - Qarn Bint Saud | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
160 | Bad Bint Saud | Qarn Bint Saud, Bad' Bint Sa'oud | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
161 | Bad Bint Saud | Qarn Bint Saud, Bad' Bint Sa'oud | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
162 | Bad Bint Saud | E95, Bad' Bint Sa'oud - Qarn Bint Saud. Nahil Rd. | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
163 | Sweihan | Ramlat Sweihan 3, Ramlat Sweihan | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
164 | Sweihan | Sayh Madhran, Al 'Ajban | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
165 | Sweihan | Al Taf Rd. Sweihan - Abu Dhabi Rd, Niqa Al Dheeb - Raigha | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
166 | Sweihan | Al Taf Rd. Sweihan - Abu Dhabi Rd, Sweihan - Bida Al Samah | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
167 | Sweihan | E20, Ramlat Sweihan - Ramlat Sweihan 3 | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
168 | Sweihan | Al Taf Rd. Raigha, Niqa Al Dheeb | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
169 | Sweihan | Al Taf Rd. Sayh Al Tuwaissah, Al Sad | High | TRUE | Pond/Side slope protection | Design phase | 2027-12-01 | No specific plan
170 | Sweihan | Al Taf Rd. Sweihan - Bida Al Samah | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
171 | Sweihan | E20, Niqa Al Dheeb - Niqa Al Dheeb 2 - Sweihan Rd. | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
172 | Sweihan | Ramlat Sweihan 3, Ramlat Sweihan | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
173 | Sweihan | E20, Sweihan - Ghaffat Rakadh | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
174 | Sweihan | Bida Al Mghanni, Nahil Sweihan Rd. | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
175 | Sweihan | 44th St, Sweihan - Shabiat Suweihan | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
176 | Sweihan | Shabiat Suweihan, Sweihan Area | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
177 | Zakhir & Neima & Shi'bat Al Wutah | Al Shamali St, Zakhir - Zakhir South | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
178 | Zakhir & Neima & Shi'bat Al Wutah | Gafat Al Nayyar, Zakhir | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
179 | Zakhir & Neima & Shi'bat Al Wutah | Zakher Wedding Hall | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
180 | Zakhir & Neima & Shi'bat Al Wutah | Ramlat Zakher, Zakhir | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
181 | Zakhir & Neima & Shi'bat Al Wutah | Neima 1, Ni'mah | High | TRUE | Upgrade Network | Design phase | 2028-12-01 | No specific plan
182 | Zakhir & Neima & Shi'bat Al Wutah | Neima 1, Ni'mah | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
183 | Zakhir & Neima & Shi'bat Al Wutah | Neima 1, Ni'mah | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan
184 | Zakhir & Neima & Shi'bat Al Wutah | 6 Al Hawayir St Shi'bat Al Wutah - Shiebat Al Watah 1 | High | TRUE | Based on future design | future project | CLIENT INPUT REQUIRED | No specific plan

## Analysis
[11 empty] | Municipality Emergency Response Plan A For storm events up to a 1-in-10-year event: Very high Criticality hotspot: <2h ¦ High criticality hotspot: <4h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [20 empty] | Municipality Emergency Response Plan B For storm events exceeding a 1-in-10-year event: Very high Criticality hotspot: <4h ¦ High criticality hotspot: <6h ¦ Medium criticality hotspot: <10h ¦ Low criticality hotspot: >10h | [5 empty] | IDD Intervention Plan
[38 empty] | Select Yes or No | Select one: Critical Infrastructure, Detailed Design, Fast-Track, or Quick Win | Provide the primary solution such as inlet, pipe, Upgrade to Catchment , Pond / Spillway, etc | Select one: Permanent, Interim, or Temporary | Please specify if additional budget is required for this hotspot (Yes/No) | Provide the requested budget for each applicable hotspot. If a single project spans multiple hotspots, list the budget only once under the primary hotspot. For all other covered hotspot entries, replace the budget with: "Included in Hotspot #X budget." | Provide the current rainfall design event, including the return period | Provide the existing network’s technical or hydraulic capacit | Provide the future or target rainfall design event, including the return period | Provide the future or target network capacity after the planned intervention | Provide the estimated floodwater volume managed by network after intervention | Provide the expected number of hours required for floodwater to recede after intervention | Revise the planned mobilization date | Revise the planned completion date | Select one: Contractor Design phase, Parsons Verification Phase, IDAS Review Phase, Municipality Permitting Phase, Implementation phase, Hand Over Phase | Select Yes or No. Enter Yes only after formal approval has been issued. | Provide the actual mobilization date (only after actual mobilization) | Provide the actual completion date (only after actual completion) | Select one: Not Started, On Track, Delayed, or Completed | Provide the full name of the accountable IDD owner.
Hotspot_ID | Hotspot_Area | Hotspot_Location | Latitude | Longitude | Criticality | Developer_Private_Area | Developer Name | Network_Available | Root_Cause | Root_Cause_Details | Manpower_Qty | Manpower Active-duty AED | Manpower Standby AED | Total Manpower_Budget_AED | Pumps_Qty | Diesel Pump 12 inch Qty | Diesel Pump 8 inch Qty | Diesel Pump 6 inch Qty | Diesel Pump 12 inch AED/Day | Diesel Pump 8 inch AED/Day | Diesel Pump 6 inch AED/Day | Total Pump Daily Rate | Total Pump Active Duty AED2 | Total Pump Standby AED | Pumps_Budget_AED | Tankers_Qty | Tankers_Budget_AED | Concrete_Barrier_AED | Sand_Barrier_AED | Detention_Ponds_AED | Collection_Chamber_AED | Manpower_Qty2 | Manpower_Budget_AED3 | Pumps_Qty4 | Pumps_Budget_AED5 | Tankers_Qty6 | Tankers_Budget_AED7 | IDD Interventoin Planned | IDD_Design_Category | Design Solution | Type of Intervention | Additional Budget Requirment | Additional Budget Requested | Hotspot Network Rain Design Event (Current) | Hotspot Network Design Technical Capacity (Current) | Hotspot Network Rain Design Event (Future) | Hotspot Network Design Technical Capacity (Future) | Flood Volume Capacity after Intervention | Associated recovery time after intervention | Planned_IDD_Mobilization_Date | Planned_IDD_Completion_Date | Project Stage | Approval from IDAS secured (Yes/No) | Actual_Mobilization_Date | Actual_Completion_Date | Intervention status | IDD_Owner_Name | Is_Private_Developer | Root_Cause_Category | IDD_Covered | IDD_Completion_Date2 | IDD_Timeline_Status
1 | Al Aamerah & Al Sad & Al Salamat | Al Rifaa, Al Aamerah | 24.2457 | 55.5743 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location |  |  |  |  | 6 | [9 empty] | 30000 | 30 | 150000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
2 | Al Aamerah & Al Sad & Al Salamat | 34 Ramlat Al Khadar St, Al Aamerah - Al Samar | 24.2383 | 55.552 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 34 Ramlat Al Khadar St, Al Aamerah - Al Samar require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
3 | Al Aamerah & Al Sad & Al Salamat | Al Samar, Al Aamerah | 24.2347 | 55.5505 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Samar, Al Aamerah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
4 | Al Aamerah & Al Sad & Al Salamat | Wadi Al Fayah St, Al Sad - Ramlat Al Saad | 24.2197 | 55.5014 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Wadi Al Fayah St, Al Sad - Ramlat Al Saad require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
5 | Al Aamerah & Al Sad & Al Salamat | 28 An Nasr St, Al Salamat - Al Salamat 1 | 24.2134 | 55.5906 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 28 An Nasr St, Al Salamat - Al Salamat 1 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
6 | Al Arad | Sayh Al ʹArad St, Al 'Arad - Al Arad 1 | 23.847 | 55.5294 | Medium | Applicable with (AACM) |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed intervention at Sayh Al ʹArad St, Al 'Arad - Al Arad 1; response is based on tanker dewatering until a drainage network/permanent solution is available. |  |  |  |  | 0 | [9 empty] | 0 | 1 | 5000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
7 | Al Bateen | Ghafat Al Shwaihi, Al Bateen | 24.2105 | 55.6359 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ghafat Al Shwaihi, Al Bateen require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 1 | [9 empty] | 5000 | 1 | 5000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2026-02-11 | 2026-08-30 | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
8 | Al Bateen | Yaw Sablah St, Al Bateen - Ghafat Al Shwaihi | 24.2098 | 55.627 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Yaw Sablah St, Al Bateen - Ghafat Al Shwaihi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Based on Future Design | Based on Future Design | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
9 | Al Bateen | Ghiyout Al Hidayri St, Al Bateen - Ghafat Al Shwaihi | 24.1993 | 55.6282 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ghiyout Al Hidayri St, Al Bateen - Ghafat Al Shwaihi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2026-05-14 | - | On Track | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
10 | Al Dhahir & Mezyad & Um Ghafah | Zayed Bin Sultan St, Al Dhahir - Dhaher 1 | 24.0644 | 55.8374 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest Wadi |  |  |  |  | 3 | [9 empty] | 15000 | 4 | 20000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
11 | Al Dhahir & Mezyad & Um Ghafah | Al Barari Mall R/A, Dhaher 3, Al Dhahir | 24.0857 | 55.832 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Barari Mall R/A, Dhaher 3, Al Dhahir require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
12 | Al Dhahir & Mezyad & Um Ghafah | Al Ain City Municipality – Customer Service Center, Mezyad | 24.0328 | 55.8445 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest Wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
13 | Al Dhahir & Mezyad & Um Ghafah | Zayed Bin Sultan St, Mazyad - Mazyad 2 | 24.0368 | 55.8441 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Zayed Bin Sultan St, Mazyad - Mazyad 2 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
14 | Al Dhahir & Mezyad & Um Ghafah | Al Muraikhat, Um Ghafah | 24.0911 | 55.9081 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Muraikhat, Um Ghafah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
15 | Al Faqaa | Al Ain - Dubai Rd, Al Faqaa | 24.6866 | 55.6418 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest Wadi |  |  |  |  | 0 | [9 empty] | 0 | 1 | 5000 | [10 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46722 | No specific plan
16 | Al Faqaa | Dulaymah 1, Al Fagaa | 24.6936 | 55.6126 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
17 | Al Rawdah Al Sharqiyah - Al Ifaz & Al Ghireebah | 19-7 Al Sofouh St, Al Rawdah Al Sharqiyah - Al Ifaz | 24.1551 | 55.658 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 19-7 Al Sofouh St, Al Rawdah Al Sharqiyah - Al Ifaz require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 1 | 5000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
18 | Al Rawdah Al Sharqiyah - Al Ifaz & Al Ghireebah | Al Ifaz, Al Rawdah Al Sharqiyah | 24.163 | 55.655 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed intervention at Al Ifaz, Al Rawdah Al Sharqiyah; response is based on tanker dewatering until a drainage network/permanent solution is available. Discharge point is nearest Wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
19 | Al Fou'ah | Al Ain - Dubai Rd, Al Nabbagh – Sibeitah Tahnoun Bin Mohammed Al Nhayan Rd. | 24.3469 | 55.7778 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Ain - Dubai Rd, Al Nabbagh – Sibeitah Tahnoun Bin Mohammed Al Nhayan Rd. require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 2 | 10000 | [10 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46753 | No specific plan
20 | Al Fou'ah | Al Fou'ah - Al Sajaa | 24.3599 | 55.7875 | Medium | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest Wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
21 | Al Fou'ah | Abu 'Ubaidah Bin Al Jarrah St. Al Sajaa, Al Fou'ah | 24.3426 | 55.795 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Abu 'Ubaidah Bin Al Jarrah St. Al Sajaa, Al Fou'ah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2025-06-16 | - | On Track | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
22 | Al Fou'ah | Al Fouʹah St, Al Fou'ah - Al Raqiyah | 24.3342 | 55.7923 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Fouʹah St, Al Fou'ah - Al Raqiyah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
23 | Al Hiyar | Wadi Maad, Al Hiyar | 24.6107 | 55.7563 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Wadi Maad, Al Hiyar require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi |  |  |  |  | 2 | [9 empty] | 10000 | 8 | 40000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2026-04-15 | - | On Track | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
24 | Al Hiyar | Ramlat Al Hayer, Al Hiyar | 24.6035 | 55.76 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
25 | Al Hiyar | E20, Al Hiyar - Al Hayer 6 | 24.583 | 55.7373 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
26 | Al Hiyar | Um Al Dakhan, Al Hiyar | 24.5246 | 55.553 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46722 | No specific plan
27 | Al Hiyar | Al Shansoobah, Al Hiyar | 24.5488 | 55.7554 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46722 | No specific plan
28 | Al Hiyar | Al Shansoobah, Al Hiyar | 24.5725 | 55.7477 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Shansoobah, Al Hiyar require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
29 | Al Hiyar | 36 Wadi At Tabnah St, Al Hiyar - Ramlat Al Hayer | 24.5889 | 55.7442 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | Yes | New Network | New Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | Ongoing | Ongoing | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
30 | Al Hiyar | Shaʹbiyat Al Hiyar St, Al Hiyar - Al Jabib - East | 24.6412 | 55.7105 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46722 | No specific plan
31 | Al Hiyar | Sweihan Rd, Al Hiyar - Al Ghashbah | 24.5489 | 55.6722 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | the accumulated water will be removed by a tanker and discharged at the nearest pond or another disposal location | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
32 | Al Jimi | 35 Al Jamal St, Al Jimi - Al Mraijeb | 24.2601 | 55.7251 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 35 Al Jamal St, Al Jimi - Al Mraijeb require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 7 | 35000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2025-09-01 | - | On Track | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
33 | Al Jimi | 4-8 Al Tajer St. Al Jimi - Slemi | 24.2418 | 55.7465 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 4-8 Al Tajer St. Al Jimi - Slemi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
34 | Al Jimi | 5-1 Al Snono, Al Jimi - Slemi | 24.2473 | 55.7477 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 5-1 Al Snono, Al Jimi - Slemi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
35 | Al Jimi | 47-7 Al Bahaa St, Al Jimi - Al Mraijeb | 24.2628 | 55.7282 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 47-7 Al Bahaa St, Al Jimi - Al Mraijeb require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2026-04-05 | - | On Track | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
36 | Al Jimi | Hazza Bin Sultan Staduim Tunnel, Zayed The First St | 24.2424 | 55.7194 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Hazza Bin Sultan Staduim Tunnel, Zayed The First St require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46753 | No specific plan
37 | Al Jimi | Mohammed Bin Khalifa St, Al Jimi | 24.2499 | 55.7532 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Mohammed Bin Khalifa St, Al Jimi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-06-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46905 | No specific plan
38 | Al Jimi | Al Muwaijʹi St, Al Jimi - Civic Center | 24.2401 | 55.7305 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | Existing Gullies only not connected to the network at Al Muwaijʹi St, Al Jimi - Civic Center require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2026-09-01 | - | On Tack | AAI | TRUE | Absence of Drainage Network | FALSE | 46357 | No specific plan
39 | Al Jimi | Civic Center, Al Jimi | 24.2373 | 55.7377 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Civic Center, Al Jimi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
40 | Al Jimi | Ugdat Al Ameriya, Al Jimi | 24.2456 | 55.7226 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ugdat Al Ameriya, Al Jimi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
41 | Al Khibeesi | 28-56 AI Lammah St, Al Khibeesi - Al Naseriyya | 24.2291 | 55.682 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 28-56 AI Lammah St, Al Khibeesi - Al Naseriyya require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi |  |  |  |  | 0 | [9 empty] | 0 | 4 | 20000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2026-01-01 | - | On Tack | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
42 | Al Khibeesi | Al Zaafaran, Al Khibeesi | 24.239 | 55.7081 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Zaafaran, Al Khibeesi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
43 | Al Khibeesi (Emergency plan with Al Dar) | Al Meryal, Al Khibeesi Area | 24.2352 | 55.6983 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Meryal, Al Khibeesi Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | New Network | New Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | under construction | under construction | Implementation phase | Yes | - | - | On Track | AlDar | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
44 | Al Maqam & Asharej (to be rais to injazz) | Shabiyat Al Maqam, Al Maqam | 24.1814 | 55.599 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing Gullies not connected to the network or nearby drainage arrangements at Shabiyat Al Maqam, Al Maqam require pumping support during storm events, Discharge point is nearest Wadi |  |  |  |  | 6 | [9 empty] | 30000 | 4 | 20000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
45 | Al Maqam & Asharej | Al Maqam - Shabiyat Al Maqam | 24.1799 | 55.6051 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Maqam - Shabiyat Al Maqam require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
46 | Al Maqam & Asharej | Al Urjuwan St, Al Maqam - Shabiyat Al Maqam | 24.1811 | 55.6139 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Urjuwan St, Al Maqam - Shabiyat Al Maqam require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
47 | Al Maqam & Asharej (to be check or to removed) | Al Yasat St. Shabiyat Al Maqam, Al Maqam | 24.1891 | 55.6318 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Yasat St. Shabiyat Al Maqam, Al Maqam require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
48 | Al Maqam & Asharej | 151-149 Al Jawharah St, 'Asharij - Al Dafeinah | 24.2143 | 55.6764 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 151-149 Al Jawharah St, 'Asharij - Al Dafeinah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. Discharge point is nearest Wadi | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
49 | Al Maqam & Asharej | Tawam Tunnel, Shabhanat Asharej, Al Muwaij'i | 24.1948 | 55.655 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Tawam Tunnel, Shabhanat Asharej, Al Muwaij'i require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | completed | completed | Hand Over Phase | Yes | Completed | Completed | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
50 | Al Maqam & Asharej (to be added the tankers) | Asharej Tunnel, Khalifa Bin Zayed St, | 24.2077 | 55.6869 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Asharej Tunnel, Khalifa Bin Zayed St, require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2019-10-01 | 2020-12-01 | Hand Over Phase | Yes | Completed | Completed | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 44166 | No specific plan
51 | Al Maqam & Asharej (confirmed to be add 1 no of Pump) | Bida Bin Ammar, Al Muwaij'i Area | 24.2043 | 55.651456° | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Bida Bin Ammar, Al Muwaij'i Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
52 | Al Maqam & Asharej | Maitha Bint Mohammed St 'Asharij - Shiebat Al Oud - Abu | 24.192 | 55.6766 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Maitha Bint Mohammed St 'Asharij - Shiebat Al Oud - Abu require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
53 | Al Mu'tarid | 75-45 AI Siray St, Al Mu'tarid - Hai Al Wadi | 24.2347 | 55.7372 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 75-45 AI Siray St, Al Mu'tarid - Hai Al Wadi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 10 | 50000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
54 | Al Mu'tarid | Al Baladiyah St, Al Mu'tarid - Al Gellah | 24.2131 | 55.7375 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Baladiyah St, Al Mu'tarid - Al Gellah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
55 | Al Mu'tarid | Al Jabal R/A Khalifa Bin Zayed St, Al Mu'tarid | 24.2247 | 55.738 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Jabal R/A Khalifa Bin Zayed St, Al Mu'tarid require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46753 | No specific plan
56 | Al Mu'tarid | Mohammed Bin Khalifa St, Al Mu'tarid - Ramlat Aawad Shaheen | 24.2338 | 55.7515 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Mohammed Bin Khalifa St, Al Mu'tarid - Ramlat Aawad Shaheen require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-06-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46905 | No specific plan
57 | Al Mu'tarid (to be removed) | Shakhboot Bin Sultan St, Al Mu'tarid | 24.2314 | 55.744 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Shakhboot Bin Sultan St, Al Mu'tarid require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-06-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46905 | No specific plan
58 | Al Mu'tarid (to be added the tanker) | Al Radi St, Al Mu'tarid - Hai Al Jabal | 24.224 | 55.7341 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Radi St, Al Mu'tarid - Hai Al Jabal require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | completed | completed | Hand Over Phase | Yes | Completed | Completed | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
59 | Al Mu'tarid | Teebi St, Al Mu'tarid Area | 24.2186 | 55.7341 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Teebi St, Al Mu'tarid Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
60 | Al Mu'tarid | Al Husoun St, Al Mu'tarid - Ugdat Al Muwaiji | 24.226 | 55.7365 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Husoun St, Al Mu'tarid - Ugdat Al Muwaiji require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
61 | Al Mu'tarid | Khalifa Bin Zayed The First St, Al Mu'tarid - Al Jizza | 24.2178 | 55.7456 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | Existing or nearby drainage arrangements at Khalifa Bin Zayed The First St, Al Mu'tarid - Al Jizza require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
62 | Al Jahili | Al Marayegh, Al Jahili Area | 24.207 | 55.7482 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Marayegh, Al Jahili Area; require pumping support during storm events. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
63 | Al Muwaiji | Saeed Bin Shakhbout The First St, Al Muwaij'i - Majlood | 24.2108 | 55.7104 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Saeed Bin Shakhbout The First St, Al Muwaij'i - Majlood require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 3 | 15000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
64 | Al Muwaiji | Saeed Bin Shakhbout The First St, Al Muwaij'i - Al Ruwaikah | 24.2058 | 55.7129 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Saeed Bin Shakhbout The First St, Al Muwaij'i - Al Ruwaikah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
65 | Al Muwaiji | Maitha Bint Mohammed St, Al Muwaij'i - Deer Park | 24.2055 | 55.7051 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Maitha Bint Mohammed St, Al Muwaij'i - Deer Park require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | completed | completed | Hand Over Phase | Yes | Completed | Completed | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
66 | Al Nabbagh | Sibeitah, Al Nabbagh 66! | 24.3194 | 55.7535 | Medium | Not Applicable / Not identified |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed intervention at Sibeitah, Al Nabbagh 66!; response is based on tanker dewatering until a drainage network/permanent solution is available. |  |  |  |  | 0 | [9 empty] | 0 | 1 | 5000 | [10 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46753 | No specific plan
67 | Al Nabbagh | Lane 821, Al Nabbagh - Sibeitah | 24.3418 | 55.742 | Medium | Not Applicable / Not identified |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed intervention at Lane 821, Al Nabbagh - Sibeitah; response is based on tanker dewatering until a drainage network/permanent solution is available. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46722 | No specific plan
68 | Al Qattarah | 96-124 Al Dameed St, Al Qattarah - Al Mragha | 24.2651 | 55.7409 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 96-124 Al Dameed St, Al Qattarah - Al Mragha require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 4 | [9 empty] | 20000 | 2 | 10000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
69 | Al Qattarah | 96-124 Al Dameed St, Al Qattarah - Al Mragha | 24.260988° | 55.755669° | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 96-124 Al Dameed St, Al Qattarah - Al Mragha require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
70 | Al Qattarah | 96-124 Al Dameed St, Al Qattarah - Al Mragha | 24.261376° | 55.754789° | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 96-124 Al Dameed St, Al Qattarah - Al Mragha require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
71 | Al Qattarah | Bani Yas St, Al Qattarah - Al Mergab | 24.2717 | 55.7555 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Bani Yas St, Al Qattarah - Al Mergab require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
72 | Al Qattarah | alfurusia roundabout (Equestrianism)- Al Qattarah - Al Mergab | 24.2723 | 55.7603 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at alfurusia roundabout (Equestrianism)- Al Qattarah - Al Mergab require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
73 | Al Qattarah | Bani Yas St, Al Qattarah - Al Mergab | 24.2714 | 55.7536 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Bani Yas St, Al Qattarah - Al Mergab require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
74 | Al Sarouj & Al Noud | Al Qanadeel St, Al Sarouj - Al Harmoozi | 24.2027 | 55.7759 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed interventionat Al Qanadeel St, Al Sarouj - Al Harmoozi require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 5 | 25000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
75 | Al Sarouj & Al Noud | Al Harmoozi, Al Sarouj | 24.1985 | 55.7815 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Harmoozi, Al Sarouj require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
76 | Al Sarouj & Al Noud | Hai Al Wadi, Al Sarouj | 24.1869 | 55.7992 | Very High | Not Applicable / Not identified |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Hai Al Wadi, Al Sarouj require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
77 | Al Sarouj & Al Noud | Al Mashall, Al Sarouj | 24.202 | 55.7857 | Very High | Not Applicable / Not identified |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Al Mashall, Al Sarouj require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
78 | Al Sarouj & Al Noud | Al Harmoozi, Al Sarouj | 24.2012 | 55.7744 | Very High | Not Applicable / Not identified |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Al Harmoozi, Al Sarouj require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
79 | Al Sarouj & Al Noud | 29-23 Al Qutami St, Al Sarouj - Hai Al Wadi | 24.1874 | 55.808 | Very High | Applicable with (AACM) |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at 29-23 Al Qutami St, Al Sarouj - Hai Al Wadi require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
80 | Al Sarouj & Al Noud | Al Mashall, Al Sarouj | 24.1983 | 55.7966 | Very High | Applicable with (AACM) |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Al Mashall, Al Sarouj require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
81 | Al Sarouj & Al Noud | Zayed Bin Sultan St Hai Al Wadi, Al Sarouj | 24.1791 | 55.796 | Very High | Applicable with (AACM) |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Zayed Bin Sultan St Hai Al Wadi, Al Sarouj require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
82 | Al Sarouj & Al Noud | Al Harmoozi, Al Sarouj | 24.2062 | 55.782 | Very High | Not Applicable / Not identified |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Al Harmoozi, Al Sarouj require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-31 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | 46783 | No specific plan
83 | Al Sarouj & Al Noud | Truck R/A Wadi Al Ain 3, Al Noud | 24.1107 | 55.8256 | Very High | Applicable with (AACM) |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Truck R/A Wadi Al Ain 3, Al Noud require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | New Network | New Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | under construction | under construction | Design phase | Yes | - | - | Not Started | AlDar | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
84 | Al Sarouj & Al Noud | ADNOC Station, Wadi Al Ain 2, Al Noud | 24.1233 | 55.8224 | Very High | Not Applicable / Not identified |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at ADNOC Station, Wadi Al Ain 2, Al Noud require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | New Network | New Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | under construction | under construction | Implementation phase | Yes | - | - | On Track | AlDar | TRUE | Topography & Road Engineering | FALSE | CLIENT INPUT REQUIRED | No specific plan
85 | Al Shiwayb | AL SHWAIB FAMILY PARK | 24.74 | 55.7886 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at AL SHWAIB FAMILY PARK require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
86 | Al Shiwayb | Ramlat Al Shuwaib, Al Shiwayb | 24.7321 | 55.7813 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ramlat Al Shuwaib, Al Shiwayb require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-07-01 | 2026-07-01 | Implementation phase | Yes | 2025-07-01 | 2026-07-01 | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | 46204 | No specific plan
87 | Al Shiwayb | Al Shiwayb Rd, Al Shiwayb | 24.7395 | 55.7941 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Shiwayb Rd, Al Shiwayb require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-07-01 | 2026-07-01 | Implementation phase | Yes | 2025-07-01 | 2026-07-01 | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | 46204 | No specific plan
88 | Al Shiwayb | Shibak 2, Al Shiwayb Rd. | 24.6912 | 55.7276 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Shibak 2, Al Shiwayb Rd. require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
89 | Al Tiwayya | 6-8 Al Mu'attar St, Al Markhaniyyah - Muaifaa | 24.250512° | 55.687096° | Medium | applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 6-8 Al Mu'attar St, Al Markhaniyyah - Muaifaa require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 3 | 15000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
90 | Al Tiwayya | Jafeer Obaid, Al Tiwayya | 24.2498 | 55.7022 | Medium | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Jafeer Obaid, Al Tiwayya require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2025-09-16 | 2026-08-10 | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
91 | Al Tiwayya | Ras Ash Sheikh St, Al Tiwayya - Eidan Al Ridda | 24.2549 | 55.6945 | Medium | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ras Ash Sheikh St, Al Tiwayya - Eidan Al Ridda require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-01-01 | 2026-12-01 | Implementation phase | Yes | 2025-11-18 | 2026-08-10 | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | 46357 | No specific plan
92 | Al Tiwayya | Eidan Al Jareh, Al Tiwayya Area | 24.2563 | 55.6922 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Eidan Al Jareh, Al Tiwayya Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | completed | completed | Hand Over Phase | Yes | Completed | Completed | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
93 | Al Wiqan | Um Az Zumoul Rd, Al Wiqan - Saq Al Awir | 23.635 | 55.5678 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Um Az Zumoul Rd, Al Wiqan - Saq Al Awir require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 2 | [9 empty] | 10000 | 5 | 25000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
94 | Al Wiqan | 26th St, Al Wiqan - Al Sayh | 23.6322 | 55.5453 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 26th St, Al Wiqan - Al Sayh require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
95 | Al Wiqan | Al Muhallab St, Al Wiqan - Ramlat Addimah | 23.6412 | 55.5603 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Muhallab St, Al Wiqan - Ramlat Addimah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
96 | Al Quo'a | 40th St, Al Qou' - Al Quo'a Town | 23.4149 | 55.4055 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed intervention at 40th St, Al Qou' - Al Quo'a Town; response is based on tanker dewatering until a drainage network/permanent solution is available. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
97 | Central District | 25 Al Mandhour St, Central District - Hai Al Murabbaa | 24.2221 | 55.7789 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No effective stormwater connection is evident from the listed at 25 Al Mandhour St, Central District - Hai Al Murabbaa require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 4 | [9 empty] | 20000 | 14 | 70000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 47088 | No specific plan
98 | Central District | AI Mut-haf St, Central District - Hai Al Hisn | 24.2162 | 55.7746 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at AI Mut-haf St, Central District - Hai Al Hisn require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
99 | Central District | Al Ain Oasis, Central District | 24.215 | 55.7603 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Ain Oasis, Central District require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
100 | Central District | 33-9 Al Hdaybah St, Central District - Al Talaa | 24.2245 | 55.7887 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 33-9 Al Hdaybah St, Central District - Al Talaa require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
101 | Central District | Al Wisal St, Central District - Al Nyadat | 24.2119 | 55.7942 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Wisal St, Central District - Al Nyadat require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
102 | Central District | 73-67 Al Masarrah St, Central District - Al Kuwaitat | 24.2164 | 55.7788 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 73-67 Al Masarrah St, Central District - Al Kuwaitat require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
103 | Central District | Al Ain Civil Defense | 24.2335 | 55.7504 | Very High | Not Applicable / Not identified |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at Al Ain Civil Defense require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
104 | Central District | 25 Al Sufouq St, Central District | 24.230711° | 55.751657° | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 25 Al Sufouq St, Central District require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-06-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46905 | No specific plan
105 | Central District | 25 Al Sufouq St, Central District | 24.213898° | 55.787167° | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 25 Al Sufouq St, Central District require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
106 | Central District | Hai Al Qasr, Central District | 24.2259 | 55.7542 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Hai Al Qasr, Central District require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
107 | Central District | 12-16 Seasons St, Central District - Nad Al Rusas | 24.2295 | 55.7594 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 12-16 Seasons St, Central District - Nad Al Rusas require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
108 | Central District | Malayim St, Central District - Nad Al Gorban | 24.2323 | 55.7574 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Malayim St, Central District - Nad Al Gorban require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
109 | Central District | Al Sufouq St, Central District - Shiebat Bin Anbar | 24.2286 | 55.7541 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Sufouq St, Central District - Shiebat Bin Anbar require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
110 | Central District | 97-87 Al Anhar St Central District - Nad Al Gorban - Abu | 24.233 | 55.7551 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at 97-87 Al Anhar St Central District - Nad Al Gorban - Abu require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
111 | Falaj Hazza | Falaj Hazza' - Jefeer Jedeed | 24.184456° | 55.711336° | Low | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Falaj Hazza' - Jefeer Jedeed require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 1 | 5000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
112 | Falaj Hazza | Falaj Hazza' - Jefeer Jedeed | 24.170400° | 55.711031° | Medium | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Falaj Hazza' - Jefeer Jedeed require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
113 | Falaj Hazza | 14 شارع السَاسْ, Falaj Hazza' - Jefeer Jedeed | 24.1744 | 55.7187 | Low | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 14 شارع السَاسْ, Falaj Hazza' - Jefeer Jedeed require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
114 | Falaj Hazza | Zkhir Tunnel, Nahyan The First St, Falaj Hazza' - Ramlat Zakher | 24.1683 | 55.7109 | Low | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Zkhir Tunnel, Nahyan The First St, Falaj Hazza' - Ramlat Zakher require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | completed | completed | Hand Over Phase | Yes | Completed | Completed | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
115 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Ain Al Fayda, Ain Al Faydah | 24.0945 | 55.6956 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ain Al Fayda, Ain Al Faydah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 10 | [9 empty] | 50000 | 4 | 20000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-09-01 | 2026-09-01 | Implementation phase | Yes | 2025-09-01 | - | On Track | AAI | TRUE | Inadequate Design Capacity | FALSE | 46266 | No specific plan
116 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Al Bawarij St, Ain Al Faydah - Ain Al Fayda | 24.0961 | 55.7073 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Bawarij St, Ain Al Faydah - Ain Al Fayda require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
117 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Ain Al Fayda, E40 E30 R/A | 24.0797 | 55.6637 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ain Al Fayda, E40 E30 R/A require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
118 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Dihn Al ʹOud St, Mbazzarah Al Khadra - Green Mubazzarah 2 | 24.0785 | 55.73 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Dihn Al ʹOud St, Mbazzarah Al Khadra - Green Mubazzarah 2 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2025-09-01 | 2026-09-01 | Implementation phase | Yes | 2025-09-01 | 2026-08-01 | Completed | AAI | TRUE | Inadequate Design Capacity | FALSE | 46266 | No specific plan
119 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | 6-16 Tawi Tay St, Al Dhahrah - Al Malaleeh | 24.0134 | 55.5614 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 6-16 Tawi Tay St, Al Dhahrah - Al Malaleeh require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
120 | Green Mubazzarah & Ain Al Fayda & Al Dhahrah | Um Az Zumoul Rd, Al Dhahrah - Al Malaleeh | 23.9913 | 55.5711 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Um Az Zumoul Rd, Al Dhahrah - Al Malaleeh require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
121 | Hili | 4 An Nayfah St, Hili - Al Reef | 24.315390° | 55.796974° | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Netwrok Existing or nearby drainage arrangements at 4 An Nayfah St, Hili - Al Reef require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 8 | 40000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
122 | Hili | 91-87 Muslim Bin Yasar St, Hili - Shareat Hili | 24.2878 | 55.7757 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 91-87 Muslim Bin Yasar St, Hili - Shareat Hili require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
123 | Hili | 6 Al Astorlab St - Hili - Eidan Al Mahaba | 24.2813 | 55.7786 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at 6 Al Astorlab St - Hili - Eidan Al Mahaba require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
124 | Hili | 7-3 Irq As Simayh St Hili - Al Reef | 24.3133 | 55.8094 | Very High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at 7-3 Irq As Simayh St Hili - Al Reef require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
125 | Hili | Al Misbah, Hili | 24.2894 | 55.7687 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Misbah, Hili require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
126 | Hili (completed only monitoring) | Al Misbah, Al Athar St. Hili Area | 24.2886 | 55.7765 | Very High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Misbah, Al Athar St. Hili Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
127 | Hili | Hili Archaeological park Roundabout, 55 - Hili - Athar Hili | 24.2898 | 55.7833 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Hili Archaeological park Roundabout, 55 - Hili - Athar Hili require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
128 | Hili | 62-66 Al Hawwami St, Hili - Al Reef | 24.3143 | 55.8089 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 62-66 Al Hawwami St, Hili - Al Reef require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
129 | Hili | Khalfan Bin Matar Al Rumaithi St, Hili - Al Misbah | 24.295611° | 55.767882° | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Khalfan Bin Matar Al Rumaithi St, Hili - Al Misbah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
130 | Hili | Falaj Hili St, Hili - Ugdat Al Husoon | 24.3225 | 55.7851 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Falaj Hili St, Hili - Ugdat Al Husoon require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
131 | Hili | Mohammed Bin Khalifa St, Hili | 24.3088 | 55.7605 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Mohammed Bin Khalifa St, Hili require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
132 | Hili | Imran Bin Talhah St, Hili - Al Nayfa 1 | 24.295 | 55.7616 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Imran Bin Talhah St, Hili - Al Nayfa 1 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
133 | Hili | Ramlat Al Ghabbah St, Hili - Al Nayfa 1 | 24.298 | 55.7656 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ramlat Al Ghabbah St, Hili - Al Nayfa 1 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
134 | Hili | Abu ʹUbaidah Bin Al Jarrah St, Al Fou'ah | 24.2629 | 55.767 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Abu ʹUbaidah Bin Al Jarrah St, Al Fou'ah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
135 | Hili | Al Reef, Hili Area | 24.299888° | 55.801601° | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Reef, Hili Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
136 | Industrial Area | Al Naglah, Industrial Area | 24.2006 | 55.7616 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Local overland flow/road grading conditions at Al Naglah, Industrial Area require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. |  |  |  |  | 3 | [9 empty] | 15000 | 12 | 60000 | [10 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
137 | Industrial Area | Al Naglah, Industrial Area | 24.191192° | 55.764633° | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Local overland flow/road grading conditions at Al Naglah, Industrial Area require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
138 | Industrial Area | Shiebat Al Salam, Industrial Area | 24.1962 | 55.7508 | Very High | applicable with (AACM) |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Shiebat Al Salam, Industrial Area require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | 46722 | No specific plan
139 | Industrial Area | As Siham 2 St, Industrial Area - Leetag | 24.1867 | 55.7583 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Local overland flow/road grading conditions at As Siham 2 St, Industrial Area - Leetag require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
140 | Industrial Area | Sanaiyah Tunnel, Khalid Bin Sultan St, Al Mutaw'ah - Hai Al Musalla | 24.2055 | 55.7608 | Very High | Applicable with (AACM) |  | No | Topography & Road Engineering | Local overland flow/road grading conditions at Sanaiyah Tunnel, Khalid Bin Sultan St, Al Mutaw'ah - Hai Al Musalla require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Topography & Road Engineering | FALSE | 46753 | No specific plan
141 | Industrial Area | Al Aras, Industrial Area | 24.1753 | 55.7637 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Local overland flow/road grading conditions at Al Aras, Industrial Area require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
142 | Industrial Area | Cement Factory R/A Green Mubazzarah 1 | 24.1397 | 55.7375 | Very High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Local overland flow/road grading conditions at Cement Factory R/A Green Mubazzarah 1 require temporary bunding/barriers and operational dewatering until a permanent drainage/conveyance solution is implemented. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
143 | Masakin | 1024 Rd, Masakin - Ghshabah | 24.4289 | 55.7889 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 1024 Rd, Masakin - Ghshabah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 4 | 20000 | [10 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
144 | Masakin | Al Adhamiyah, Masakin | 24.4886 | 55.7722 | Medium | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at Al Adhamiyah, Masakin require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 46722 | No specific plan
145 | Masakin | Al Adhamiyah, Masakin | 24.52 | 55.763 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Adhamiyah, Masakin require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
146 | Nahil | Al Shaqq, Nahil | 24.4646 | 55.6356 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Shaqq, Nahil require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 2 | 10000 | [10 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
147 | Nahil | Masakkin | 24.5112 | 55.5663 | Medium | applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Masakkin require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
148 | Nahil | E95, Nahil - Nahil 5 | 24.4778 | 55.6163 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E95, Nahil - Nahil 5 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
149 | Saih Al Gharbal | E30, Saih Al Gharbal | 24.1312 | 55.5348 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E30, Saih Al Gharbal require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 2 | [9 empty] | 10000 | 2 | 10000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
150 | Saih Al Gharbal | Saih Al Gharbal, Al Rawdah E30 | 24.1269 | 55.5583 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Saih Al Gharbal, Al Rawdah E30 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
151 | Saih Al Gharbal | E30, Al Salamat - Sayh Al Daay, Ar Rawdah Rd | 24.1402 | 55.4859 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E30, Al Salamat - Sayh Al Daay, Ar Rawdah Rd require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
152 | Saih Al Gharbal | E30, Al Salamat - Sayh Al Daay - Ar Rawdh Rd | 24.1407 | 55.4944 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E30, Al Salamat - Sayh Al Daay - Ar Rawdh Rd require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
153 | Al Masoudi | 6-12 Al Mataf St, Al Mas'oudi - Al Gaseemah | 24.2768 | 55.7467 | Medium | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at 6-12 Al Mataf St, Al Mas'oudi - Al Gaseemah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 1 | [9 empty] | 5000 | 1 | 5000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
154 | Al Masoudi | Al Mubtahil St, Al Mas'oudi - Al Gaseemah | 24.2735 | 55.7484 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Mubtahil St, Al Mas'oudi - Al Gaseemah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
155 | Al Masoudi | Tahnoun Bin Mohammed Al Nahyan Rd. Tunnel, Batha Bin Hilal, Al Tiwayya | 24.2746 | 55.7195 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Tahnoun Bin Mohammed Al Nahyan Rd. Tunnel, Batha Bin Hilal, Al Tiwayya require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Underpass drainage system | Upgrade Underpass drainage system | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-02-01 | 2028-01-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46753 | No specific plan
156 | Al Masoudi | Tahnoun Bin Mohammed Al Nahyan Rd. Tunnel, Batha Bin Hilal, Al Tiwayya | 24.274309° | 55.740023° | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Tahnoun Bin Mohammed Al Nahyan Rd. Tunnel, Batha Bin Hilal, Al Tiwayya require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 47088 | No specific plan
157 | Al Masoudi | Al Abtal St, Al Mas'oudi - Manazef | 24.2797 | 55.7316 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Abtal St, Al Mas'oudi - Manazef require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2023-11-01 | 2026-03-01 | Hand Over Phase | Yes | 2023-11-01 | 2026-03-01 | Completed | AAM | TRUE | Inadequate Design Capacity | FALSE | 46082 | No specific plan
158 | Bad Bint Saud | Al Sharf, Bad' Bint Sa'oud | 24.3662 | 55.7293 | Medium | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Sharf, Bad' Bint Sa'oud require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 0 | [9 empty] | 0 | 12 | 60000 | [10 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
159 | Bad Bint Saud | E95, Bad' Bint Sa'oud - Qarn Bint Saud | 24.3883 | 55.7252 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E95, Bad' Bint Sa'oud - Qarn Bint Saud require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
160 | Bad Bint Saud | Qarn Bint Saud, Bad' Bint Sa'oud | 24.4101 | 55.7049 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Qarn Bint Saud, Bad' Bint Sa'oud require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
161 | Bad Bint Saud | Qarn Bint Saud, Bad' Bint Sa'oud | 24.439 | 55.6676 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Qarn Bint Saud, Bad' Bint Sa'oud require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
162 | Bad Bint Saud | E95, Bad' Bint Sa'oud - Qarn Bint Saud. Nahil Rd. | 24.422 | 55.6887 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E95, Bad' Bint Sa'oud - Qarn Bint Saud. Nahil Rd. require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
163 | Sweihan | Ramlat Sweihan 3, Ramlat Sweihan | 24.4576 | 55.3174 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ramlat Sweihan 3, Ramlat Sweihan require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 2 | [9 empty] | 10000 | 10 | 50000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
164 | Sweihan | Sayh Madhran, Al 'Ajban | 24.5642 | 55.1974 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Sayh Madhran, Al 'Ajban require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
165 | Sweihan | Al Taf Rd. Sweihan - Abu Dhabi Rd, Niqa Al Dheeb - Raigha | 24.5033 | 55.2964 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Taf Rd. Sweihan - Abu Dhabi Rd, Niqa Al Dheeb - Raigha require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
166 | Sweihan | Al Taf Rd. Sweihan - Abu Dhabi Rd, Sweihan - Bida Al Samah | 24.3635 | 55.3983 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Taf Rd. Sweihan - Abu Dhabi Rd, Sweihan - Bida Al Samah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
167 | Sweihan | E20, Ramlat Sweihan - Ramlat Sweihan 3 | 24.4572 | 55.3013 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E20, Ramlat Sweihan - Ramlat Sweihan 3 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
168 | Sweihan | Al Taf Rd. Raigha, Niqa Al Dheeb | 24.4817 | 55.3195 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Taf Rd. Raigha, Niqa Al Dheeb require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
169 | Sweihan | Al Taf Rd. Sayh Al Tuwaissah, Al Sad | 24.3034 | 55.4211 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Taf Rd. Sayh Al Tuwaissah, Al Sad require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Pond/Side slope protection | Pond/Side slope protection | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:50 | 105mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2026-11-01 | 2027-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | 46722 | No specific plan
170 | Sweihan | Al Taf Rd. Sweihan - Bida Al Samah | 24.3807 | 55.3889 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Taf Rd. Sweihan - Bida Al Samah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
171 | Sweihan | E20, Niqa Al Dheeb - Niqa Al Dheeb 2 - Sweihan Rd. | 24.4403 | 55.2127 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E20, Niqa Al Dheeb - Niqa Al Dheeb 2 - Sweihan Rd. require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
172 | Sweihan | Ramlat Sweihan 3, Ramlat Sweihan | 24.4671 | 55.3264 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ramlat Sweihan 3, Ramlat Sweihan require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
173 | Sweihan | E20, Sweihan - Ghaffat Rakadh | 24.4682 | 55.3284 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at E20, Sweihan - Ghaffat Rakadh require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
174 | Sweihan | Bida Al Mghanni, Nahil Sweihan Rd. | 24.516553,55.498937 | 55.4989 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Bida Al Mghanni, Nahil Sweihan Rd. require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
175 | Sweihan | 44th St, Sweihan - Shabiat Suweihan | 24.4657 | 55.3405 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at 44th St, Sweihan - Shabiat Suweihan require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
176 | Sweihan | Shabiat Suweihan, Sweihan Area | 24.4679 | 55.3294 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at Shabiat Suweihan, Sweihan Area require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
177 | Zakhir & Neima & Shi'bat Al Wutah | Al Shamali St, Zakhir - Zakhir South | 24.1249 | 55.7007 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Al Shamali St, Zakhir - Zakhir South require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. |  |  |  |  | 1 | [9 empty] | 5000 | 8 | 40000 | [10 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
178 | Zakhir & Neima & Shi'bat Al Wutah | Gafat Al Nayyar, Zakhir | 24.1275 | 55.6824 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Gafat Al Nayyar, Zakhir require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
179 | Zakhir & Neima & Shi'bat Al Wutah | Zakher Wedding Hall | 24.1276 | 55.6879 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Zakher Wedding Hall require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
180 | Zakhir & Neima & Shi'bat Al Wutah | Ramlat Zakher, Zakhir | 24.1756 | 55.6958 | High | Applicable with (AACM) |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at Ramlat Zakher, Zakhir require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan
181 | Zakhir & Neima & Shi'bat Al Wutah | Neima 1, Ni'mah | 24.1177 | 55.7044 | High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at Neima 1, Ni'mah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | Yes | Upgrade Network | Upgrade Network | Permenent | No | - | 1:2 | 23mm depth for 24hr | 1:5 | 47mm depth for 24hr | the information will be provided by end of next week | the information will be provided by end of next week | 2027-01-01 | 2028-12-01 | Design phase | Yes | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | 47088 | No specific plan
182 | Zakhir & Neima & Shi'bat Al Wutah | Neima 1, Ni'mah | 24.149300° | 55.695813° | High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at Neima 1, Ni'mah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
183 | Zakhir & Neima & Shi'bat Al Wutah | Neima 1, Ni'mah | 24.141845° | 55.709916° | High | Applicable with (AACM) |  | No | Absence of Drainage Network | No Network Existing or nearby drainage arrangements at Neima 1, Ni'mah require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | No network | N/A | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Absence of Drainage Network | FALSE | CLIENT INPUT REQUIRED | No specific plan
184 | Zakhir & Neima & Shi'bat Al Wutah | 6 Al Hawayir St Shi'bat Al Wutah - Shiebat Al Watah 1 | 24.1283 | 55.7258 | High | Not Applicable / Not identified |  | Yes | Inadequate Design Capacity | Existing or nearby drainage arrangements at 6 Al Hawayir St Shi'bat Al Wutah - Shiebat Al Watah 1 require pumping support during storm events, indicating insufficient conveyance/storage capacity for peak runoff. | [27 empty] | No | Based on future design | Based on future design | Permenent | No | - | 1:2 | 23mm depth for 24hr | Based on future design | Based on future design | the information will be provided by end of next week | the information will be provided by end of next week | future project | future project | future project | No | - | - | Not Started | AAI | TRUE | Inadequate Design Capacity | FALSE | CLIENT INPUT REQUIRED | No specific plan